| SI | Name of the Package | Status |
| --- | --- | --- |
| CATEGORY-A Order Placed/ Under Execution--Rs 7080 Cr.(Gross) (12 nos.) |  |  |
|  | Rebuilding of COB#2 Stage-1 approval: 30.05.2019 Stage-1 Cost - Rs. 356.31 Crs (Net of ITC) (Battery-225 Crs + Oven M/c-50 Crs+ Silica-29.81 Crs) Stage-2 approval: 17.11.2020 Stage-2- Rs 377.18 Cr. (Net of ITC) ( Battery-245.25 Crs + Oven M/c-53.46 Crs+ Silica-26.80 Crs) /433.58 Crs(Gross) - Effective date of Contract - 15.12.2020 - Schedule completion- 14.05.2023 - 1st Coke pushing-15.11.2024 - PAC-29.03.2025 PM-Shri S K Rout Implementation period: 29 months Executing agency i) Battery Proper-M/s MECON (29 months) ii) Oven Machines-M/s BEC Ltd. (29 months) iii) Silica Brick & Mortar-M/s Dalmia (Bharat) India Ltd. (11 months) Environment Clearance-NA Consent to Establish(SPCB)-NA | RSP PROJECTS STATUS dtd 29.05.2026 Battery Proper - 30.03.2022-1st Milestone-Refractory laying started - 1st Coke Pushing done on 15.11.2024.PAC issued on 29.03.2025. - Gas Mixing Station commissioned on 11.04.2025 - Overall Physical Progress-99.75% Financial Progress(Rs. in Crs.) Gross Cost; Achieved till Mar’26; BE/RE for FY27; Plan till April’26 -BE; Achieved till May’26; Plan for June’26. 433.58; 461.41 (106.43%); 5.0; 0.0; 0.00 Cumulative 461.41 (106.43%); --. Progress of CSP - New CSP is to be connected with existing wharfs#1,2 & 3 during shutdown via 2 streams - Route-1:-Wharf#3 of COB-3 interconnection with new CSP - Route-2:-Wharf#1 of COB-1 & Wharf#2 of COB-2 interconnection with new CSP. - PAC issued on 29.03.2025. Defect Liquidation under progress - Trial run of individual equipments/conveyors of Stream 1 was carried out from 14th to 17th Nov’2025. - Trial Run of Route 1 of CSP successfully done on 16.12.2025. - Route-2 –Trial run completed under operation. - M35 & M36 shutdown job for extension to JH#3 completed. - Commissioning Certificate issued on 26.03.2026. - C5 & C6 Joining of track under progress, M26 & M27 shutdown to be taken after completion of C5 & C6 work . Oven Machine Package(BEC): Commissioning certificate issued on 16.07.2025 Silica Bricks(M/s Dalmia Bharat) Supply of Silica bricks & Mortar-6457 T(Completed) |
|  | Installation Of 4th Slab Caster along with its auxiliaries and a New Ladle Furnace In SMS-II Stage-I approval: 30.05.2019 Stage-I (Net of ITC): Rs. 745.82 Crs Stage-II approval: 21.01.2022 Stage-II(Net of ITC): Rs.970.18 Cr. /1105.23 Cr(Gross) - Effective date of Contract –16.02.2022 - Schedule completion- 15.05.2025 - 1st Heat LHF-11.06.2025 - 1stslab cast-13.10.2025 Implementation period: 39 months PM-Shri P Pedapudi Executing agency-M/s SMS India- Consortium Leader, M/s SMS Group GmbH- Consortium Partner Environment Clearance-issued on 06/11/2019 with validity till 05/11/2029. | - 21.01.2022- Stage-II Sanction received - 21.01.2022- LoA issued. - Contract signed on 16.02.2022. - Kick Off meeting held on 08.03.2022 - 02.06.2022-L-2 network approved, Layout finalized - 21.06.2022-Foundation stone laid Financial Progress (Rs. in Crs.) Gross Cost; Achieved till Mar’26; BE/RE for FY27; Plan till May’26 -BE; Achieved till May’26; Plan for June’26. 1105.23; 897.96 (81.24%); 195.00; 25.00; 66.56 Cumulative 964.52 (87.27%); 10. Progress - Phase-1 activities (Enabling work)-Bulk oil storage, ACVS system, Booster pump house & EOHWT-01 completed on 21.08.2023. - Inter-connection of facilities during 4 days Shutdown of Caster-1 & 2 of SMS-II completed during the period from 04.09.2023-07.09.2023 - Ladle Heating Furnace civil foundation work completed on 20.09.2024 - The second shutdown (Scheduled from 25.11.2024 to 30.11.2024) for rerouting and hook-up of utility lines—including mixed gas, O2, N2, propane, compressed air, sample conveying, argon, service water, drinking water, and steam—at the new gable end of the Caster#4 project was successfully completed two shifts ahead of schedule on November 30, 2024. - Ladle Heating Furnace-1st Heat done on 11.06.2025. - First slab cast successfully completed on 13.10.2025. (Casting Start: 19:51 hrs ¦ Stop: 21:02 hrs ¦ Cast Length: 60,300 mm ¦ Cold Width: 1,275 mm ¦ Thickness: 220 mm ¦ Ladle Weight: 150 MT ¦ Total Slabs: 6) - Ramp-up plan of 36 days to reach 18 heats/day (in the final 7 days) submitted by M/s SMS. - Subsequent heats were taken intermittently as follows:· - 13.10.2025 – 1st Heat· - 30.10.2025 – 1 Heat· - 03.11.2025 – 1 Heat· - 06.11.2025 – 4 Heats - Inaugurated by MoS on 18.11.2025. - Commissioning test completed on 21.01.2026. - Commissioning Certificate issued on 19.03.2026. - LHF PG test under progress(28.05.2026-30.05.2026) Number of heats: Month; Heat/Month. Oct-25; 3. Nov-25; 59. Dec-25; 98. Jan-26; 249. Feb-26; 163. Mar-26; 335. Apr-26; 497. 28- May-26; 155. Delay Reasons& Action Taken - Civil work delays in the LF area due to LM bay front unavailability, caused by tundish-related shifting due to delay in supply of KL Bay crane. WTP, flume tunnel, and EOWHT-2 affected due to poor resource mobilization. - Repeated delays in supplying critical equipments like segments, cranes and molds along with its erection, severely impacted overall project progress. - Structural erection delays due to sub-vendors' inadequate manpower and resources affected subsequent activities, including caster floor civil work due to delayed gable structure dismantling. - As concerns persisted, the matter was escalated to M/s SMS higher management. Engineer’s notice was served to M/s SMS on 25.01.2025 for poor progress in supply and site activities. - In response to these escalations, in a letter dated 21.02.2025, the CEO, Region APAC & MEA, M/s SMS India Pvt. Ltd., reaffirmed their commitment to completing the first cast for Caster-IV by July’2025 - M/s SMS India has submitted a micro-schedule for commissioning by Sept’25. - Equipment erection in Caster run-out area completed. Workshop equipments in MSRS installed. WTP-4 Cooling Tower Completed - Caster run-out area equipment erection, MSRS workshop equipment, WTP-4 Direct Cooling Tower, Mold segment alignment completed. - Turret rotation and arm lifting/lowering trials, hydraulic flushing, WTP-4 pump trials completed and electrical I/O checking completed. - Foreign process expert arrived at RSP on 17.09.2025. - SFT of all critical equipments completed. All major mechanical and electrical works of Caster-IV completed; Signal Function Tests of critical systems done, and integrated trial run done in oct’25.. - Review by Director (I/c), RSP held on 24.06.2024, 19.07.2024, 27.08.2024& 16.10.2024, 22.01.2025,12.03.2025, 18.06.2025, 22.07.2025, 30.08.2025 - ED (P) Monthly review meeting held on 31.07.2024, 28.08.2024, 27.12.2024, 14.01.2025, 19.02.2025, 20.05.2025,26.06.2025, 01.09.2025.APEX level meeting held on 11.04.2025, 15.05.2025, 12.07.2025 Daily ED(P) site review meetings held from July’25 till Oct’25 (First Slab Cast). |
|  | Power Enabling Package For Additional Oxygen/ Nitrogen Gas For Steel Production Stage-I approval:29.07.2022 (received on 08.09.2022) Stage-I cost: Rs.65.53(Net of ITC) Cr. /71.96(Gross) Stage-II approval:27.03.2023 (received on 28.03.2023) Stage-II cost (Net of ITC):Rs 60.40 Cr /69.62 Cr(Gross) RCE(Net of ITC):Rs 72.46 Cr./83.49 (Gross) - Effective date of Contract –11.04.2023 - Schedule completion- 10.09.2024 - Transformer Energised-07.01.2025 Implementation period: 17 months PM-Shri P K Mohapatra Executing agency- M/s Bharat Bijlee EC-issued on 30/03/2022 with validity of 5 yrs i.e. till 29/03/2027 Consent to Establish(SPCB)-issued on 27/10/2022 with validity of 5 yrs i.e. till 26/10/2027 | - Transformer(no load) energized on 07.01.2025. - 12.04.2023-Kick Off meeting held. - 24.04.2023-Survey Work started & completed on 01.05.2023. - Billing schedule & L-2 network approved - M1 payment done in the month of Mar’23 - Ground Breaking-20.06.2023. - Transformer (no load) energized on 07.01.2025. Change Proposal Timeline - 20.01.2024 – Mail sent to CET reagrding fouling of cable routing layout with proposed layout of COB#7 complex - 23.01.2024 & 12.02.2024 – Joint site visits by CET & RSP; alternate route proposed and MOM signed - 18.03.2024 – In-principle approval obtained for soil survey and change proposal - 28.06.2024 – After completion of soil survey & underground mapping Request for change proposal sent to M/s Bharat Bijlee - 17.08.2024 – M/s Bharat Bijlee submitted change proposal - 08.10.2024 – Joint site visit held; MOM signed to finalize foundation locations - 13.12.2024 – Technical offer finalized; M/s BBL initially proposed an implementation schedule of 15 months, which was subsequently revised and finalized at 12 months - 22.01.2025-Price Bid opened (Quoted Price-Rs.13.91 Cr. is 47.37% higher than estimate-Rs 9.44 Cr.) - 13.03.2025 – Three rounds of negotiation were held with M/s Bharat Bijlee on 19.02.2025, 27.02.2025, and 07.03.2025, following which the party submitted their final no-regret price –Rs 10.25 Cr.(Basic) which is 8.57% higher than CET’s estimate of Rs 9.44 Cr. - 20.03.2025 – Change Order Committee recommended the proposal - 05.05.2025 – Competent authority approved the proposal (subject to RCE approval) - 29.05.2025 – Draft board note received from CET.(RCE-Rs 72.46 Cr. (Net of ITC) on base date 2nd Qtr’25 is 19.97% higher than the Stage-II Cost –Rs 60.40 Cr. (Net of ITC) on base date 1st Qtr’2023. - Boardnote approved by Competent authority on 02.07.2025. Proposal for RCE sent to corporate office on 03.07.2025. - CoDheld on 11.07.2025. PAG held on 19.07.2025. PAG observations complied on 23.07.2025. - PCSB held on 11.08.2025. - SAIL Board considered the proposal on 11.08.2025. Board Extract received on 14.08.2025. - Change Order issued on 14.08.2025 with implementation schedule of 12 months i.e. till 13.08.2026. Micro-plan submitted by party on 17.10.2025. Execution Status of Change Order - The charging of equipment at MSDS-VI completed in Jan'25. All job completed except construction of overhead Cable Gallery and laying of 33kV cables - Original length of cable gallery route: 1100 mtr (approx.) - Length of cable gallery route in alternate route: 1550 mtr. - Additional length of cable gallery required- 450 mtr. - Change Order issued on 14.08.2025 with implementation schedule of 12 months i.e. till 13.08.2026.Micro-plan submitted by party on 17.10.2025. - Meeting held in the office of CGM(Projects) on 23.07.2025. M/s BBL agreed to review and compress timelines for supply and erection as requested by RSP to meet the overall project execution target of 31.03.2026 including the change order(~1550 m). - Design and engineering completed. - Detailed micro-plan submitted by party for accelerated completion by May'25 - 33 kV HT Cables delivered on site . Progress:- - Route-1 : under progress - Route-2 : Completed. - Power to supplied to Oxygen plant through route-2 ready. - CGM(P) Monthly review meeting held on 23.07.2025,29.08.2025, 09.09.2025, 23.09.2025,17.10.2025,08.1.2025,24.12.2025,20.01.2026, 10.03.2026 - ED(P) Monthly Review-22.01.2026, 20.02.2026 Financial Progress(Rs. in Crs.) Gross Cost; Achieved till Mar’26; BE/RE for FY27; Plan till May’26 -BE; Achieved till May’26; Plan for June’26. 69.62 Revised 83.49; 60.28 (72.2%); 16.00; 2.0; 2.62 Cumulative 64.90 (75.34%); 2.0. |
|  | Construction of 30 MLD Sewage Treatment Plant for treating sewage from existing pump house at Tumkela Sector-16 along with pumping station at Balughat Sector-16 for Township Stage-I approval: Jan’2023 Stage-I cost(Net of ITC): Rs 105.44 Cr.(Net of ITC) Stage-II approval:June’2023 Stage-II cost:Rs 96.62 Cr (net of ITC)/96.62 Cr(Gross) - Effective date of Contract –29.06.2023 - Schedule completion- 28.03.2025 - Commissioning-15.08.2025 Implementation period: 21 months PM-Shri V K Yadav Executing agency- M/s Bharat G Patel & Oasis EPC solution Ltd. SPCB CTO dtd 15/03/2021 – Special conditions for installation of STP Directions of - CPCB 21.04.2015-revision of thenorms for STP - SPCB dated 31.03.2017- revamp STP with new CPCB norms - SPCB dtd 15.03.2021 | - 09.06.2023-EC in its meeting accorded stage-II approval for the proposal at an evaluated cost of Rs 96.62 Crore(net of ITC on GST-nil) on base date of 1st Qtr,2023 with implementation schedule of 21 mon from effective date of contract. - LoA issued on 09.06.2023. - Party visited RSP on 13.06.2023. - 29.06.2023-Contract signed. - 29.06.2023-Kick Off meeting held. - Soil testing - Balughat Nallah site- completed. - Tumkela Pump house site-Local resistance on 29.07.2023. After intervention of local police authorities (sector-15 PS), work resumed on 31.07.2023. All 3 boring for soil testing completed on 03.08.2023. - M1 payment done in Aug’23. M2 payment done in Oct’23. - 14.08.2023-During contour survey, again local resistance faced. In view of the resistance,support from police sought. In view of resistance Barbed wire fencing Job to be carried out. (Estimate-Rs 8.26 Lakhs). - Contour Survey work resumed & completed on 07.10.2023. - Initial 4 months delay in site handover due to local resistance - Site work started from 03.11.2023. - Site leveling work completed on 27.12.2023. - MBBR media & 6.6 kV (6nos.) transformer supplied - Major Civil work completed on 26.02.2024 - Equipment Erection at various areas(Thickener, MBBR Tanks, etc) under progress. - Phase-1 trial run done on 17.05.2025 (VFD Panels charged, Tiral run of Blower, Effluent filling of Equalixation& Anoxic Tank). - Phase-2 trial done from 13.06.2025 to 17.06.2025.(Equalization tank , MBBR1 &2 , Blower, Aeration testing) - Transformer Charged. PAC issued on 26.07.2025. - Commissioning test done from 12.08.2025 to 15.08.2025. - Inaugurated by DIC on 27.08.2025. - Commissioning Certificate issued on 11.11.2025 w.e.f 15.08.2025. - PG test completed on 10.03.2026. - Delay Analysis Committe formed. - Review by Director (I/c), RSP held on 27.08.2024, 16.10.2024, 14.01.2025, 18.06.2025,22.07.2025 - ED(P) Monthly review meeting held on 24.08.2024, 14.12.2024, 21.01.2025, 17.02.2025, 19.03.2025, 25.04.2025, 19.05.2025, 25.06.2025, 29.07.2025, 12.01.2026 - Letter issued to the agency for completion of all defect points on 29.12.2025 Financial Progress(Rs. in Crs.) Gross Cost; Achieved till Mar’26; BE/RE for FY27; Plan till May’26 -BE; Achieved till May’26; Plan for June’26. 96.62; 87.02 (90.06%); 12.20; 1.0; 0.0 Cumm.- 87.02 (90.06%); 1.2. |
|  | Installation Of 1000 TPD Oxygen Plant at RSP On Construct, Operate &Maintain(COM) Basis Stage-I approval: 01.09.2021(received on 04.09.2021) Stage-I Cost: COM Basis Stage-II approval: 10.08.2023(received on 25.08.2023) Stage-II Cost-com Basis NPV- Rs 1874.42 Cr (-20.99% lower) Estimate-Rs 2372.53 Cr. - Effective date of Contract –24.09.2023 - Schedule completion- 23.02.2026 - Expected Completion-June’26 Implementation period: 29 months PM-Shri B S Dash Executing agency-M/s Linde India Ltd. EC-issued on 30/03/2022 with validity 29/03/2032 Consent to Establish(SPCB)-issued on 27/10/2022 with validity of 5 yrs i.e. till 26/10/2027 | - 01.09.2021: Stage-I sanction accorded Tender History – Summary Consultant Appointment & Tender Initiation - 16.09.2021: NIT issued for appointment of M/s MECON Ltd. as Consultant. - 26.11.2021: Order placed on MECON. - 07.04.2022: Draft NIT documents submitted by MECON - 11.04.2022: Open Tender Enquiry issued (ToD: 11.05.2022). - 25.04.2022: Pre-bid meeting held (Air Water, Inox, Linde participated). Revision & Retendering - Based on bidder request and Consultant’s advice, Eligibility Criteria revised (cryogenic oxygen plant experience increased from 10 to 15 years) to enhance competition. - 11.05.2022: Tender reissued with revised EC (ToD: 10.06.2022). - 20.05.2022: Pre-bid meeting held. - Corrigendum issued incorporating clarifications. - 09.08.2022: Three bids received and opened (after two extensions). - Techno-commercial evaluation completed; all three bidders found acceptable. - 17.04.2023: Reverse Auction conducted based on combined Net Present Value (NPV) for 20 years (10% discount rate), considering: - Monthly hire charges - O&M charges - Power consumption - Water consumption - M/s Linde L-1 price ₹1874.42 Cr (NPV calculated for 20 years with 10% annual discount rate based on Monthly hire charges, O&M charges, Electrical Energy Consumption & Water Consumption) is 20.99% lower than estimate ₹2372.53 Cr. - 27.06.2023: TC recommendation approved by Director I/c, RSP. Stage-II Approval - 25.08.2023- Board Extract received along with sanction letter. - 25.08.2023-LoA issued. - 29.11.2023-Contract signed. - 08.12.2023- Letter sent to the agency for kick off meeting &start of site activity. - 14.12.2023- Kick off meeting held. - M/s Linde has been asked to submit PERT chart time & again. After a recent meeting held with Managing Director on 03.05.2024, communication received on 10.05.2024 expressing inability to submit PERT citing procedural reasons. - Area survey & underground mapping completed - Area development work completed (~57,000 Cum overburden removed) - Soil testing (12.06.2024)& area leveling completed - Order has been placed for all critical and long lead equipments viz. MAC, BAC, Horton’s Sphere, transformers, motors, compressors, etc - Sub-vendor approval given to - M/s Srikali Enterprises on 16.05.2024 for construction power jobs. Work completed on 19.09.2024 - M/s Ray Construction Ltd. on 05.07.2024 for civil work. Preparatory jobs started from 15.07.2024.Civil work started on 22.07.2024. - Physical Progress Activity; Actual in % till May-26. Overall Progress; 92 %. Progress - Major Civil work Completed. - Mechanical Works: - Completed for Cooling tower, cold box ,Main heat Exchanger, cooling tower, pre-purifications units, seal gas tank ,LAR tank - Erection activities for Horton Sphere, LOX & LIN tanks, vaporizers under progress - Piping Works: Underground piping completed; above-ground piping is under progress. - Electrical Works: - 30 MVA HT transformer erections done, LT Transformer-6 nos. erection done, Panel Erection & cable tray work completed. - Cooling tower, Bus duct & Instrumentation , Cable Laying, Testing of Transformer, Earthing work under progress. Delay Reasons& Action taken Delay reasons - Initial delay in start of civil work- Though contract was effective from 24.09.2023, order for civil sub-contractor was placed by M/s Linde only on 05.07.2024 and civil works commenced on 22.07.2024 resulting in a delay of about 10 months in start of civil activities. - Inadequate resource mobilization – Lack of round-the-clock working; delayed mobilization of resources incl. cranes for Horton Spheres, LOX/LIN/AR tanks and Cold Box; shortage of specialized aluminium welders; delay in finalisation and mobilization of sub-contractors for electrical, instrumentation, and piping works. - Delay in supply of critical equipment – Delayed supply of MAC-1, vaporizers, HT motors, seal gas tank, 200 MT LAR VIE, etc., and return of piping materials to workshops for modification, affecting erection schedules. - Delay in erection of above-ground piping works – Slow progress in water and process piping erection. - Increased excavation due to adverse site conditions – Higher earthwork quantities and encounter of hard rock, affecting foundation readiness, particularly for the electrical building Action taken - Continuous Follow-Ups & Escalations made to M/s Linde urging timely execution. - Repeated deliberations, formal communications, and periodic review meetings have been conducted at multiple levels. M/s Linde was repeatedly advised to furnish updated schedules, monthly execution plans, and credible recovery programmes; however, in view of the COM nature of the contract, detailed L-2 schedules were not provided, and monitoring remained dependent on the contractor’s internal planning. - In the last ED(Projects) review meeting held on 15.01.2026, M/s Linde presented a revised action plan indicating commissioning by July’25, which is approximately four months behind the scheduled commissioning of February’25. ED(Projects) advised M/s Linde to further rework the plan with enhanced manpower and resources, ensure simultaneous execution at all available fronts, and closely monitor the supply schedule of balance equipment so as to target completion by June’26 - Review by Director (I/c), RSP held on 27.08.2024, 16.10.2024,14.01.2025, 18.06.2025,22.07.2025 - ED(P) Monthly review meeting held on 24.08.2024, 18.09.2024, 22.01.2025, 25.02.2025, 26.03.2025& 17.04.2025, 05.06.2025, 28.06.2025, 30.07.2025, 01.09.2025,16.10.2025,15.01.2026 .14.02.2026, 11.03.2026,21.04.2026 |
|  | Micro-Pellet Plant on COM Basis Stage-I approval: 14.06.2023 (received on 07.07.2023) Stage-I-Rs 1485/T(Conversion Price) Stage-II approval: 07.06.2024 (received on 01.07.2024) Conversion cost - Rs 748.50/T(-42.78%) Estimate-Rs 1308/T Conversion Cost-Rs 748.50/T Cost- Capital shall be invested by the COM operator - Effective date of Contract –01.08.2024 - Schedule completion- 31.07.2026 Implementation period: 24 months PM-Shri B S Dash Executing agency- M/s Jagannath Steels & Power Ltd. EC-issued on 30/03/2022 with validity 29/03/2032 Consent to Establish(SPCB)-issued on 27/10/2022 with validity of 5 yrs i.e. till 26/10/2027 | - 14.06.2023: Stage-I sanction accorded Tender History – Summary - 26.09.2022 & 30.09.2022: Pre-NIT discussions held with M/s Maco Corporation (India) Pvt. Ltd. and M/s Harsco India Pvt. Ltd. - 12.07.2023: Open Tender Enquiry issued (ToD: 11.08.2023). - 31.07.2023: Pre-Bid meeting held; five parties participated / submitted queries. - 25.08.2023: Corrigendum issued incorporating pre-bid clarifications. - 07.09.2023: Three bids received and opened (after two extensions). - Techno-commercial evaluation completed; all three bidders found eligible. - During evaluation, certain commercial relaxations introduced (off-take increased to 80%, LD modifications, quarterly performance assessment). - Updated estimate revised by Consultant PwC to ₹1308/tonne (from Stage-I estimate ₹1485/tonne). - 05.01.2024: Reverse Auction conducted (Start Bid Price- ₹750/tonne). - M/s Shri Jagannath Steels & Power Ltd. emerged L-1 at ₹748.50/tonne, which is42.78% lower than updated estimate (₹1308/tonne) - 18.04.2024: TC recommendation approved by Director I/c, RSP. Stage-II Approval - 07.06.2024-Proposal was considered by SAIL Board. - 01.07.2024- Board Extract received alongwith sanction letter. - 02.07.2024-LoA issued. - 29.08.2024-Contract signed. - 07.09.2024-Kick Off meeting held. Physical Progress Activity; Actual in % till May-26. Overall Progress; 88%. - Ground breaking done on 06.12.2024 Progress - Design & Engineering completed. - Major long lead Equipments-Eirich mixer, slewing & luffing conveyor delivered at site in Dec’25. - Civil Work –completed(except roads & finishing work of shed#3) - Structural work : Completed except Shed#3 - Equipment Work - Mechanical Erection- Mixers (2 nos.), Conveyor Galleries, slewing & luffing conveyor erection completed - Balance-2nd transformer , screw feeder - Trial and testing of Mixers to start. Delay Reasons& Action taken - Following the award of the contract in August 2024, initial activities such as area survey (carried out between September–October 2024) and soil testing (conducted in December 2024) were completed, along with plot plan preparation and approval in Jan’25. However, despite these preliminary steps, no construction work commenced on-site for an extended period - The matter was persistently followed up and escalated through multiple review meetings chaired by ED (Projects) on 21.01.2025, 26.04.2025, and 20.05.2025, highlighting continued inaction on-site. - Additionally, review meetings were held by CGM (Projects) on 11.11.2024 and again on 12.04.2025 to drive early mobilization and site activity. - A series of communications were issued by Project Manager and CGM (Projects), including emails dated 06.02.2025 and 15.02.2025, and letters dated 14.03.2025, 21.04.2025, 24.03.2025, and 28.04.2025. A letter addressed to the Managing Director of M/s SJSPL was also issued seeking immediate intervention. - During the 20.05.2025 review meeting, M/s SJSPL assured commencement of civil works and presented a detailed action plan aligned with the project schedule - M/s SJSPL also informed that Design & Engineering have been completed. The order for the critical equipment Eirich Mixer has been placed on M/s Eirich, Germany, with delivery expected by October 2025. Orders for other major equipment are under finalization and will be placed shortly. - In line with their commitment, civil works commenced on 30.05.2025 - Review by Director (I/c), RSP held on 14.01.2025, 18.06.2025,22.07.2025 - ED(P) Monthly review meeting held on 21.01.2025, 26.04.2025, 20.05.2025, 28.06.2025,30.07.2025, 09.09.2025,14.10.2025, 06.12.2025, 06.02.2026. |
|  | INSTALLATION OF NEW STAMP CHARGE COB-7 (1 MTPA) ALONG WITH CDCP & BY-PRODUCT PLANT Stage-I approval: 27.04.2022 (received on 30.04.2022) Stage-I Cost -Rs 2566.80 Cr.(Net of ITC)/2882.53 Cr. Stage-II approval: 06.09.2024 (received on 07.09.2024) Stage-II Cost-Rs 4227.34 Cr. (Net of ITC) (+64.69%)/ 4789.03 Cr. Battery Proper - Effective date of Contract –07.10.2024 - Schedule completion- 06.03.2028 ByProduct - Effective date of Contract –04.10.2024 - Schedule completion- 03.03.2028 Implementation period: 41 months PM-Battery Proper-Shri KK Patra PM- CDCP- Shri S. K. Dash PM- By-Product- Shri D. K. Sahoo Executing agency-:- Battery Proper-Consortium of M/s L&T & M/s Thyssenkrupp Industrial solutions A G Private Ltd. CDCP- Consortium of M/s L&T & M/s JV “GIPROKOKS” LLC BPP-Consortium of M/s Hutni Projekt Frydek-Mistek, Czech Republic & M/s Hutni Projects FM (india) Pvt. Ltd EC-issued on 30/03/2022 with validity 29/03/2032 Consent to Establish(SPCB)-issued on 27/10/2022 with validity of 5 yrs i.e. till 26/10/2027 | - 27.04.2022: Stage-I sanction accorded at ₹2566.80 Cr (Net of ITC) Tender History – Summary Pkg-2: Battery Proper - 30.04.2022: NIT issued (TOD: 08.06.2022). - 18.05.2022: Pre-bid meeting held (6 major technology providers participated). - Corrigendum issued on 21.06.2022. - Bid Processing - After 12 extensions, tender opened on 17.03.2023. - Two bids received (BEC Consortium & L&T Consortium). - Only L&T Consortium met financial eligibility criteria. - Price Discovery & Negotiation - 03.08.2023: Decremental price bid opened. - Multiple negotiations held (Aug–Sept 2023). - Final negotiated price: ₹1899.19 Cr (Net of ITC). - Price was 31.79% higher than updated estimate. - Approval - 29.11.2023: PTC recommended award. - 02.12.2023: Approved by Director I/c, RSP. - Further negotiations (Mar–May 2024) as per McKinsey &CoD advice. - Final firmed-up price: ₹1889.02 Cr (Net of ITC). Pkg-3: CDCP with BPTG, Boiler & DM Plant 1st Tender - 30.04.2022: NIT issued. - After 12 extensions, single bid received (BEC Consortium). - Bidder failed financial eligibility → retendered. Retender - 03.06.2023: Retender issued. - Single bid received (BEC Consortium). - Techno-commercially acceptable. - Price Discovery & Negotiation - 25.08.2023: Decremental bid opened. - Negotiations held (Aug–Sept 2023). - Final firmed-up price: ₹744.10 Cr (Net of ITC). Pkg-4: By-Product Plant (incl. BOD & Water Supply System) - 30.04.2022: NIT issued. - Tender opened on 15.03.2023 (after 12 extensions). - Two bids received. - Only Hutni Projekt Consortium found techno-commercially eligible. - 19.05.2023: Decremental bid opened. - Multiple negotiations held (May–July 2023). - Final negotiated price: ₹820.24 Cr (Net of ITC).~9.86% above estimate. - Further negotiation in May 2024 (CoD advice). - Final firmed-up price: ₹820.13 Cr (Net of ITC) Description; Battery Proper; CDCP; By Product. Firmed up price; 1889.02 Cr.; 744.10 Cr.; 820.13 Cr.. Stage-I Cost (3rd Qtr’21); 1067.29 Cr; 518.39 Cr; 491.13 Cr. Package Estimate (3rd Qtr’23); 1441.06 Cr; 637.91 Cr; 746.60 Cr. % age Variation of firmed up price with Stage-I; (+)76.99%; (+)43.54%; (+)66.99%. % age Variation of firmed up price with Pkg. Estimate; (+)31.09%; (+)16.65%; (+)9.85%. Stage-II approval - 27.04.2022- SAIL Board approved the proposal. Sanction order for Stage-I received on 30.04.2022 - Stage-II Cost-Rs 4227.34 Cr. (Net of ITC) (+64.69%) - 07.09.2024- Stage-II sanction received. - 07.09.2024-LoA issued. - Contract Signed : - Battery Proper Along with Oven Machine & Refractories with M/s L&T & M/s Thyssenkrupp on 07.10.2024; Schedule Completion-06.03.2028 - Coke Dry Cooling Plant including BPTG, Gas Fired Boiler and DM Water Plant with M/s BEC Ltd., M/s Giprokoks& M/s CUI on 05.10.2024. Schedule Completion-04.03.2028 - By Product plant including BOD Plant and water supply system with M/s Hutni Projekt Frydek-Mistek, Czech Republic & M/s Hutni Projects India on 04.10.2024. Schedule Completion-03.03.2028 Battery Proper - Contract signed-07.10.2024. Schedule Completion-06.03.2028 - Site visit done with M/s L&T for identification of space for office set up. - Kick off meeting heldfrom 18-20th Nov’24 - Soil investigation started on 12.12.2024, under progress - M1 payment done in Jan’25. - Area survey completed - 20.01.2025-22.01.2025-Engineering meetings held - 22.01.2025-Ground breaking done. - Design &Engg. under progress. - M1 & M2 payment processed. - All major equipments order placed. Supply of major equipments like Primary, Secondary crusher and Stamping, Charging & Pushing Machine done. - Piling work - Piling work (1762 nos. completed out of 1836 nos. as on 30.04.2026) - Piling works completed: Test Piles(05 nos.), Coal silo area(195 nos.) & Battery#7A area (250 nos.), Battery#7B(250 nos.), Buttress Wall 7A(48 Nos), Buttress Wall 7B (48 Nos.), Coal Tower (156 nos.), Intermediate Bench (22 Nos.), Stack Flue Tunnel(38 Nos), End Bench 7B(48 nos.) Pipe rack stockade (40 nos completed.). pipe rack(40 nos.), NTP#1(8 nos.) Primary Crusher House(17 nos.) and Intermediate Storage Hopper Building (21 Nos.) completed, - Piling work under progress in Coke bucket car Track, End Bench-7A, SCPM Track, PECS, Coke Bucket Repair Station, Existing Crusher House Extension, Hammer Exchange, etc. - Civil work - Completed- Coal Handling silo (6 nos. of 41.65 m height completed), Battery#7A (buttress wall, deck slab, waste gas tunnel), Battery #7B ( buttress wall, deck slab) , Compressor room for silo. - Under Progress - Admin Building, Waste gas tunnel, Common flue tunnel 7A&7B, GIS Substation, Chimney, Conveyor Y1–Y2, SCPM(Stamping Charging and Pushing Machine) Track, HPALA Building, Coke Bucket Car Track, NTP-2, DFDS, LBDS, Coal Tower, Cable Gallery, Conveyor Y14 penthouse, Conveyor Y13, Primary Crusher house - TOPR Structures supply completed. TOPR erection started on 28.11.2025. TOPR structural erection along with sheeting completed for Battery#7A, TOPR sheeting under progress for Battery#7B side - Structural Erection : Compressor Room, Battery #7A, CI bend erection, SCPM Track, cable gallery(MSDS-3 to MSDS-6) - Mechanical erection under progress (5MT EOT crane Battery#7B completed) - Refractory erection started in Battery #7A side (1st brick laid on 20.04.2026). quality issues observed with supplied lot . - SCPM machine supplied in Apr’26. Physical Progress Activity; Scope; Cumulative Plan till May’26; Cumulative Achieved till May’26; Plan for June’26. Over All; 100%; 50.60%; 45.00%; 7.0%. Design &Engg.; 2285 Nos.; 2144 Nos. (93.83%); 2019 Nos. (88.36%); 90 (3.94%). Civil; 54781 CUM; 33031CUM (54.26%); 31549.CUM (57.59%); 3308 (5.55%). Structural Supply; 9290 MT; 5952 MT (67.04%); 4313 MT (46.43%); 1259 MT (13.55%). Structural Erection; 9290 MT; 1141 MT (12.28%); 1029 (11.08%); 285 MT (3.07%). Refractory Supply; 25800 MT; 18158MT (70.38%); 16375 MT (63.47%); 2057 MT (7.94%). Electrical Supply; 310 NOs.; 122 Nos. (39.35%); 98 Nos. (31.61%); 26 Nos. 8.39%). Mechanical Supply; 13584 MT; 5298 MT (39%); 4628 MT (34.07%); 1150 MT (8.47%). Mechanical Erection; 13584 MT; 68 MT (0.5%); 124 MT (0.91%); 130 MT (0.96%). Financial Progress(Rs. in Crs.) Gross Cost; Achieved till Mar’26; BE/RE for FY27; Plan till May’26 -BE; Achieved till May’26; Plan for June’26. 2584.41; 768.38 (29.73%); 700; 100; 274.55 Cumm.- 1042.93 (40.35%); 50. - ED(P) Monthly review meeting held on 28.03.2025, 28.04.2025& 29.05.2025, 30.06.2025, 31.07.2025, 29.08.2025,17.10.2025, 22.11.2025, 13.01.2026, 13.02.2026, 21.04.2026 - Review by Director (I/c), RSP held on 18.06.2025,22.07.2025, 20.03.2026 CDCP Earlier Contract - Contract signed-05.10.2024. Schedule Completion-04.03.2028 - Kick Off meeting held on 22.11.2024. - 17.01.2025-18.01.2025-Engineering meetings held - Area surveycompleted. - General layout drawing approved. - Design & Engineering under progress - Showcause notice issued to M/s BEC on 16.04.2025 regarding submission of forged BG. BEC has replied on 30.04.2025. - M/s BEC Ltd. has been banned with effect from 03.06.2025 - Contract Terminated on 09.07.2025. Tendering - Retendered on 27.08.2025 with ToD scheduled on 17.09.2025, - Pre-bid meeting held on 03.09.2025. 5 Parties participated 1. M/s. L&T Limited, Kolkata + GIPROKOKS 2. M/s. MECON Limited, Ranchi 3. M/s. Nippon Steel Engineering India Private Limited, Delhi 4. M/s. Steel Plantech India Private Limited, Kolkata 5. M/s. Cladding Projects Limited, Haryana - TOD extended upto 03.10.2025(1st) - Clarification regarding DMISP from MoS received , TOD further extended upto 10.10.2025 (IInd) - ToD Further extended upto17.10.2025(IIIrd ) - 2 offers received & opened on 17.10.2025 and sent to CET for evaluation - M/s Consortium of M/s. L&T Limited and M/s. SE GIPROKOKS - Consortium of M/s. MECON Limited and M/s. JP STEEL PLANTECH CO. and M/s. Steel Plantech India Private Limited - To expedite technical evaluation, RSP officials deputed at CET Ranchi from 23.10.2025. - TER received on 08.12.2025. TEC & CEC Done on 09.12.2025 - TC held on 09.12.2025 - TC recommendation for opening of revice price bid approved on 10.12.2025 - Opening of the revised price bid was scheduled for 15.12.2025. While M/s L&T Consortium has submitted its price bid, the opening has been extended up to 22.12.2025 at the request of the MECON Consortium. - The price bid was opened on 23.12.2025. M/s L&T and Consortium emerged as the sole bidder for the subject package, with an evaluated price of ₹787.57 crore (net of ITC), which is 2.78% higher than the corresponding estimate of ₹766.30 crore. - First round negotiation held on 26.12.2025, Discount of rupee 1 Cr. Received - Second round of negotiation held on 06.01.2026. Discounted offer awaited. - Third round of negotiation held on 08.01.2026. - L-1 Bidder has offered an overall discount of Rs. 3.93 Crore on original updated price bid. - The consultant – CET submitted PBER on 09.01.2026. As per the PBER, the evaluated price (net of ITC) is Rs. 783.64 Cr, which is 2.26% higher than the estimated cost of Rs. 766.30 Cr (net of ITC) - TC in its meeting held on 09.01.2026 recommended for placement of order on which was approved by CA on 09.01.2026 - Board Note finalised on 13.01.2026 and approved by CA on 13.01.2026. - Proposal for order placement sent to Corporate Office on 13.01.2026. Approval for order placement - Corporate PAG meeting held on 20.01.2026. PAG queries received on 21.01.2026, replied on 23.01.2026 and 27.01.2026(legal opinion received from corporate law on 27.01.2026). - EC in its meeting held on 05.02.2026 accorded approval for award of work. Sanction received on 06.02.2026. Progress - LoA issued on 07.02.2026. - Contract signed on 20.02.2026 for Coke Dry Cooling Plant of Coke Oven Battery No. 7 with the Consortium of Larsen & Toubro Limited & State Institute for Designing Enterprises of Coke Oven and By-Product Plants LLC (JV “GIPROKOKS” LLC). Scheduled completion-20.08.2028. - Draft L-2 schedule for approval submitted by M/s L&T, Observation intimated to M/s L &T , L& T to submit revised schedule for approval. - Design & Engineering under progress.(280 nos. submitted out of 1218 nos. of drawings) - M1 milestone achieved and payment Released in Mar’26. - Ground breaking done on 28.05.2026 By-Product - Contract signed-04.10.2024. Schedule Completion-03.03.2028 - Kick Off meeting held on 21.11.2024 - M/s Hutni visited RSP on 17.12.2024 - 16.01.2025-17.01.2025-Engineering meetings held - Area survey, soil investigation & underground mapping completed - Design & Engg. under progress. - Area leveling completed - Order Placement for all imported items placed. - Order Placement indigenous supplies under progress. - Ground breakingdone on 31.07.2025. - Civil work - Completed:- LCSS-1 building, Exhauster machine foundation, PGC foundation, Tar Separator Plant (TSP) & Detarred Ammonia Plant (DAP) foundation, Tar tank foundation in old CCD Site B, Tar separator - Under progress in Gas Distribution Plant, Workshop building, Coarse Condensation Plant(Decanter), Fine Condensation Plant, Gas Liquor Tank, BOD & ZLD area (Clariflocculator), Tar tank in Old CCD Site-B, scrubbing plant, area reapir shop, cooling tower. - Mechanical work under progress in Tar Tank in Old & New CCD Site, & DAP tank Physical Progress Activity; Scope; Cumulative Plan till May’26; Cumulative Achieved till May’26; Plan for June’26. Over All; 100%; 18.51%; 14.75%; 1.60%. Design &Engg.; 1148 Nos.; 1036 Nos. (90.17%); 730Nos. (63.53%); 52 Nos. (4.53%). Civil; 20000 CUM; 4666 CUM (23.33%); 3753.60 CUM (18.77%); 550 CUM (2.75%). Piping Supply; 11000 Mtr.; 8000 Mtr. (72.73%); 8000Mtr (72.73%). Equipment Supply; 806 NOs.; 12 Nos. (1.49%); 7 Nos. (0.87%); 16 Nos. (1.99%). Financial Progress(Rs. in Crs.) Gross Cost; Achieved till Mar’26; BE/RE for FY27; Plan till May’26 -BE; Achieved till May’26; Plan for June’26. 1140.07; 58.90 (5.17%); 315; 20; 41.43 Cumm.- 100.33 (8.80%); 10. - Review by Director (I/c), RSP held on 18.06.2025,22.07.2025,09.03.2026 - ED(P) Monthly review meeting held on 29.03.2025, 25.04.2025, 28.05.2025, 30.06.2025, 31.07.2025,15.09.2025, 30.10.2025, 06.12.2025,22.01.2026, 03.03.2026, 23.04.2026, 22.05.2026. |
|  | Installation of 4th Stove for BF-5 Stage-I approval: 31.01.2022 (received on 11.02.2022) Approval of change in implementation schedule & consequent change in Stage-I approved cost : 02.12.2023 (received on 14.12.2023) Stage-I Cost - Rs 65.00 Cr. (Net of ITC)/Gross-74.82 Cr Revised Stage-I Cost- Rs 66.77 Cr. (Net of ITC)/Gross-76.59 Cr Stage-II approval: 20.01.2025(received on 23.01.2025) Stage-II Cost-Rs 104.28 Cr. (Net of ITC) (+56.18%)/ 120.51 Cr. - Effective date of Contract –10.02.2025 - Schedule completion- 09.10.2026 Implementation period: 20 months PM--Shri M D Tirkey Executing agency-:- M/s Primetals Technologies India Pvt.Ltd.. EC-issued on 30/03/2022 with validity 29/03/2032 Consent to Establish(SPCB)-issued on 27/10/2022 with validity of 5 yrs i.e. till 26/10/2027 | - 31.01.2022: Stage-I sanction – Rs 65.00 Cr (Net of ITC) with 16-month implementation period. Tender History – Summary 1st Tender - 21.02.2022: LTE issued to M/s Paul Wurth, DCI & PTI. - 06.05.2022: Two bids received (after extensions). - 25.07.2022: Techno-commercial evaluation completed; bidders retained major deviations. - 06.01.2023: Tender cancelled to re-tender with revised TS/EC. Revision & Approvals - Jan–Feb 2023: Pre-NIT discussions held to enhance participation. - Proposal revised considering updated prices and implementation period extended to 20 months. - 26.07.2023 (CoD) & 29.07.2023 (Corporate PAG): Proposal cleared. - 11.12.2023: EC approved schedule revision (16 → 20 months) and revised cost to ₹66.77 Cr (Net of ITC) on base date Q4 2021. 2nd Tender - 16.12.2023: Fresh LTE issued to M/s SMS India, DCI & PTI. - 15.02.2024: Three bids received. - 24.05.2024: Price bids opened; M/s PTI emerged L-1 at ₹90.96 Cr. - After negotiations, final “no regret” price of ₹90.26 Cr received on 30.09.2024. - 08.10.2024: TC recommended placement of order (12.61% above package cost). - 22.10.2024: Proposal forwarded to CO for Stage-II approval. Stage-II Approval - 20.01.2025-EC meeting held - 23.01.2025-Stage-II sanction received. - 23.01.2025-LoA issued. - 10.02.2025-Contract signed - 24.02.2025-Kick Off meeting held. 25.02.2025-Engineering meeting held. Physical Progress Activity; Scope; Cumulative Plan till May’26; Cumulative Achieved till May’26; Plan for June’26. Over all Progress; 100%; 63.40%; 47.60%; 19.99%. Design & Engineering; 223 Nos.; 223 Nos (100%); 223 Nos (100%); --. Civil; 72 Cum; 72 (100%); 71 (98.61%); --. Structural Supply; 70 MT; 15MT (21.43%); 0 MT (0%); 25 (35.71%). Structural Erection; 70 MT; 10 MT (14.29%); 0 MT (0%); 25 (35.71%). Equipment Supply; 790 Nos.; 582 Nos. (73.67%); 530 Nos. (67.09%); 120 Nos. (15.19%). Equipment Erection; 790 Nos.; 288 Nos. (36.46%); 202 (45.57%); 150 Nos. (18.99%). Refractory Supply; 4000 MT; 2964 MT (74.10%); 1813 MT (45.32%); 1036 (25.90%). Refractory Erection; 4000 MT; 2000 MT (50%); 0 MT (0%); 1415 MT (35.78%). Financial Progress(Rs. in Crs.) Gross Cost; Achieved till Mar’26; BE/RE for FY27; Plan till May’26 -BE; Achieved till May’26; Plan for June’26. 120.51; 22.74 (18.87%); 55.00; 10; 13.49 Cumm.- 36.23 (30.01%); 5. Progress - M1& M2 payment done in Apr’25 - Design & Engineering under progress.(Basic Engg. Completed, Detail Engg. under progress) - Order placed for Ceramic Burner ,Stove valves, Stove shells, gobble valve & vent valve of mixed gas line - Team from RSP visited ISP, Burnpur on 27.06.2025 & 28.06.2025 for detailed study of erection approach and bottlenecks faced during execution of similar project(stove of ISP) by M/s Primetals - Ground breaking done on 26.08.2025 - Civil Work Started from 23.09.2025 - Design & Engineering completed - Civil work completed for Gas Analyzer room and under progress for valve stand & duct foundation. - All 16 Nos. tier stove shells and 10 nos. domes delivered, assembly and erection of stove shells under progress. T-1 to T-10 erected on foundation, T-11 to T-13 ready for erection, T-15,16 shell plate alignement and welding under progress. - Stove Valves reached at port on 16.05.2026. - Engineer’s notice issued to M/s PTIN for slow progress on 19.05.2026 - Review by Director (I/c), RSP held on 18.06.2025,22.07.2025. - Review by ED(P) : 09.10.2025, 04.12.2025,12.01.2026, 16.02.2026, 09.04.2026, 26.05.2026. |
|  | Pellet Plant on COM Basis Stage-I approval: 29.10.2021 (received on 22.12.2021) Stage-I Cost – COM Basis Stage-II approval: 10.01.2025 (Board Extract received on 15.01.25) Stage-II Cost– COM Basis Conversion cost- Rs 2061/T(-13.04%) Estimate-Rs 2370/T Conversion Cost-Rs 2061/T - Effective date of Contract – 14.02.2025 - Schedule completion- 13.02.2027 Implementation period: 24 months PM-Shri D K Sahoo Executing agency-:- Consortium of M/s Odisha Metaliks& Rosemary Sponge & M/s Ispat Private Limited EC-issued on 15.12.2016 with validity till 14.12.2026 Consent to Establish(SPCB)-issued on 13/12/2022 with validity of 5 yrs i.e. till 12/12/2027 | - Stage-I approval accorded (29.10.2021). Tender History – Summary - 02.11.2021: Proposal received from CET, Ranchi for engagement of PwC as consultant. - 28.02.2022: A/T placed on M/s PwCPL with delivery schedule of 12 months. - 12.09.2022: PwC submitted final RFP document, Service Agreement & Financial Model. 1st Tender Process - 16.09.2022: First NIT issued; Pre-bid held on 28.09.2022. - Oct–Nov 2022: Corrigendum issued; ToD extended; two bids received and opened on 06.12.2022. - Dec 2022 – Feb 2023: Detailed techno-commercial evaluation, clarifications, bidder meetings, and TEC/CEC completion. - 09.03.2023: Approval for opening of Price Bid. - 24.03.2023: Price bid opened; Consortium of Odisha Metaliks& Rosemary Sponge emerged L-1. - April – June 2023: Detailed price evaluation, reasonability analysis, and multiple rounds of structured negotiations held; consultant review of conversion cost undertaken. - July 2023: Final deliberations and assessment of price non-reduction. - 10.08.2023: Approval for cancellation of tender and re-tendering. Re-Tender Process - 25.08.2023: Fresh NIT issued. - Sept–Oct 2023: Pre-bid, corrigendum, and receipt of three bids. - Oct–Nov 2023: Techno-commercial meetings; deviations resolved. - 14.12.2023: Reverse Auction conducted; M/s Odisha Metaliks emerged L-1. - Jan 2024: Price evaluation and negotiation; final quoted price ₹2470/Tonne (~4.24% above estimate). - 05.02.2024: TC recommendation approved. - 15.02.2024: Proposal forwarded to Corporate Office for Stage-II sanction. - As advised CoD further negotiations held, Final Price-Rs 2061/T (~13.04% below estimate) Stage-II Approval - 10.01.2025-SAIL Board meeting held. - 15.01.2025-Board Extract received - 16.01.2025-LoA issued - 29-31.01.2025-Discussions held for finalisation of service agreement. - 14.02.2025-Contract signed. - 20.02.2025-Kick Off meeting held. Physical Progress Activity; Actual in % till May’26. Overall Progress; 77%. Progress - Ground breaking done on 26.02.2025. - Area grading , removal of overburden(1.5 lakh cubic meters) and underground mapping completed. - Design & Engineering Completed. - Major civil work completed. Balance civil work mainly pertains to pellet storage yard, stacker cum reclaimer, finishing work etc - Equipment supply under progress.(approx 85% completed) - Structural erection under progress (PD Building, TG building, grinding, filter press, etc) - Equipment erection completed TG building, annular cooler, balling mill, thickener, screens & under progress for filter press, grinding mill, hydrocyclone, ESP, etc - 120m chimney of pellet plant completed on 26.05.2026 - RSP has accorded permission to proceed with additional storage yard, facilitated round the clock entry of construction materials, construction & operation of canteen, assembly of bins inside RSP. - Review by Director (I/c), RSP held on 18.06.2025,22.07.2025,23.03.2026 - ED (Project) review meeting held on 29.04.2025, 30.05.2025, 30.06.2025, 30.07.2025, 28.08.2025, 11.10.2025, 05.12.2025,19.02.2026, 20.05.2026. |
|  | Implementation of Treatment System-2 under ZLD Stage-I approval: 10.06.2021 (received on 16.06.2021) Stage-I Cost – Rs. 156.22 Cr. (Net of ITC)/177.22 Cr.(Gross) Stage-II approval: 21.02.2025 (received on 28.02.25) Stage-II Cost– Rs. 187.29 Cr. (Net of ITC)/216.02 Cr.(Gross) - Effective date of Contract – 12.03.2025 - Schedule completion- 11.09.2026 Implementation period: 18 months PM-Shri V K Yadav Executing agency-:- Consortium of M/s Effwa Infra & Research Pvt.Ltd.,Thane&M/s SMC Resources SDN, Malaysia Environment Clearance-NA Consent to Establish(SPCB)-NA | Tender History – Summary 1st Tender (17.06.2021 – 26.04.2022) - 17.06.2021: NIT issued. - 31.08.2021: Three bids received (after 4 extensions). - 27.10.2021: Techno-commercial evaluation completed (2 parties eligible). - Despite multiple communications, bidders did not agree to a common competitive platform (RA/Price Bid). - 26.04.2022: Tender cancelled. 2nd Tender (19.07.2022 – 10.02.2024) - 23.06.2022: MECON submitted revised EC. - RA provision deleted; eligibility criteria modified to enhance competition. - 19.07.2022: Fresh NIT issued. - 12.09.2022: Five bids received (after 3 extensions). - Nov 2022: Techno-commercial evaluation completed (all 5 parties eligible). - 18.11.2022: Price bid opened; M/s VA Tech Wabag emerged L-1. - 16.12.2022: Proposal sent to CO for Stage-II approval. - 20.04.2023: Proposal returned due to debarment of M/s Wabag by Delhi Jal Board. - 14.08.2023: Proposal resubmitted after Hon’ble High Court of Orissa judgement in favour of M/s Wabag. - 06.11.2023: PCSB revalidated Stage-I and recommended RCE (Stage-II cost ~40% higher). - 10.11.2023: SAIL Board deliberated and advised re-tendering due to delay, cost escalation and legal complexities. - 10.02.2024: Tender cancelled; bidder informed. - 21.02.2024: Writ petition filed by M/s Wabag before Hon’ble High Court. 3rd Tender - 13.02.2024: NIT issued. - 22.02.2024: Pre-bid held (8 participants). - 19.03.2024: Seven bids received (after 1 extension). - 22.05.2024: Techno-commercial evaluation completed (6 parties eligible). - 28.05.2024: Price bids opened; Consortium of M/s Effwa& M/s SMS Resources emerged L-1. - Interim court order directed tender not to be finalized; subsequent hearings extended the stay. - 21.08.2024: Proposal sent to CO for Stage-II approval. Stage-II approval - 31.08.2024: L-1 offered voluntary discount; revised cost ₹193.91 Cr (31.05% below estimate of ₹281.23 Cr incl. O&M). - 02.09.2024: CoD held; interim order continued. - 13.09.2024: Negotiation held (no further discount). - 17.01.2025: Hon’ble High Court verdict pronounced in favour of RSP. - 21.02.2025-EC meeting held. - 28.02.2025-Stage-II sanction received. - 28.02.2025-LoA issued. - 12.03.2025-Contract Signed. - 12.03.2025-Kick Off meeting held Physical Progress Activity; Scope; Cumulative Plan till May’26; Cumulative Achieved till May’26; Plan for June’26. Over all Progress; 100%; 84.38%; 78.93%; 7.25%. Design & Engineering; 443 Nos.; 443Nos (100%); 443Nos (100%); --. Civil -RCC; 9000 Cum; 8889.86 CUM (98.78%); 8837 CUM (98.19%); 34.97 Cum (0.39%). Structural Supply; 50 MT; 50 MT (100%); 50 MT (100%); --. Structural Erection; 50 MT; 27 MT (54%); 17 MT (34.00%); 23 MT (46.0%). Equipment Supply; 570 NOs.; 555 Nos. (97.89%); 492 Nos. (86.32%); 12 Nos. 2.11%). Equipment Erection; 570 Nos.; 107Nos. (18.77%); 139 Nos. (24.39%); 150 Nos. (26.32%). Financial Progress(Rs. in Crs.) Gross Cost; Achieved till Mar’26; BE/RE for FY27; Plan till May’26 -BE; Achieved till May’26; Plan for June’26. 216.02; 0.01 (0.005%); 90; 18; 26.04 Cumm.- 109.69 (50.78%); 9. Progress - Design & Engineering under Progress.(Basic Engg. Completed, Detail Engg. under progress) - M1 & M2 payment done. - Area levelling & survey work completed - Piling work started from 22.07.2025. - Design & Engg completed. - Pilling work (508 nos.) Completed. - Civil work - Completed for Common collection sump(CCS), Filtration area, Electrical building, UFRO pump house(SMS-II), - Under progress for UF-RO, Emergency Over Head Tank, SLF, Equalization Tank, Chemical Building, Filter Press Building, Dyke area, FW Pump House, PBS UF Pump House etc - Pipeline laying is progressing at site, with hydro testing works also in progress - Erection under progress under progress for CCS, Electrical Building (PCC Panel & Cable Tray Installation), UF Pump House (Pump Alignment), and SMS-II UF-RO Building cum Pump House (MCC Alignment & Coupling, Air Blower System and associated equipment installation activities). - Engineers Notice issued on 07.10.2025 for delay in UFRO pilling work - Review by Director (I/c), RSP held on 18.06.2025, 22.07.2025. - Review By ED: 01.09.2025, 09.10.2025, 05.12.2025,23.01.2026, 15.04.2026, 23.05.2026. |
|  | Replacement of one EOT Crane (250+75/10)t in converter charging bay of SMS-2 Stage-I approval: 07.06.2024 (received on 01.07.2024) Stage-I Cost – Rs. 65.04 Cr. (Net of ITC)/ 74.61 Cr.(Gross) Stage-II approval: 28.04.2025 (received on 05.05.2025) Stage-II Cost– Rs 75.87 Cr.(Net of ITC)/87.48 Cr.(Gross) - Effective date of Contract – 28.05.2025 - Schedule completion- 27.11.2026 Implementation period: 18 months PM-Shri M D Tirkey Executing agency-:- M/s Anupam Industries Limited, Ahmedabad Environment Clearance-NA Consent to Establish(SPCB)-NA | Stage-I approval: Approved on 07.06.2024, cost-Rs 65.04Cr.(Net of ITC) Tender History – Summary - 06.07.2024: NIT issued. - 18.07.2024: Pre-bid meeting held; M/s Anupam Industries Ltd. and M/s Mukand Ltd. participated. - 04.10.2024: Two bids received and opened (after 2 extensions). - 04.11.2024: Tender Evaluation Report (TER) received from CET. - 05.11.2024: Techno-commercial evaluation completed; both bidders found suitable. - 19.11.2024: Reverse Auction conducted; M/s Anupam Industries Ltd. emerged as L-1 bidder. - Dec 2024 – Feb 2025: Four rounds of negotiations held (10.12.2024, 23.12.2024, 14.01.2025 & 04.02.2025). - 10.02.2025: TC recommended order placement. - 13.03.2025: TC recommendation approved. - 27.03.2025: Draft Board Note approved and proposal sent to Corporate Office for Stage-II approval. Stage-II approval - 28.04.2025-EC meeting held. - 05.05.2025-Stage-II sanction received. - 05.05.2025-LoA issued. - 28.05.2025-Contract Signed. - Kick Off meeting held on 29.05.2025 Progress - Design & Engineering completed - Manufacturing under progress(Mechanical inspection done from 19.05.2026 to 21.05.2026; Inspection of control panels done from 19.05.2026 to 22.05.2026.) Physical Progress Activity; Actual in % till May’26. Overall Progress; 10.00%. Gross Cost; Achieved till Mar’26; BE/RE for FY27; Plan till May’26 -BE; Achieved till May’26; Plan for June’26. 87.48; 10.12 (0.005%); 47.00; 20; 1.61 Cumm.- 11.73 (13.61%); 15. |
|  | Product Testing Laboratory for NPM, SPP & NHSM Stage-I approval: 28.12.2023 (received on 22.05.2024) Stage-I Cost – Rs. 164.40 Cr. (Net of ITC)/ 186.80 Cr.(Gross) Stage-II approval: 02.06.2025 (received on 05.06.2025) Stage-II Cost– Rs 137.99Cr.(Net of ITC)/155.26Cr.(Gross) - Effective date of Contract – 04.07.2025 - Schedule completion- 04.08.2027 Implementation period: 25 months PM-Shri P K Nanda Executing agency-:- M/s Sterling& Wilson Environment Clearance-NA Consent to Establish(SPCB)-NA | Stage-I approval: Approved on 28.12.2023, Cost-Rs 186.80Cr.(Net of ITC). Stage-I Stage-I sanction formally received after addressing Board observations on 22.05.2024. Tender History – Summary Finalization of Technical Specification (TS) - 15.06.2024: Revised TS finalized to comply with Make-in-India (MII) provisions and GFR guidelines. - Local content requirement ensured (minimum 50%). - Preferred manufacturers list reviewed by CSIR-NML; expert opinion obtained. Tender Process (15.06.2024 – 27.03.2025) - 15.06.2024: NIT issued. - 25.06.2024: Pre-bid meeting held. - 27.08.2024: Five bids received (after 2 extensions). - 15.10.2024: TER received. - 25.01.2025: Techno-commercial evaluation completed; 3 bidders found eligible. - Detailed verification of local content (MII) declarations undertaken. - 05–06.02.2025: Reverse Auction conducted. - 13.02.2025: RA Report & Price Evaluation received. - 19.02.2025: Tender Committee recommended award. - 11.03.2025: Recommendation approved. - 27.03.2025: Draft Board Note approved and proposal sent to Corporate Office for Stage-II approval. Stage-II approval - 02.06.2025-Proposal considered by EC - 05.06.2025-Stage-II sanction received - 05.06.2025-LoA issued - Contract signed on 04.07.2025 , Schedule completion 04.08.2027 - Kickoff meeting held on 04.07.2025. Progress - Design &Engg. under progress - Ground Breaking done on 03.11.2025. - 1st milestone(M1) achieved & payment done in Dec’25. - Enabling activities completed in Dec’25. - Civil work - Completed for parking shed & Scrap shed - Under progress for Main Lab Building, Macro Etching, DWTT - Equipment Supply under progress: XRF, OES, Profile Projector, Image analyzer Transformer, Vertical Milling Machine FESEM, Hardness testing Machine arrived at Site. - Review By ED(Projects)-15.04.2026 - Physical Progress Activity; Scope; Cumulative Plan till May’26; Cumulative Achieved till May’26; Plan for June’26. Over all Progress; 100%; 39.80%; 39.65%; 4.25%. Design & Engineering; 320 Nos.; 270Nos (84.38%); 278Nos. (86.88%); 30 (9.4%). Civil -RCC; 2500 cum; 766.3 cum (30.65%); 1056.4 cum (42.26%); 240 (9.60%). Structural Supply; 25 MT; 25 MT (100%); 20.5 MT (82.0%); 0 (0%). Structural Erection; 25 MT; 4 (16%); 3.5 (14%); 2 (8%). Equipment Supply; 135 Nos.; 46 Nos. (34.07%); 46.0Nos. (34.07%); 2 (1.48%). Financial Progress(Rs. in Crs.) Gross Cost; Achieved till Mar’26; BE/RE for FY27; Plan till May’26 -BE; Achieved till May’26; Plan for June’26. 155.26; 27.94 18.00%); 50.0; 6; 21.8 Cumm.- 49.74 (32.04%); 6. |
| Highlights: - CAPEX FY2025-26 - Target RE- Rs 2152.5 Cr., Achieved- Rs 2155.44 Cr. (100.14%) - 1000 Safe mandays achieved in projects department on 01.05.2026. - 120m chimney of pellet plant completed on 26.05.2026 - LHF PG Test under Progress( 28.05.2026 to 30.05.2026) |  |  |
| CATEGORY-B Stage-I approved-Rs 367 Cr.(Gross) (1 nos.) |  |  |
|  | Transportation of Coal from COB#6 to COB#1-5 along with installation of Silos Sanctioned Cost- Rs. 323.67 Cr. (Net of ITC)/ 367.15 Cr.(Gross) 1st Tender Consultant Estimate –Rs 337.63 Crs L-1 cost-Rs 455.59Crs Implementation period: 35 months PM-Shri S K Rout - Stage-I approval timeline: - Proposal sent to CO:31.07.2023 - CoD-21.08.2023 - Corporate PAG-08.11.2023 - PCSB-22.12.2023 - SAIL Board-28.12.2023 Stage-I approval: 28.12.2023 (received on 02.02.2024) - NIT issued -08.02.2024 (Retendered on 29.03.2025) EC-NA Consent to Establish(SPCB)-issued on 06/02/2024 with validity of 5 yrs i.e. till 05/02/2029 | - Proposal sent to CO on 31.07.2023 - 21.08.2023-CoD meeting held - 27.10.2023- Reply to observations of COD complied. - Corporate PAG held on 08.11.2023. Observations received on 09.11.2023, complied on 24.11.2023. - 22.12.2023- PCSB held. - 28.12.2023- Proposal Considered by Board. - 02.02.2024-Sanction letter received. - 06.02.2024-Pre-NIT held with bidders - 08.02.2024-TS received from CET 1st Tender - 08.02.2024-NIT issued with ToD on 08.03.2024. - Pre-bid meeting held on 22.02.2024. 8 participated. - Indure Pvt. Ltd. - BTL EPC Ltd. - MacmetEngg. Ltd. - Kalpataru Projects International Ltd. - MacwberBeekay - Mecon Ltd. - SEPC Ltd. - Tata Projects Ltd. - 12.04.2024-3 offers received & opened - Indure Pvt. Ltd., New Delhi - MECON, Ranchi - MacmetEngg. Ltd., Kolkata - M/s. MECON Ltd. retained 11 nos. of commercial deviations. Both M/s. MECON Ltd. & M/s. MACMET Engineering Ltd. have not accepted the Reverse Auction clause - 25 & 28.05.2024-TC meeting held for recommendation of 11 nos. of deviations & opening of revised price bids. TC Recommendations approved on 05.06.2024. - 24.06.2024- Price bids opened. M/s IndurePvt. Ltd. emerged as L-1 bidder. L-1 Price-Rs 475.10 Cr. ,Pkg cost estimate –Rs 312.63 Cr. - 03.07.2024- Price bid evaluation report received from CET. L-1 bidder is 52.17% higher than estimate. - 09.07.2024- Negotiations held. - 15.07.2024-Reply received from L-1 bidder. Party submitted their justification along with BOM, Break-up of civil & structural quantities, Design consideration for Silos etc. towards their quoted prices against the project. - 17.07.2024-The justification/s submitted by the L-1 bidder is forwarded to CET. - 31.07.2024-03.08.2024: Joint meeting held at CET, Ranchi for detail discussion with the L-1 bidder w.r.t. scope and their quoted prices. - 08.08.2024- As per discussions held during the TC meeting, the Consultant-CET is requested to forward their views/ recommendations on the justifications/ documents provided by the L-1 bidder towards further processing of the tender after the joint meeting held at Ranchi. - 12.08.2024-M/s Indure submitted their justification for their quoted prices. - Reminder sent to CET on 14.08.2024.Reply from CET received on 20.08.2024. Further CET vide their mail dtd 23.08.2024 indicated that the overall cost impact will be approx. Rs. 50 Cr. to Rs. 55 Cr. after considering the additional quantities as per the L-1 bidder - 23.08.2024-TC meeting held. A Team comprising of members from Projects Deptt., Coke Ovens deptt. and F&A- deptt. of Rourkela Steel Plant shall visit CET, Ranchi to examine and discuss with the Consultant-CET in order to make comparative analysis of the Pkg. Cost estimate vis-a-vis the quoted price of L-1 bidder w.r.t. scope of work mentioned in T.S. &Drg. and submit detailed report to Tender committee - 03.09.2024-04.09.2024-Meeting held at Ranchi. - 05.09.2024-MoM received. Bidder requested to submit revised offer as per discussion. Civil & Structural quantity was reviewed, CET observed there is an increase in quantities accordingly the impact on estimate is around Rs 20-25 Cr. - 06.09.2024-Negotiations held. Party sought time to submit revised offer. - 30.09.2024-Discounted Price submitted by the party-Rs 455.59 Cr. - 07.10.2024-Item-wise price breakup submitted by the L-1 bidder, under evaluation - 10.10.2024-TC meeting held. CET has indicated that implication due to increase in the estimated quantity of work (for Civil & Structural) is Rs.20-25 Cr. (approx). If the same is taken into account, the reassessed cost estimate for the Package would be Rs.337.63 Cr. (approx) in which case the revised quoted price of L-1 bidder (Rs 455.94 Cr.) is 35.04% higher. - 19.10.2024 & 30.10.2024-TC Meeting held. - 02.11.2024-Case referred to consultant CET for reasonability of price. - 08.11.2024-Reply from CET received. - 28.02.2025-TC minutes for cancellation of tender approved on 08.03.2025 - 08.03.2025-Tender Cancelled. 2ndTender - 29.03.2025-Retendered with ToD scheduled on 26.04.2025. - Pre-bid meeting held on 08.04.2024. 8 participated - Indure Pvt. Ltd. - BTL EPC Ltd. - MacmetEngg. Ltd. - Kalpataru Projects International Ltd. - MacwberBeekay - Mecon Ltd. - SEPC Ltd. (Via VC) - TATA Projects Ltd. (Via VC) - ToD extended till 24.05.2025 - ToD further extended upto 07.06.2025 - ToD extended upto 14.06.2025 - 6 offeres received & opened on 14.06.2025. Offers were sent to CET for evaluation. - M/s. SEPC Ltd. - M/s. The Indure Pvt. Ltd. - M/s. Mecon Ltd. - M/s. BTL EPC Ltd. - M/s. Hamtek Technologies India Pvt. Ltd. - Consortium of M/s. EPIL & M/s. RHIPL - Proposal for cancellation of tender approved by CA on 28.08.2025. - Revised EC submitted by CET on 04.11.2025. - To be retendered with revised TS and EC.( Pending with Coke Oven Department). - NIT Issued on 06.04.2026 - ToD Scheduled on 04.05.2026 - The Following prospective bidders participated in the Pre-bid meeting held on 16.04.2026; - M/s. TKIL Industries Private Limited. (formerly known as M/s. Thyssenkrupp Industries India Private Limited - M/s. BTL EPC Ltd. - M/s. SEPC Ltd. - M/s. Imeco Overseas Pvt. Ltd. - M/s. Macmet Engineering Ltd. - M/s. Hamtek Technologies India Pvt. Ltd. - M/s. Mecon Ltd. - M/s. Engineering Projects India Ltd. - M/s. Reliable Hitech Infrastructure Pvt Ltd. - M/s. The Indure Private Limited. - M/s. Takshvi Infra Pvt Ltd, Engineers & Constructor (wholly owned by Amit Alliance) - TOD Extended upto 18.05.2026. - 18.05.2026-4 offers received & opened - Consortium of M/s. EPIL & M/s. RHIPL - M/s. Hamtek Technologies India Pvt. Ltd., Hyderabad - M/s. Macmet Engineering Ltd. - M/s. BTL EPC Ltd., Kolkata - Technical discussion meeting scheduled at CET, Ranchi from 02.06.2026 to 05.06.2026. |
| CATEGORY-C Under Stage-I approval- Rs 181.93 Cr. (Gross)(3 nos.) |  |  |
|  | Dust Extraction system for BF#1 Estimate – Rs 45.74 Cr. (Net of Input tax credit of Rs 6.82 Cr) Gross-52.56 Cr. Implementation period: 15 months PM-Shri M D Tirkey - Stage-I approval timeline: - Proposal sent to CO:22.03.2025 - CoD-21.05.2025 Environment Clearance- Obtained Consent to Establish(SPCB) | - 22.03.2025-Proposal sent to CO for stage-I approval - EMD Observation received on 07.04.2025, complied on 19.04.2025 - 21.05.2025-CoD held.CoD advised for completion of soil survey, soil investigation & underground mapping. - Order placed for soil survey & underground mapping - Soil survey, soil investigation and underground mapping completed. - CET to submit revised estimate along with reply to observation of CoD. - FR with revised estimate recived from CET. - Reply to CoD Observation sent to corporate office on 07.04.2026. - CoD held on 18.05.2026. |
|  | Installation of Additional De-dusting System in SP-III Estimate – Rs 62.87 Cr. (Net of Input tax credit of Rs 7.84 Cr) Gross-70.71 Cr. Implementation period: 15month - Stage-I approval timeline: - Proposal sent to CO:11.09.2025 - CoD-18.09.2025,18.05.2026 | - 11.09.2025-Proposal sent to CO for stage-I approval - CoD held on 18.09.2025 - Observation received on 22.09.2025 . - Compliance to CoD Observation sent to Corporate office on 30.03.2026. - CoD held on 18.05.2026. |
|  | Provision of Mixed Gas Firing in oil fired kilns at CP II Estimated Cost-Rs 50.66 Cr. (Net of ITC of Rs 8.00 Cr. ) Gross-Rs 58.66 Cr. Implementation period: 18 months PM-Shri Ramesh Singh - Stage-I approval timeline: - Proposal sent to CO:26.05.2026 | - FR (R1) received from CET on 12.03.2026 - Cleared by IPSC on 22.06.2024 - Plant PAG held on 24.07.2024 - PAG MoM signed on 13/04/2026 - Proposal sent to Corporate office on 26.05.2026 for stage-I approval |
| CATEGORY-D Under Formulation |  |  |
| SI | Name of the Package | Status |
| - 16. | NEW SMS-1 (1.15 MTPA) Estimated Cost- Rs 4623.10 Cr. (Net of Input tax credit of Rs 632.80 Cr) Gross-52.56 Cr. Implementation period: 41 months PM-Shri Sanjeev Kumar - Stage-I approval timeline: | - Appointment of Consultant for preparation of DPR & consultancy services upto Stage-II approval - 10.08.23-Contract signed with M/s Dasturco (Contract Cost-Rs 6.25 Cr.) Schedule-18 months. - Timeline - Draft Pre-FR-04/10/23 - Final Pre-FR-18/10/23 - Draft DPR-06/03/24 - Final DPR-20/03/24 - TS & EC-15/05/2024 - 17.08.2023-19.08.2023-Kick-off meeting and site visit along with DASTURCO team held for preparation of Pre-FR and DPR - 21.09.2023-Meeting held by Director (I/c), RSP with DASTURCO. RSP approved the location at CRM -HSM1 site and layout plan - 21.10.2023- Concept note submitted by DASTURCO. - 02/03/2024- FR submitted by DASTURCO (Rs 6067 Cr. (Net of ITC-Rs 762 Cr.), Implementation schedule-41 months). - 17.05.2024-Draft DPR submitted by DASTURCO. Final DPR expected by 1st week of Jul’24. - 17.05.2024- Review of proposal was done by Dir(I/c), RSP. - 07.06.2024- Revised package list with packaging methodology submitted 26.06.2024-Final DPR submitted by M/s DASTURCO. Cost-Rs 5931 Cr. (Net of ITC), Gross-6693 Cr. IRR-13.3% , Implementation schedule-41 months - 09.07.2024-L&T visited RSP for discussion with regards to new SMS-I packaging philosophy. - 19.07.2024-Meeting held by Dir(I/c) - 24.07.2024-RSP proposed 3 nos. of packages for implementation - Pkg-1-BOF,RHOB,HMDS,LF,Caster - Pkg-2-LDCP(350 tpd Lime, 250 tpd Dolo) - Pkg-3-Enabling jobs, Dismantling work, Rerouting of existing facilities & strengthening of building structure, installation of utilities for construction, etc - 20-21.09.2024-Bidders conference held with Technology providers & EPC contractors. - During the conference, it was proposed by some probable bidders to keep the HMDS and BOF package separately from RHOB, LF & Caster packages. - 30.09.2024-VC held with M/s M.N.Dastur& Co. to finalise the package list. - Inline with the discussions during bidders conference, M/s M.N.dastur& Co proposed package methodology consisting of 6 Pkgs. (BOF, HMDS, RHOB-LF-Caster ,LDCP, BOP, Enabling) - 01.10.2024-SMS deptt. views sought regarding injection/KR process for HMDS. Incase of injection process HMDS & BOF can be made a single package, however for KR process HMDS separate package methodology to be adopted for BOF & HMDS. - 07.10.2024-SMS Deptt. agreed for injection process for HMDS. - 15.10.2024- 5 pkgs implementation methodology proposed to Dasturco for preparation of TS(BOF-HMDS, RHOB-LF-Caster ,LDCP, BOP, Enabling) - 24.10.2024- Plant PAG held. Obsn. Under compliance (with Dasturco for providing clarification regarding balancing of 0.32 mtpa crude steel and comparison of capital cost of ISP SMS vs RSP SMS including justification of higher cost. - 26.10.2024 & 18.11.2024-Multiple correspondences done with Dasturco in this regard. - 05.11.2024 & 25.11.2024-Reply received from M/s Dasturco - 24.12.2024-DASTURCO once again requested to provide detailed breakup of cost estimate along with comparison of cost of ISP SMS (4.08 MTPA) vs RSP SMS (1.15 MTPA). - 16.01.2025-Reply received from DASTURCO. The revised estimated cost is Rs 5973 Cr. (Gross) Earlier Cost estimate-Rs 6693 (Gross) - 13.02.2025- A discussion was held with CET, followed by a visit from DASTURCO on 14.02.2025. The feasibility of installing a new SMS-I at the existing SMS-I location using the EAF route was explored. - 18.02.2025-DASTURCO requested for data related to scrap balance, which was provided on 20.02.2025. Multiple reminders sent vide mail dtd 11.03.2025& 01.03.2025for submission of proposal. - M/s Dasturco submitted a study report for installing new SMS-1 at existing SMS-1 site on 21.03.2025. - M/s DASTURCO visted RSP on 4th and 5thof April 2025 for detailed discussion, Study report sent to concerned department for comments. - 21.04.2025-Consolidated observations of user Deptt. sent to DASTURCO(minimum 150T converter proposed) - Further data related to flux balancing & kiln capacity provided to DASTURCO - 29-30.05.2025-Proposal presented by DASTURCO. - 30.05.2025-Meeting held in the Office of DIC, RSP. Approach note presented by DASTURCO. The approach note has been cleared. DASTURCO has been asked to prepare DPR. - DASTURCO has sought comprehensive coordinate data for existing underground and overground facilities. - Soil testing requested by DASTUR CO. To be done by SMS-2 - A meeting was held on 30.06.2025 with DASTUR Co., RMHP, and CP to finalise the bunker location. Meeting held with M/s DASTURCO with all concerned departments on 11 to 13th Aug’25. Soil investigation order placed on 03.09.2025. - DPR submitted by M/s DASTURCO on 14.10.2025. - Observation received from all stakeholders sent to M/s Dastur Co. On 11.11.2025. - A meeting was held with DIC on 04.12.2025, during which M/s Dastur Co. was requested to submit the final DPR incorporating all finalized observations. - Meeting held on 06.01.2026 at ED(Works) conference hall for finalization of enabling package/dismantling of buildings. - Contract agreement was amended vide reference no. 041/644/2295000054/Consultancy/SMS-I/R1/13 dated 27th January 2026 for rework on DPR. - Final discussion with concerned department done during visit of Dastur on 06.02.2026 - The final DPR, incorporating the agreed observations, is expected to be received by the end of February 2026. - DPR received in March’26. - Proposal for In Principle approval intiated by SMS-I department on 07.03.2026 - Proposal cleared by IPSC on 23.03.2026 - Plant PAG held on 25.03.2026 - PAG MOM signed on 04.05.2026 - Final DPR received on 17.04.2026 - Proposal under approval at plant for sending to Corporate Office for stage-I approval |
| - 16. | Upgradation of Electrics for 2 nos. Hot Metal Handling Cranes at SMS-II Estimated Cost- Rs 53.51 Cr. (Net of ITC of Rs 8.43 Cr. ) Gross-Rs 61.94 Cr. Implementation period: 19 months PM-Shri Ramesh Singh - Stage-I approval timeline: | - FR(R0) & TS (R0) received on 28.01.2025 - PAG held on 23/01/2026. PAG MoM signed on 28.03.2026. - Cost Estimate revised & revised FR received on 21.04.2026 - PAG addendum signed on 04/05/2026 - Proposal under approval at plant for sending to Corporate Office for stage-I approval |

Expansion

| SI | Name of the Package | Status |
| --- | --- | --- |
|  | Green Field Expansion Tentative Cost-Rs 64000 Cr. | - Land Status : - Rourkela Steel Plant has a plan of enhancing its Hot Metal Capacity from 4.5 to 9.8 MTPA. For this, a contiguous patch of land of approx. 1200 Acre adjacent to RSP boundary towards Dumetra side of RSP has been identified. - This land belongs to RSP and is out side the existing plant boundary. The area is encroached by approx. 300 families across 8 bastis in different patches. Out of these 8 bastis, survey work is already done in 4 bastis namely (1) Kate, (2) Girijatoli, (3) Jharmunda (4) Rengadih. Upon completion of the survey, the number of Project Affected Persons (PAPs) requiring rehabilitation will be determined. - SAIL has already identified 10 acres of land for rehabilitation & re-settlement of these encroachers. - This issue has been taken up by RSP management with Govt. of Odisha at Chief Secretary level, Collector Sundergarh district, ADM and Superintendent Police, local administration. - Another meeting in this regard was held on 25.06.2025 in the presence of Hon’ble Steel Minister(GOI). Subsequently a high level committee has been constituted on 30.06.2025 for resolving the issues of encroachment of RSP land. The committee held extensive deliberations with stakeholders at Rourkela on 24.07.2025. Meeting held on 12.09.2025 chaired by Shri Juel Oram, Hon’ble cabinet minister in presence of Collector, Additional District Magistrate (ADM), and Deputy Inspector General of Police (DIG). - Meeting held on 19.11.2025 by Hon’ble Union Minister for Steel and Heavy Industries; Govt. of India with Hon’ble Chief Minister of Odisha in presence of the Secretary (Steel), Government of India; Chief Secretary, Govt. of Odisha; Chairman, SAIL; and Director-in-Charge, RSP. - Last Meeting held on 06.01.2026 with Chief Secretary Odisha in presence of Steel Secretary & CMD SAIL - A concept note for the RSP Expansion Plan envisaging the installation of a 5.0 MTPA Greenfield Crude Steel Facility along with selective Brownfield capacity enhancements has been accorded in principal approval by SAIL Board in its meeting held on 25.07.2025. Uploading of land encroachment issue on PRAGATI portal is in process - Project Formulation Status: - Concept Note: In-principle clearance received from Board onJuly 2025. - Assignment given to CET for preparation of feasibility report on 09.08.2025. - Assignment accepted by CET on 13.08.2025. - Pre-FR Submitted by CET on 05.11.2025. Consolidated observations from all stakeholder departments sent to CET on 06.01.2026. CET has submitted its comments on observations of RSP on 03.02.2026 - CET on 07.02.2026 suggested RSP to engage an external consultant for DPR/CPFR on account of its current engagement with multiple ongoing AMR &expansion projects across all SAIL plants. Accordingly, RSP has initiated steps for engagement of an external consultant for greenfield expansion. - Proposal for appointment of MECON on a single-tender basis for engagement as consultant for preparation of the CPFR and obtaining Environmental Clearance (EC) approved by Competent Authority on 16.02.2026 - Proposal for appointment of M/s MECON on a single-tender basis for engagement as Consultant for preparation of CPFR and obtaining Environmental Clearance (EC) was approved by the Competent Authority on 16.02.2026. - NIT was issued on 21.02.2026 with Tender Opening Date (TOD) as 28.02.2026. - Offer of M/s MECON has been received and opened on 02.03.2026. - Two rounds of negotiations were held with M/s MECON on 02.03.2026 and 05.03.2026. - MECON Consultancy for DPR. - Letter of Acceptance (LOA) was issued to M/s MECON on 07.03.2026 for the work of “Appointment of Consultant for Preparation of Feasibility Report and Detailed Project Report for Expansion of RSPLOA issued on 07.03.2026 at a total price of 12.75 Cr. (Net of ITC). - Contract signed with M/s MECON on 16.03.2026 for preparation of the Feasibility Report and Detailed Project Report (DPR) for the expansion of RSP, at a total contract value of ₹12.75 crore (net of ITC). - Site Visit & interaction with Various deparment with MECON 26.03.2026 - Draft FR submitted on 18.04.2026 - Survey & Soil investigation status - Topological survey (M/s CE testing Co. Pvt. Ltd. )- Started from 04.05.2026 (1175 acres completed) - Underground survey (M/s Parsan Overseas(P) Ltd.)-started from 15.05.2026 (168.28 acres completed) - Soil investigation(M/s CE testing Co. Pvt. Ltd. )- started on 09.05.2026 (7 out of 235 boreholes completed) - MECON has proposed three configuration options in the FR for the proposed expansion. - Discussions are in progress for finalization of the optimum configuration. - Based on preliminary analysis, Option-2 appears to be the most favourable option and is under consideration for further detailed evaluation. - Land demarcation, fencing & boundary wall work of RSP expansion area. - The previous order was cancelled due to non-submission of Bank Guarantee (BG) by M/s Gautam despite multiple reminders - AT placed on 18.04.2026 to M/s NBCC for Barbed wire fencing & Construction of road along with leveling the area near Barkani / Dumetra at a cost of Rs. 12.327 Cr. Including GST. The final rate shall be incorporated in this order after finalisation of rate by M/s NBCC with their sub-contractors. Based on AT 10% Advance Payment done on18.04.2026. - The work commenced on 28.04.2026 under security cover provided by the local administration. - Go-ahead was issued to M/s NBCC on 30.04.2026 for construction of RCC Plant Boundary Wall (Length-6000 m) along with a 3.5 m wide metal peripheral road. - Fencing, area leveling and approach road constructions in progress. (Fencing work completed-11.19 Km; 6 agencies were deployed for fencing job ) - Permanent RCC boundary wall construction covering about 11 Km has been taken up through deployment of 10 executing agencies at multiple locations |
|  | Brown Field Tentative Cost-Rs 11000 Cr. (approx.) To be implemented in Phases | - Assignment was given to CET on 06.11.2025. - CET has expressed its constraints in taking up the assignment &suggested RSP to engage an external consultant for preparation of the DPR/CPFR on account of its current engagement with multiple ongoing AMR and expansion projects across all SAIL plants |

Annexure-I

Fencing

| Sl. | Contractor |
| --- | --- |
| 1 | M/s USS |
| 2 | M/s Alekh |
| 3 | M/s Jupiter |
| 4 | M/s Banbhori |
| 5 | M/s AM Associates |
| 6 | M/s Mahapatra |

Permanent Boundary Wall

| SI | Contractor | Length Assigned (km) |
| --- | --- | --- |
|  | M/s NBCC (through USS Construction & Shri Jagannath Traders) | 1.50 |
|  | M/s Sarada Enterprises | 1.00 |
|  | M/s Reliable Hitech Infrastructure Pvt. Ltd. | 1.75 |
|  | M/s Abinash Construction | 1.50 |
|  | M/s Viman Constructions | 3.50 |
|  | M/s Unistar Company | 0.50 |
|  | M/s Pranir Infra Pvt. Ltd. | 0.25 |
|  | M/s Maa Tarini Enterprises | 0.50 |
|  | M/s Anil Kumar Lenka | 0.25 |
|  | M/s Bhagwati Projects | 0.25 |
|  | M/s Deb Constructions | Contract Terminated |

Expansion details

| Plant facilities | Option-1 (Green Field) | Option-2 (Green Field) | Option-3 (Green Field) |
| --- | --- | --- | --- |
| Crude Steel production, t/yr | 47,89,600 | 47,89,600 | 47,89,600 |
| Pellet plant (BOO/COM) | 1 × 4.5 Mt/yr | 1 × 4.5 Mt/yr | 1 × 4.5 Mt/yr |
| Coke oven and by product plant | 2 × 70 ovens, 6.25/6.78 m ht. BPP for recovery of tar, sulphur and naphthalene | 2 × 70 ovens, 6.25/6.78 m ht. BPP for recovery of tar, sulphur and naphthalene | 2 × 70 ovens, 6.25/6.78 m ht. BPP for recovery of tar, sulphur and naphthalene |
| Sinter plant | 1 × 360 m² | 1 × 360 m² | 1 × 360 m² |
| Blast furnace (useful vol.) | 1 × 5900 m³ | 1 × 5900 m³ | 1 × 5900 m³ |
| Granshot machine | 2 × 300 t/h | 2 × 300 t/h | 2 × 300 t/h |
| HMDS (KR process) | 2 × 300 t | 2 × 300 t | 2 × 300 t |
| Basic oxygen furnace | 2 × 300 t | 2 × 300 t | 2 × 300 t |
| Ladle furnace (LF) | 1 × 300 t (twin) + 1 × 300 t, 60 MVA each | 1 × 300 t (twin) + 1 × 300 t, 60 MVA each | 1 × 300 t (twin) + 1 × 300 t, 60 MVA each |
| RH degasser | 1 × 300 t | 1 × 300 t | 1 × 300 t |
| Slab caster | 2 × 2-strand | 1 × 2-strand | – |
| Thin slab caster | – | 1 × 1-strand | 2 × 1-strand |
| Hot strip mill | 1 × 5.0 Mt/yr | 1 × 3.0 Mt/yr | 1 × 3.0 Mt/yr + 1 × 2.0 Mt/yr |
| Cold rolling mill | 1 × 1.5 Mt/yr | 1 × 1.5 Mt/yr | 1 × 1.5 Mt/yr |
| Silicon mill (CRNO) | 1 × 0.3 Mt/yr | 1 × 0.3 Mt/yr | 1 × 0.3 Mt/yr |
| Briquetting plant | 1 × 50 t/h | 1 × 50 t/h | 1 × 50 t/h |
| Micro-pelletising plant | 1 × 0.1 Mt/yr | 1 × 0.1 Mt/yr | 1 × 0.1 Mt/yr |
| Metal recovery plant | 1 × 61,500 t/yr | 1 × 61,500 t/yr | 1 × 61,500 t/yr |
| Lime calcination plant | 3 × 600 t/d | 3 × 600 t/d | 3 × 600 t/d |
| Dolo calcination plant | 1 × 600 t/d | 1 × 600 t/d | 1 × 600 t/d |
| Oxygen plant (BOO basis) | 2 × 2500 t/d | 2 × 2500 t/d | 2 × 2500 t/d |
| Captive power plant | 1 × 38 MW TRT + 1 × 15 MW BPTG + 1 × 15 MW STG | 1 × 38 MW TRT + 1 × 15 MW BPTG + 1 × 15 MW STG | 1 × 38 MW TRT + 1 × 15 MW BPTG + 1 × 15 MW STG |
| Tentative cost (Rs Cr.) | Rs 69,926 Cr. | Rs 64,788 Cr. | Rs 66,245 Cr. |