CAPEX Monitoring — MoS Format — 1000 TPD Oxygen Plant — 2026-06

CAPEX Overview

MoS CAPEX Format

| Sl | Head / Scheme | Gross Cost | Cum till last FY | BE (FY) | RE (FY) | Actual (YTD) | Achv % |
| --- | --- | --- | --- | --- | --- | --- | --- |

1000 TPD Oxygen Plant

Structural

LIN INNER TANK - 4th Stage Shell Plate Horizontal Plate welding completed. Inside backchipping completed. Welding in progress.

LOX Inner Tank - Ist Stage Shell Plates Bottom outer welding completed. Inside welding progressing.

A/G Piping Fabrication & Erection work for Process piping in Core Plant area in progress.

Mechanical

ECR - HT & LT Cable laying from ECR to MAC & BAC compressor under progress.

Electrical

30 MVA HT Transformers NIFPS Panel erection completed. Regards BSDASH.

ECR - Oil filtration of 6 nos. of LT Trafos completed. LT cable laying work for Cooling Tower Fan motor, Supply & Delivery pumps is in progress.

30 MVA HT Transformers NIFPS Pipe line Erection job in progress. LT Trafos Gavel filling under progress.

Electrical Earthing work in progress.

Erection of HVAC job for ECR under progress .

Instrument cable tray work as well as laying of Instrumentation cable from MAC, BAC to ECR, and DCAC, EVC, PPU to ECR Instrumentation control room under progress.

Instrument cable tray work from MAC, BAC to ECR, and DCAC, EVC, PPU to ECR Instrumentation control room under progress.

Preparation ongoing for Erection of HVAC job for ECR.

Piping

A/G Piping Erection (Process) - Out of total 33,00 Inch Meter, 28,000 inch meter erection completed.

Cooling Water Line hydrotesting under progress. 8 ) Stability Testing job completed at site. Report expected on 22.06.2026.

Cold Box - Pneumatic Test for Pipes under progress.

Cooling Water Line hydrotesting started. 10 ) Stability Testing job started and under progress at site Regards BSDASH.

General

Erection of Stack (30 mtr. height) for 1000 KVA DG set completed. Regards BSDASH.

Horton Sphere (A) - Radiography Test For Equatorial Plate under progress. 8 nos. ofJoint RT completed.

Horton Sphere (B) - Bottom Crown Plate Radiography Test completed.

LIN - 7 nos. of Vaporisers Erection completed. Regards BSDASH.

Insulation work for DCAC,EVC and Regeneration Heater in progress.

Balance 3 nos. Vaporisers reached at site and expected to be erected tomorrow. Regards BSDASH.

Preparation ongoing for Insulation work for DCAC,EVC and Regeneration Heater. Regards BSDASH.

COB#7 Battery Proper (Pkg-2)

Civil

Total Concrete for Piling works: under progress (6313/6464.5 ).

Piping

Cumulative Achieved = 1766 (TP:- 5, Silo:- 195, Battery 7A:- 250, Battery 7B:- 250, Coke Bucket Car:- 100, EB-7A:- 46, EB-7B:- 48, Buttress Wall 7A:-48, Buttress Wall 7B:- 48, SCP Car Track:- 343, Stack Flue Tunnel-38, Coal Tower-156, Intermediate Bench-22, PECS-68, Coke Bucket Repair Station-9, Pipe Rack-40, Hammer Exchange = 34 nos, NTP-1 = 8 nos, Existing CHS Extension = 9 nos, TP8B = 21 nos., PCH = 17 nos., Y-7 = 11 nos.).

Dwg Avl = 1810 (TP:- 5 + Silo:- 195 + Battery-7A:- 250 + EB-7A:- 59 + EB-7B:- 48 + Battery-7B:- 250 + Coke Bucket Car:- 108 + Buttress 7A:- 48, + Buttress 7B = 48 + SCP Car Track = 348+ coal tower =156+ Intermediate bench = 22, Stack Flue Tunnel = 38, PECS = 80, PCH = 17, NTP1 = 8, Coke Bucket Repair Station = 27, Existing CHS Extension = 14, Pipe Rack = 40, Hammer Exchange = 34, TP8B = 21, Y-7 =.

General

A.1: completed (253/253 ).

A.11: completed (22/22 ).

A.12: completed (156/156 ).

A.13: completed (38/38 ).

A.15: completed (17/17 ).

A.16: completed (8/8 ).

A.19: completed (40/40 ).

A.2: completed (250/250 ).

A.20: completed (34/34 ).

A.21: completed (21/21 ).

A.22: completed (12/12 ).

A.24: completed (5/5 ).

A.4: completed (48/48 ).

A.5: completed (197/197 ).

A.7: completed (48/48 ).

A.8: completed (48/48 ).

B.1: completed (2160/2160 ).

B.10: completed (417/417 ).

B.11: completed (9910/9910 ).

B.12: completed (3610/3610 ).

B.16: completed (5361/5361 ).

B.18: completed (3736/3736 ).

B.19: completed (5330/5330 ).

B.2: completed (3908/3908 ).

B.21: completed (5025/5025 ).

B.22: completed (1956/1956 ).

B.23: completed (5445/5445 ).

B.24: completed (382/382 ).

B.25: completed (800/800 ).

B.26: completed (800/800 ).

B.28: completed (2532/2532 ).

B.29: completed (1013/1013 ).

B.39: completed (7495/7495 ).

B.4: completed (6000/6000 ).

B.5: completed (3786/3786 ).

B.52: completed (2905/2905 ).

B.7: completed (591/591 ).

B.8: completed (1330/1330 ).

B.9: completed (3460/3460 ).

D.19: completed (380.2/380 ).

D.2: completed (2367/2367 ).

D.20: completed (367.05/367 ).

D.27: completed (866/866 ).

D.29: completed (379/379 ).

D.30: completed (26.5/23 ).

D.41: completed (247/247 ).

D.66: completed (444/444 ).

E.14: completed (26/26 ).

E.17: completed (23/23 ).

E.5: completed (192.01/192.01 ).

FTD Achieved = 2 nos. Y-7 (P-4,P-7).

G.1: completed (3247/3247 ).

G.2: completed (16065/16065 ).

H.1: completed (10402.7/10200 ).

J.2: completed (2/2 ).

J.3: completed (19.78/12.08 ).

J.4: completed (96/96 ).

A.10: under progress (343/348 ).

A.14: under progress (68/76 ).

A.17: under progress (9/27 ).

A.18: under progress (10/14 ).

A.3: under progress (46/59 ).

A.6: under progress (100/108 ).

B.13: under progress (3508/3925 ).

B.14: under progress (4375/7235 ).

B.15: under progress (1065/2525 ).

B.17: under progress (8854/14700 ).

B.27: under progress (9531/13778 ).

B.3: under progress (4101.5/4102 ).

B.30: under progress (3270/4013 ).

B.31: under progress (1185/1246 ).

B.32: under progress (3105/3285 ).

B.33: under progress (6275/25082 ).

B.34: under progress (1460/1498 ).

B.35: under progress (761/888 ).

B.36: under progress (5710/8106 ).

B.37: under progress (2540/4544 ).

B.38: under progress (4720/8187 ).

B.40: under progress (280/752 ).

B.41: under progress (1380/2223 ).

B.42: under progress (100/6742 ).

B.43: under progress (4770/6655 ).

B.44: under progress (1375/4197 ).

B.46: under progress (1920/4654 ).

B.48: under progress (1060/2855 ).

B.49: under progress (1505/1600 ).

B.50: under progress (1070/1350 ).

B.51: under progress (360/1620 ).

B.54: under progress (250/2300 ).

B.6: under progress (850/2751.89 ).

C.1: under progress (6313/6649.2 ).

D.1: under progress (3982/4690 ).

D.10: under progress (52/182 ).

D.11: under progress (33.2/38 ).

D.12: under progress (1850/3102 ).

D.13: under progress (112.78/113 ).

D.14: under progress (335/587 ).

D.16: under progress (162.2/919 ).

D.17: under progress (761/959 ).

D.18: under progress (2168.1/3003 ).

D.21: under progress (584.82/678 ).

D.23: under progress (1398.9/5228 ).

D.24: under progress (485.5/547 ).

D.25: under progress (852.5/852.663 ).

D.26: under progress (861.35/1175.01 ).

D.28: under progress (215/704 ).

D.3: under progress (2284.19/2324 ).

D.31: under progress (154/621 ).

D.32: under progress (955.5/1325 ).

D.33: under progress (7/204 ).

D.34: under progress (176.7/185 ).

D.35: under progress (54.5/57 ).

D.37: under progress (38/92 ).

D.39: under progress (103.2/176 ).

D.4: under progress (1395/1433 ).

D.40: under progress (84/240 ).

D.42: under progress (519.5/592 ).

D.44: under progress (435/757 ).

D.45: under progress (41/182 ).

D.47: under progress (51.9/81 ).

D.48: under progress (813.5/814 ).

D.49: under progress (134/211 ).

D.5: under progress (666.72/667 ).

D.50: under progress (42.5/453 ).

D.51: under progress (164.3/302 ).

D.52: under progress (97/287 ).

D.53: under progress (884.5/1721 ).

D.54: under progress (101.5/102 ).

D.57: under progress (260.1/280 ).

D.6: under progress (88.5/369 ).

D.63: under progress (20.5/130 ).

D.65: under progress (103/440 ).

D.69: under progress (80/8115 ).

D.7: under progress (40/101 ).

D.8: under progress (84/125 ).

D.9: under progress (126.05/180 ).

E.1: under progress (731/736 ).

E.10: under progress (45/71 ).

E.11: under progress (758/842 ).

E.15: under progress (632.63/1153 ).

E.16: under progress (1/157 ).

E.18: under progress (176.678/252 ).

E.19: under progress (48.428/99 ).

E.2: under progress (215/225 ).

E.21: under progress (13.54/79 ).

E.22: under progress (195/248 ).

E.23: under progress (12.15/820 ).

E.24: under progress (84/198 ).

E.25: under progress (97.745/290 ).

E.26: under progress (53/59.7 ).

E.27: under progress (152.73/259 ).

E.29: under progress (2.023/10.5 ).

E.3: under progress (331.529/384 ).

E.30: under progress (277.09/296 ).

E.36: under progress (105.251/219.071 ).

E.37: under progress (446.576/566 ).

E.4: under progress (224.6/228 ).

E.6: under progress (8.074/12 ).

E.7: under progress (23/26 ).

E.9: under progress (63.101/276 ).

F.1: under progress (713.996/736 ).

F.10: under progress (8.8/71 ).

F.15: under progress (304.27/1153 ).

F.17: under progress (12/23 ).

F.2: under progress (132.335/225 ).

F.26: under progress (50.182/59.7 ).

F.3: under progress (70.79/384 ).

F.37: under progress (26.536/566 ).

F.5: under progress (190.953/192.01 ).

F.7: under progress (14.17/26 ).

H.2: under progress (5367.73/10200 ).

H.3: under progress (981.251/4000 ).

I.1: under progress (192/280 ).

J.1: under progress (15.912/16 ).

K.1: under progress (7192/7354 ).

K.2: under progress (3320/7354 ).

L.1: under progress (242.3/265 ).

L.2: under progress (303/500 ).

M.3: under progress (6/4000 ).

Total for Erection: under progress (6/24410 ).

Total for Supply: under progress (16751.7/24410 ).

1: yet to start.

8th June : 8 trips 9th June : 9 trips 10th June : 11 trips 11th June : 12 trips Cumulative : 40 trips Regards KK.

A.23: yet to start.

A.9: yet to start.

B.20: yet to start (0/928 ).

B.45: yet to start (0/1640 ).

B.47: yet to start (0/515 ).

B.53: yet to start.

Concerns:-: yet to start.

D.15: yet to start (0/1070 ).

D.22: yet to start (0/436 ).

D.36: yet to start (0/123 ).

D.38: yet to start (0/69 ).

D.43: yet to start (0/47 ).

D.46: yet to start (0/16 ).

D.55: yet to start (0/200 ).

D.56: yet to start (0/1844 ).

D.58: yet to start.

D.59: yet to start (0/25 ).

D.60: yet to start (0/46 ).

D.61: yet to start (0/98 ).

D.62: yet to start (0/130 ).

D.64: yet to start (0/40 ).

D.67: yet to start (0/167 ).

D.68: yet to start (0/95 ).

E.12: yet to start (0/6 ).

E.13: yet to start (0/318 ).

E.20: yet to start (0/30 ).

E.28: yet to start (0/1.42 ).

E.31: yet to start (0/1.104 ).

E.32: yet to start (0/0.921 ).

E.33: yet to start (0/0.982 ).

E.34: yet to start (0/0.303 ).

E.35: yet to start (0/2.712 ).

E.38: yet to start (0/5 ).

E.39: yet to start (0/126 ).

E.40: yet to start (0/58 ).

E.41: yet to start (0/26 ).

E.42: yet to start.

E.43: yet to start.

E.44: yet to start.

E.45: yet to start.

E.8: yet to start (0/3 ).

F.11: yet to start (0/842 ).

F.12: yet to start (0/6 ).

F.13: yet to start (0/318 ).

F.14: yet to start (0/26 ).

F.16: yet to start (0/157 ).

F.18: yet to start (0/252 ).

F.19: yet to start (0/99 ).

F.20: yet to start (0/30 ).

F.21: yet to start (0/79 ).

F.22: yet to start (0/248 ).

F.23: yet to start (0/820 ).

F.24: yet to start (0/198 ).

F.25: yet to start (0/290 ).

F.27: yet to start (0/259 ).

F.28: yet to start (0/1.42 ).

F.29: yet to start (0/10.5 ).

F.30: yet to start (0/296 ).

F.31: yet to start (0/1.104 ).

F.32: yet to start (0/0.921 ).

F.33: yet to start (0/0.982 ).

F.34: yet to start (0/0.303 ).

F.35: yet to start (0/2.712 ).

F.36: yet to start (0/219.071 ).

F.38: yet to start (0/5 ).

F.39: yet to start (0/126 ).

F.4: yet to start (0/228 ).

F.40: yet to start (0/58 ).

F.41: yet to start.

F.42: yet to start.

F.43: yet to start.

F.44: yet to start.

F.6: yet to start (0/12 ).

F.8: yet to start (0/3 ).

F.9: yet to start (0/276 ).

G.3: yet to start.

G.4: yet to start (0/375867 ).

H.4: yet to start.

I.2: yet to start.

J.5: yet to start.

K.3: yet to start.

L.3: yet to start.

M.1: yet to start.

M.2: yet to start.

M.4: yet to start.

NOTE:: yet to start.

WIP = 0 nos. Regards KK.

Treatment System-2

Civil

02 nos air blower foundation PCC pouring completed 5.RO building.

Achieved RCC till: 417 cum.

Cable trench raft 01 nos RCC pouring completed.

Cable trench raft 1 nos RCC pouring completed for DT 01 3. Filtration Area.

Cable trench wall RCC pouring completed 3. Filtration Area.

Column 1st lift 2 nos RCC pouring completed 5.CWST and UF Feed Tank.

Column RCC pouring completed 5.CWST and UF Feed Tank.

DT 01 PCC flooring completed 3. Filtration Area.

Foundation raft RCC pouring completed 9. UF RO Building cum Pump House – SMS II Area.

Grade slab RCC pouring completed.

Leachate pit excavation completed 11. Over Head Tank.

Leachate pond excavation work completed 11. Over Head Tank.

MCC room slab RCC pouring completed.

PCC pouring completed for grade slab 5.RO building.

PCC pouring completed for road works 10. Secured Landfill.

Pump foundation 6 nos RCC pouring completed.

RCC tank grouting work for hydro test completed 10. Secured Landfill.

RO room column 1st lift RCC pouring completed - 0/18/20 nos.

RO room roof slab RCC pouring completed 6.Chemical Building and Dyke Area.

Road RCC pouring completed.

Screening chamber intermediate wall RCC pouring completed.

Base slab shuttering work under progress 12. Filter press building.

Cable trench wall and pile cap shuttering work in progress 5.RO building.

Fensing pole excavation and installation under progress.

Fensing pole excavation under progress 11. Over Head Tank.

MCC room slab shuttering and reinforcement binding work in progress 9. UF RO Building cum Pump House – SMS II Area.

MCC room slab shuttering work in progress 9. UF RO Building cum Pump House – SMS II Area.

PCC 01 Panel installation in progress.

PCC lining under progress.

PCC lining under progress 11. Over Head Tank.

Pump foundation shuttering work in progress.

Pump house roof slab stagging and shuttering work in progress.

Reinforcement binding and Shuttering work for foundation work in progress.

Reinforcement binding and shuttering work in progress for Pump foundation.

RO room roof slab reinforcement binding work in progress 6.Chemical Building and Dyke Area.

Roof slab stagging work in progress 6.Chemical Building and Dyke Area.

Scaffolding erection and beam shuttering for base slab under progress 12. Filter press building.

Scaffolding erection for base slab under progress 12. Filter press building.

Tank cover slab reinforcement binding work in progress.

Tank cover slab Scaffolding erection under progress.

Cum. PCC poured: 420 cum.

Equipment erection - 0 nos Monthly Plan – June 2026 RCC Pouring.

Excavation - 0 Cum.

PCC poured - 0 Cum.

Pump foundation 0/31/31 nos.

Pump foundation 4/31/31 nos.

RCC Poured – 0 Cum.

RCC Poured – 04 Cum.

RCC Poured – 06 Cum.

RCC Poured – 07 Cum.

RCC Poured – 12 Cum.

RCC Poured – 14 Cum.

RCC Poured – 15 Cum.

RCC Poured – 16 Cum.

RCC Poured – 185 Cum.

RCC Poured – 35 Cum.

RCC Poured – 38 Cum.

Structural

Interconnecting pipe line fabrication work under progress.

MCC 03 panel base frame fabrication work in progress.

Media filling and drain pipe fabrication under progress.

Monorail beam fabrication work under progress 7.Equalization Tank.

Spool piece fabrication work under progress.

Structural shed erection under progress 4. UF Pump House – TS 02.

Mechanical

Pump house monorail beam erection completed 2. Electrical building.

Pump erection under progress 9. UF RO Building cum Pump House – SMS II Area.

Pump house monorail beam erection work in progress 2. Electrical building.

RO HPP to MCF pipe line erection under progress 9. UF RO Building cum Pump House – SMS II Area.

Valves fixing work under progress 4. UF Pump House – TS 02.

Equipment erection - 47 nos.

No progress 8. UF RO Building Cum Pump House – PBS Area.

No work 4. UF Pump House – TS 02.

Electrical

Lubrication pump inlet pipe laying completed 2. Electrical building.

MCC panel charge testing completed 10. Secured Landfill.

Bolt fixing and shuttering work in progress for column 13. Treated water pipeline.

Cable tray installation and laying work under progress 2. Electrical building.

Cable tray support and tray installation in progress.

Cable trench raft and wall reinforcement binding and shuttering work in progress Distribution transformer area.

Cable trench wall shuttering work in progress.

Column shuttering work in progress 2. Electrical building.

Control and power cable laying under progress.

Control cable laying under progress.

Control cable laying under progress 10. Secured Landfill.

Incomer cable laying under progress 10. Secured Landfill.

Instrument installation work under progress 2. Electrical building.

Painting work in progress 2. Electrical building.

Piping support fixing work under progress 2. Electrical building.

VT pump distance pieces erection work under progress 2. Electrical building.

Piping

GI pipe erection 0/331/380 mtr completed.

Filter feed pump suction pipe connection under progress 5.RO building.

Backfilling: 0/1186/1300 15. Reject water pipe line - PBS.

Pipe erection 0/2858/3060.

Pipe erection 0/2875/3060.

Pipe erection 16/2875/3060.

Pipe laying - 0 Rmt.

General

DT 02 flooring completed 3. Filtration Area.

RO skid and pressure tube erection completed.

Column shuttering work in progress.

Drain and Plinth protection work under progress 10. Secured Landfill.

JB installation under progress.

JB installation under progress 10. Secured Landfill.

Masonry work in progress.

Monorail Column and beam shuttering work in progress.

Painting work in progress.

Pump alignment under progress - 0/21/23.

Pump erection under progress.

Road and drain work under progress.

Road sub base preparation under progress.

UF skid and pressure tube erection under progress.

Valves fixing work under progress.

Wall shuttering work in progress 6.Chemical Building and Dyke Area.

Wall shuttering work in progress 7.Equalization Tank and UF Tank.

WBM work under progress 11. Over Head Tank.

1. Common Collection Sump.

Backfilling - 0/310/410 (RMT) Quantity-wise completion.

Column 2nd lift -0/15/20.

Column 3rd lift- 0/8/20.

Curing work 6.Chemical Building and Dyke Area.

Masonry work first floor - 0/93/130.

No progress 13. Treated water pipeline.

No progress 7.Equalization Tank.

This month's plan: 500 cum.

Wrapping -0/3234/3233.