PMC — Monthly Progress Report — COB#7 Battery Proper (Pkg-2) — 2026-06

I. Progress of the Project

Discipline-wise Progress

| Brief Description of Progress (Main package) | Overall % Target till the month | Cumulative % completion till the month | % achievement for the month |
| --- | --- | --- | --- |
| Civil Work | 65.84 | 64.68 | 5.55 |
| Structural Supply | 77.62 | 53.15 | 13.55 |

II. Present Status of the Project

Present Status

Civil

Total Concrete for Piling works: under progress (6313/6464.5 ).

Piping

Cumulative Achieved = 1766 (TP:- 5, Silo:- 195, Battery 7A:- 250, Battery 7B:- 250, Coke Bucket Car:- 100, EB-7A:- 46, EB-7B:- 48, Buttress Wall 7A:-48, Buttress Wall 7B:- 48, SCP Car Track:- 343, Stack Flue Tunnel-38, Coal Tower-156, Intermediate Bench-22, PECS-68, Coke Bucket Repair Station-9, Pipe Rack-40, Hammer Exchange = 34 nos, NTP-1 = 8 nos, Existing CHS Extension = 9 nos, TP8B = 21 nos., PCH = 17 nos., Y-7 = 11 nos.).

Dwg Avl = 1810 (TP:- 5 + Silo:- 195 + Battery-7A:- 250 + EB-7A:- 59 + EB-7B:- 48 + Battery-7B:- 250 + Coke Bucket Car:- 108 + Buttress 7A:- 48, + Buttress 7B = 48 + SCP Car Track = 348+ coal tower =156+ Intermediate bench = 22, Stack Flue Tunnel = 38, PECS = 80, PCH = 17, NTP1 = 8, Coke Bucket Repair Station = 27, Existing CHS Extension = 14, Pipe Rack = 40, Hammer Exchange = 34, TP8B = 21, Y-7 =.

General

A.1: completed (253/253 ).

A.11: completed (22/22 ).

A.12: completed (156/156 ).

A.13: completed (38/38 ).

A.15: completed (17/17 ).

A.16: completed (8/8 ).

A.19: completed (40/40 ).

A.2: completed (250/250 ).

A.20: completed (34/34 ).

A.21: completed (21/21 ).

A.22: completed (12/12 ).

A.24: completed (5/5 ).

A.4: completed (48/48 ).

A.5: completed (197/197 ).

A.7: completed (48/48 ).

A.8: completed (48/48 ).

B.1: completed (2160/2160 ).

B.10: completed (417/417 ).

B.11: completed (9910/9910 ).

B.12: completed (3610/3610 ).

B.16: completed (5361/5361 ).

B.18: completed (3736/3736 ).

B.19: completed (5330/5330 ).

B.2: completed (3908/3908 ).

B.21: completed (5025/5025 ).

B.22: completed (1956/1956 ).

B.23: completed (5445/5445 ).

B.24: completed (382/382 ).

B.25: completed (800/800 ).

B.26: completed (800/800 ).

B.28: completed (2532/2532 ).

B.29: completed (1013/1013 ).

B.39: completed (7495/7495 ).

B.4: completed (6000/6000 ).

B.5: completed (3786/3786 ).

B.52: completed (2905/2905 ).

B.7: completed (591/591 ).

B.8: completed (1330/1330 ).

B.9: completed (3460/3460 ).

D.19: completed (380.2/380 ).

D.2: completed (2367/2367 ).

D.20: completed (367.05/367 ).

D.27: completed (866/866 ).

D.29: completed (379/379 ).

D.30: completed (26.5/23 ).

D.41: completed (247/247 ).

D.66: completed (444/444 ).

E.14: completed (26/26 ).

E.17: completed (23/23 ).

E.5: completed (192.01/192.01 ).

FTD Achieved = 2 nos. Y-7 (P-4,P-7).

G.1: completed (3247/3247 ).

G.2: completed (16065/16065 ).

H.1: completed (10402.7/10200 ).

J.2: completed (2/2 ).

J.3: completed (19.78/12.08 ).

J.4: completed (96/96 ).

A.10: under progress (343/348 ).

A.14: under progress (68/76 ).

A.17: under progress (9/27 ).

A.18: under progress (10/14 ).

A.3: under progress (46/59 ).

A.6: under progress (100/108 ).

B.13: under progress (3508/3925 ).

B.14: under progress (4375/7235 ).

B.15: under progress (1065/2525 ).

B.17: under progress (8854/14700 ).

B.27: under progress (9531/13778 ).

B.3: under progress (4101.5/4102 ).

B.30: under progress (3270/4013 ).

B.31: under progress (1185/1246 ).

B.32: under progress (3105/3285 ).

B.33: under progress (6275/25082 ).

B.34: under progress (1460/1498 ).

B.35: under progress (761/888 ).

B.36: under progress (5710/8106 ).

B.37: under progress (2540/4544 ).

B.38: under progress (4720/8187 ).

B.40: under progress (280/752 ).

B.41: under progress (1380/2223 ).

B.42: under progress (100/6742 ).

B.43: under progress (4770/6655 ).

B.44: under progress (1375/4197 ).

B.46: under progress (1920/4654 ).

B.48: under progress (1060/2855 ).

B.49: under progress (1505/1600 ).

B.50: under progress (1070/1350 ).

B.51: under progress (360/1620 ).

B.54: under progress (250/2300 ).

B.6: under progress (850/2751.89 ).

C.1: under progress (6313/6649.2 ).

D.1: under progress (3982/4690 ).

D.10: under progress (52/182 ).

D.11: under progress (33.2/38 ).

D.12: under progress (1850/3102 ).

D.13: under progress (112.78/113 ).

D.14: under progress (335/587 ).

D.16: under progress (162.2/919 ).

D.17: under progress (761/959 ).

D.18: under progress (2168.1/3003 ).

D.21: under progress (584.82/678 ).

D.23: under progress (1398.9/5228 ).

D.24: under progress (485.5/547 ).

D.25: under progress (852.5/852.663 ).

D.26: under progress (861.35/1175.01 ).

D.28: under progress (215/704 ).

D.3: under progress (2284.19/2324 ).

D.31: under progress (154/621 ).

D.32: under progress (955.5/1325 ).

D.33: under progress (7/204 ).

D.34: under progress (176.7/185 ).

D.35: under progress (54.5/57 ).

D.37: under progress (38/92 ).

D.39: under progress (103.2/176 ).

D.4: under progress (1395/1433 ).

D.40: under progress (84/240 ).

D.42: under progress (519.5/592 ).

D.44: under progress (435/757 ).

D.45: under progress (41/182 ).

D.47: under progress (51.9/81 ).

D.48: under progress (813.5/814 ).

D.49: under progress (134/211 ).

D.5: under progress (666.72/667 ).

D.50: under progress (42.5/453 ).

D.51: under progress (164.3/302 ).

D.52: under progress (97/287 ).

D.53: under progress (884.5/1721 ).

D.54: under progress (101.5/102 ).

D.57: under progress (260.1/280 ).

D.6: under progress (88.5/369 ).

D.63: under progress (20.5/130 ).

D.65: under progress (103/440 ).

D.69: under progress (80/8115 ).

D.7: under progress (40/101 ).

D.8: under progress (84/125 ).

D.9: under progress (126.05/180 ).

E.1: under progress (731/736 ).

E.10: under progress (45/71 ).

E.11: under progress (758/842 ).

E.15: under progress (632.63/1153 ).

E.16: under progress (1/157 ).

E.18: under progress (176.678/252 ).

E.19: under progress (48.428/99 ).

E.2: under progress (215/225 ).

E.21: under progress (13.54/79 ).

E.22: under progress (195/248 ).

E.23: under progress (12.15/820 ).

E.24: under progress (84/198 ).

E.25: under progress (97.745/290 ).

E.26: under progress (53/59.7 ).

E.27: under progress (152.73/259 ).

E.29: under progress (2.023/10.5 ).

E.3: under progress (331.529/384 ).

E.30: under progress (277.09/296 ).

E.36: under progress (105.251/219.071 ).

E.37: under progress (446.576/566 ).

E.4: under progress (224.6/228 ).

E.6: under progress (8.074/12 ).

E.7: under progress (23/26 ).

E.9: under progress (63.101/276 ).

F.1: under progress (713.996/736 ).

F.10: under progress (8.8/71 ).

F.15: under progress (304.27/1153 ).

F.17: under progress (12/23 ).

F.2: under progress (132.335/225 ).

F.26: under progress (50.182/59.7 ).

F.3: under progress (70.79/384 ).

F.37: under progress (26.536/566 ).

F.5: under progress (190.953/192.01 ).

F.7: under progress (14.17/26 ).

H.2: under progress (5367.73/10200 ).

H.3: under progress (981.251/4000 ).

I.1: under progress (192/280 ).

J.1: under progress (15.912/16 ).

K.1: under progress (7192/7354 ).

K.2: under progress (3320/7354 ).

L.1: under progress (242.3/265 ).

L.2: under progress (303/500 ).

M.3: under progress (6/4000 ).

Total for Erection: under progress (6/24410 ).

Total for Supply: under progress (16751.7/24410 ).

1: yet to start.

8th June : 8 trips 9th June : 9 trips 10th June : 11 trips 11th June : 12 trips Cumulative : 40 trips Regards KK.

A.23: yet to start.

A.9: yet to start.

B.20: yet to start (0/928 ).

B.45: yet to start (0/1640 ).

B.47: yet to start (0/515 ).

B.53: yet to start.

Concerns:-: yet to start.

D.15: yet to start (0/1070 ).

D.22: yet to start (0/436 ).

D.36: yet to start (0/123 ).

D.38: yet to start (0/69 ).

D.43: yet to start (0/47 ).

D.46: yet to start (0/16 ).

D.55: yet to start (0/200 ).

D.56: yet to start (0/1844 ).

D.58: yet to start.

D.59: yet to start (0/25 ).

D.60: yet to start (0/46 ).

D.61: yet to start (0/98 ).

D.62: yet to start (0/130 ).

D.64: yet to start (0/40 ).

D.67: yet to start (0/167 ).

D.68: yet to start (0/95 ).

E.12: yet to start (0/6 ).

E.13: yet to start (0/318 ).

E.20: yet to start (0/30 ).

E.28: yet to start (0/1.42 ).

E.31: yet to start (0/1.104 ).

E.32: yet to start (0/0.921 ).

E.33: yet to start (0/0.982 ).

E.34: yet to start (0/0.303 ).

E.35: yet to start (0/2.712 ).

E.38: yet to start (0/5 ).

E.39: yet to start (0/126 ).

E.40: yet to start (0/58 ).

E.41: yet to start (0/26 ).

E.42: yet to start.

E.43: yet to start.

E.44: yet to start.

E.45: yet to start.

E.8: yet to start (0/3 ).

F.11: yet to start (0/842 ).

F.12: yet to start (0/6 ).

F.13: yet to start (0/318 ).

F.14: yet to start (0/26 ).

F.16: yet to start (0/157 ).

F.18: yet to start (0/252 ).

F.19: yet to start (0/99 ).

F.20: yet to start (0/30 ).

F.21: yet to start (0/79 ).

F.22: yet to start (0/248 ).

F.23: yet to start (0/820 ).

F.24: yet to start (0/198 ).

F.25: yet to start (0/290 ).

F.27: yet to start (0/259 ).

F.28: yet to start (0/1.42 ).

F.29: yet to start (0/10.5 ).

F.30: yet to start (0/296 ).

F.31: yet to start (0/1.104 ).

F.32: yet to start (0/0.921 ).

F.33: yet to start (0/0.982 ).

F.34: yet to start (0/0.303 ).

F.35: yet to start (0/2.712 ).

F.36: yet to start (0/219.071 ).

F.38: yet to start (0/5 ).

F.39: yet to start (0/126 ).

F.4: yet to start (0/228 ).

F.40: yet to start (0/58 ).

F.41: yet to start.

F.42: yet to start.

F.43: yet to start.

F.44: yet to start.

F.6: yet to start (0/12 ).

F.8: yet to start (0/3 ).

F.9: yet to start (0/276 ).

G.3: yet to start.

G.4: yet to start (0/375867 ).

H.4: yet to start.

I.2: yet to start.

J.5: yet to start.

K.3: yet to start.

L.3: yet to start.

M.1: yet to start.

M.2: yet to start.

M.4: yet to start.

NOTE:: yet to start.

WIP = 0 nos. Regards KK.

III. Reasons / Issues / Constraints

Issues

Design & Engineering

ED(P) advised M/s tkU to bridge the existing engineering gap by expediting the submission and approval of the pending drawings.

Consortium submitted the revised scope and status of Design & Engg. Till — committed for 2026-06-20 but not completed as per latest progress; recovery to be reviewed.  [auto-draft]

Civil

Completion of 3rd floor slab casting at — committed for 2026-06-27 but not completed as per latest progress; recovery to be reviewed.  [auto-draft]

Completion of Conveyor Y13 Slab — committed for 2026-06-26 but not completed as per latest progress; recovery to be reviewed.  [auto-draft]

Structural

In view of the past performance concerns associated with the material supplied by M/s Andrew Yule for the GMBS Fan, M/s L&T was advised to explore alternative vendors from the CET-approved make list to ensure reliable project execution.

IV. Action Taken

Actions Taken

Design & Engineering

M/s L&T informed that the balance drawings are primarily vendor drawings and are under progress.

Consortium submitted the revised scope and status of Design & Engg. Till — committed completion 2026-06-20.

Civil

M/s L&T committed to the following timelines during the meeting:.

---------------------------------------------------------------------- Sl.    Activity                                  Committed Completion No.                                              Date.

Completion of 3rd floor slab casting at — committed completion 2026-06-27.

Completion of Conveyor Y13 Slab — committed completion 2026-06-26.

Completion of civil works for the 7B Deck — committed completion 2026-07-31.

Completion of Balance Foundations for — committed completion 2026-06-30.

Completion of civil works for the 7B Deck — targeted for completion by 2026-07-31.

Completion of Balance Foundations for — targeted for completion by 2026-06-30.

Structural

M/s L&T committed the following time line during meeting.

Coke Bucket Repair Station shall commence by 10.07.2026.

ED(P) advised the Consortium to provide handrails along the ramp to enhance safety.

Completion of TOPR structural works by — committed completion 2026-06-30.

Completion of TOPR structural works by — targeted for completion by 2026-06-30.

Electrical

Transformer by — committed completion 2026-06-30.

Transformer by — targeted for completion by 2026-06-30.

Safety

ED(P) advised M/s L&T to implement AI-based CCTV monitoring at the project site to further strengthen safety surveillance.

ED(Projects) apprised M/s L&T of SAIL's new "Zero Tolerance" Safety Policy and emphasized the need for strict compliance, enhanced accountability, and the highest priority to safety across all work fronts.

It was emphasized that only workmen possessing a valid Height Pass shall be deployed for work at height.

General

Completion of dismantling of the existing — committed completion 2026-06-26.

Coke Bucket Repair Station shall commence by — committed completion 2026-07-10.

Completion of dismantling of the existing — completed (committed 2026-06-26).

Coke Bucket Repair Station shall commence by — completed (committed 2026-07-10).

V. Milestones reported on OCMS portal of MoSPI

OCMS Milestones

| Milestone | Orig. Completion | Anticipated | Reasons |
| --- | --- | --- | --- |
| Silo Building Civil | 12.11.2026 | 07.05.2027 | Drawing delay |

VI. Manpower Engaged

Manpower Engaged (Average)

| Agency / Category | Average Engaged | Reporting Days |
| --- | --- | --- |
| 1 | 7 | 1 |
| 10 | 3 | 1 |
| 11 | 1 | 1 |
| 12 | 13 | 1 |
| 13 | 1 | 1 |
| 14 | 2 | 1 |
| 15 | 2 | 1 |
| 16 | 1 | 1 |
| 17 | 1 | 1 |
| 18 | 1 | 1 |
| 19 | 1 | 1 |
| 2 | 6 | 1 |
| 20 | 1 | 1 |
| 21 | 1 | 1 |
| 22 | 1 | 1 |
| 23 | 1 | 1 |
| 24 | 1 | 1 |
| 25 | 2 | 1 |
| 26 | 2 | 1 |
| 27 | 5 | 1 |
| 28 | 7 | 1 |
| 29 | 1 | 1 |
| 3 | 2 | 1 |
| 30 | 1 | 1 |
| 31 | 2 | 1 |
| 32 | 1 | 1 |
| 33 | 2 | 1 |
| 34 | 1 | 1 |
| 35 | 3 | 1 |
| 36 | 1 | 1 |
| 4 | 1 | 1 |
| 5 | 1 | 1 |
| 6 | 1 | 1 |
| 7 | 1 | 1 |
| 8 | 2 | 1 |
| 9 | 1 | 1 |