Weekly Progress Report — COB#7 Battery Proper (Pkg-2) — 2026-06

Activity Progress (Weekly)

| Activity | UoM | Scope | Cum Plan (till date) | Cum Actual (till date) | Plan (this week) | Actual (this week) | % Complete |
| --- | --- | --- | --- | --- | --- | --- | --- |

Progress Highlights

Civil

Total Concrete for Piling works: under progress (6313/6464.5 ).

Piping

Cumulative Achieved = 1766 (TP:- 5, Silo:- 195, Battery 7A:- 250, Battery 7B:- 250, Coke Bucket Car:- 100, EB-7A:- 46, EB-7B:- 48, Buttress Wall 7A:-48, Buttress Wall 7B:- 48, SCP Car Track:- 343, Stack Flue Tunnel-38, Coal Tower-156, Intermediate Bench-22, PECS-68, Coke Bucket Repair Station-9, Pipe Rack-40, Hammer Exchange = 34 nos, NTP-1 = 8 nos, Existing CHS Extension = 9 nos, TP8B = 21 nos., PCH = 17 nos., Y-7 = 11 nos.).

Dwg Avl = 1810 (TP:- 5 + Silo:- 195 + Battery-7A:- 250 + EB-7A:- 59 + EB-7B:- 48 + Battery-7B:- 250 + Coke Bucket Car:- 108 + Buttress 7A:- 48, + Buttress 7B = 48 + SCP Car Track = 348+ coal tower =156+ Intermediate bench = 22, Stack Flue Tunnel = 38, PECS = 80, PCH = 17, NTP1 = 8, Coke Bucket Repair Station = 27, Existing CHS Extension = 14, Pipe Rack = 40, Hammer Exchange = 34, TP8B = 21, Y-7 =.

General

A.1: completed (253/253 ).

A.11: completed (22/22 ).

A.12: completed (156/156 ).

A.13: completed (38/38 ).

A.15: completed (17/17 ).

A.16: completed (8/8 ).

A.19: completed (40/40 ).

A.2: completed (250/250 ).

A.20: completed (34/34 ).

A.21: completed (21/21 ).

A.22: completed (12/12 ).

A.24: completed (5/5 ).

A.4: completed (48/48 ).

A.5: completed (197/197 ).

A.7: completed (48/48 ).

A.8: completed (48/48 ).

B.1: completed (2160/2160 ).

B.10: completed (417/417 ).

B.11: completed (9910/9910 ).

B.12: completed (3610/3610 ).

B.16: completed (5361/5361 ).

B.18: completed (3736/3736 ).

B.19: completed (5330/5330 ).

B.2: completed (3908/3908 ).

B.21: completed (5025/5025 ).

B.22: completed (1956/1956 ).

B.23: completed (5445/5445 ).

B.24: completed (382/382 ).

B.25: completed (800/800 ).

B.26: completed (800/800 ).

B.28: completed (2532/2532 ).

B.29: completed (1013/1013 ).

B.39: completed (7495/7495 ).

B.4: completed (6000/6000 ).

B.5: completed (3786/3786 ).

B.52: completed (2905/2905 ).

B.7: completed (591/591 ).

B.8: completed (1330/1330 ).

B.9: completed (3460/3460 ).

D.19: completed (380.2/380 ).

D.2: completed (2367/2367 ).

D.20: completed (367.05/367 ).

D.27: completed (866/866 ).

D.29: completed (379/379 ).

D.30: completed (26.5/23 ).

D.41: completed (247/247 ).

D.66: completed (444/444 ).

E.14: completed (26/26 ).

E.17: completed (23/23 ).

E.5: completed (192.01/192.01 ).

FTD Achieved = 2 nos. Y-7 (P-4,P-7).

G.1: completed (3247/3247 ).

G.2: completed (16065/16065 ).

H.1: completed (10402.7/10200 ).

J.2: completed (2/2 ).

J.3: completed (19.78/12.08 ).

J.4: completed (96/96 ).

A.10: under progress (343/348 ).

A.14: under progress (68/76 ).

A.17: under progress (9/27 ).

A.18: under progress (10/14 ).

A.3: under progress (46/59 ).

A.6: under progress (100/108 ).

B.13: under progress (3508/3925 ).

B.14: under progress (4375/7235 ).

B.15: under progress (1065/2525 ).

B.17: under progress (8854/14700 ).

B.27: under progress (9531/13778 ).

B.3: under progress (4101.5/4102 ).

B.30: under progress (3270/4013 ).

B.31: under progress (1185/1246 ).

B.32: under progress (3105/3285 ).

B.33: under progress (6275/25082 ).

B.34: under progress (1460/1498 ).

B.35: under progress (761/888 ).

B.36: under progress (5710/8106 ).

B.37: under progress (2540/4544 ).

B.38: under progress (4720/8187 ).

B.40: under progress (280/752 ).

B.41: under progress (1380/2223 ).

B.42: under progress (100/6742 ).

B.43: under progress (4770/6655 ).

B.44: under progress (1375/4197 ).

B.46: under progress (1920/4654 ).

B.48: under progress (1060/2855 ).

B.49: under progress (1505/1600 ).

B.50: under progress (1070/1350 ).

B.51: under progress (360/1620 ).

B.54: under progress (250/2300 ).

B.6: under progress (850/2751.89 ).

C.1: under progress (6313/6649.2 ).

D.1: under progress (3982/4690 ).

D.10: under progress (52/182 ).

D.11: under progress (33.2/38 ).

D.12: under progress (1850/3102 ).

D.13: under progress (112.78/113 ).

D.14: under progress (335/587 ).

D.16: under progress (162.2/919 ).

D.17: under progress (761/959 ).

D.18: under progress (2168.1/3003 ).

D.21: under progress (584.82/678 ).

D.23: under progress (1398.9/5228 ).

D.24: under progress (485.5/547 ).

D.25: under progress (852.5/852.663 ).

D.26: under progress (861.35/1175.01 ).

D.28: under progress (215/704 ).

D.3: under progress (2284.19/2324 ).

D.31: under progress (154/621 ).

D.32: under progress (955.5/1325 ).

D.33: under progress (7/204 ).

D.34: under progress (176.7/185 ).

D.35: under progress (54.5/57 ).

D.37: under progress (38/92 ).

D.39: under progress (103.2/176 ).

D.4: under progress (1395/1433 ).

D.40: under progress (84/240 ).

D.42: under progress (519.5/592 ).

D.44: under progress (435/757 ).

D.45: under progress (41/182 ).

D.47: under progress (51.9/81 ).

D.48: under progress (813.5/814 ).

D.49: under progress (134/211 ).

D.5: under progress (666.72/667 ).

D.50: under progress (42.5/453 ).

D.51: under progress (164.3/302 ).

D.52: under progress (97/287 ).

D.53: under progress (884.5/1721 ).

D.54: under progress (101.5/102 ).

D.57: under progress (260.1/280 ).

D.6: under progress (88.5/369 ).

D.63: under progress (20.5/130 ).

D.65: under progress (103/440 ).

D.69: under progress (80/8115 ).

D.7: under progress (40/101 ).

D.8: under progress (84/125 ).

D.9: under progress (126.05/180 ).

E.1: under progress (731/736 ).

E.10: under progress (45/71 ).

E.11: under progress (758/842 ).

E.15: under progress (632.63/1153 ).

E.16: under progress (1/157 ).

E.18: under progress (176.678/252 ).

E.19: under progress (48.428/99 ).

E.2: under progress (215/225 ).

E.21: under progress (13.54/79 ).

E.22: under progress (195/248 ).

E.23: under progress (12.15/820 ).

E.24: under progress (84/198 ).

E.25: under progress (97.745/290 ).

E.26: under progress (53/59.7 ).

E.27: under progress (152.73/259 ).

E.29: under progress (2.023/10.5 ).

E.3: under progress (331.529/384 ).

E.30: under progress (277.09/296 ).

E.36: under progress (105.251/219.071 ).

E.37: under progress (446.576/566 ).

E.4: under progress (224.6/228 ).

E.6: under progress (8.074/12 ).

E.7: under progress (23/26 ).

E.9: under progress (63.101/276 ).

F.1: under progress (713.996/736 ).

F.10: under progress (8.8/71 ).

F.15: under progress (304.27/1153 ).

F.17: under progress (12/23 ).

F.2: under progress (132.335/225 ).

F.26: under progress (50.182/59.7 ).

F.3: under progress (70.79/384 ).

F.37: under progress (26.536/566 ).

F.5: under progress (190.953/192.01 ).

F.7: under progress (14.17/26 ).

H.2: under progress (5367.73/10200 ).

H.3: under progress (981.251/4000 ).

I.1: under progress (192/280 ).

J.1: under progress (15.912/16 ).

K.1: under progress (7192/7354 ).

K.2: under progress (3320/7354 ).

L.1: under progress (242.3/265 ).

L.2: under progress (303/500 ).

M.3: under progress (6/4000 ).

Total for Erection: under progress (6/24410 ).

Total for Supply: under progress (16751.7/24410 ).

1: yet to start.

8th June : 8 trips 9th June : 9 trips 10th June : 11 trips 11th June : 12 trips Cumulative : 40 trips Regards KK.

A.23: yet to start.

A.9: yet to start.

B.20: yet to start (0/928 ).

B.45: yet to start (0/1640 ).

B.47: yet to start (0/515 ).

B.53: yet to start.

Concerns:-: yet to start.

D.15: yet to start (0/1070 ).

D.22: yet to start (0/436 ).

D.36: yet to start (0/123 ).

D.38: yet to start (0/69 ).

D.43: yet to start (0/47 ).

D.46: yet to start (0/16 ).

D.55: yet to start (0/200 ).

D.56: yet to start (0/1844 ).

D.58: yet to start.

D.59: yet to start (0/25 ).

D.60: yet to start (0/46 ).

D.61: yet to start (0/98 ).

D.62: yet to start (0/130 ).

D.64: yet to start (0/40 ).

D.67: yet to start (0/167 ).

D.68: yet to start (0/95 ).

E.12: yet to start (0/6 ).

E.13: yet to start (0/318 ).

E.20: yet to start (0/30 ).

E.28: yet to start (0/1.42 ).

E.31: yet to start (0/1.104 ).

E.32: yet to start (0/0.921 ).

E.33: yet to start (0/0.982 ).

E.34: yet to start (0/0.303 ).

E.35: yet to start (0/2.712 ).

E.38: yet to start (0/5 ).

E.39: yet to start (0/126 ).

E.40: yet to start (0/58 ).

E.41: yet to start (0/26 ).

E.42: yet to start.

E.43: yet to start.

E.44: yet to start.

E.45: yet to start.

E.8: yet to start (0/3 ).

F.11: yet to start (0/842 ).

F.12: yet to start (0/6 ).

F.13: yet to start (0/318 ).

F.14: yet to start (0/26 ).

F.16: yet to start (0/157 ).

F.18: yet to start (0/252 ).

F.19: yet to start (0/99 ).

F.20: yet to start (0/30 ).

F.21: yet to start (0/79 ).

F.22: yet to start (0/248 ).

F.23: yet to start (0/820 ).

F.24: yet to start (0/198 ).

F.25: yet to start (0/290 ).

F.27: yet to start (0/259 ).

F.28: yet to start (0/1.42 ).

F.29: yet to start (0/10.5 ).

F.30: yet to start (0/296 ).

F.31: yet to start (0/1.104 ).

F.32: yet to start (0/0.921 ).

F.33: yet to start (0/0.982 ).

F.34: yet to start (0/0.303 ).

F.35: yet to start (0/2.712 ).

F.36: yet to start (0/219.071 ).

F.38: yet to start (0/5 ).

F.39: yet to start (0/126 ).

F.4: yet to start (0/228 ).

F.40: yet to start (0/58 ).

F.41: yet to start.

F.42: yet to start.

F.43: yet to start.

F.44: yet to start.

F.6: yet to start (0/12 ).

F.8: yet to start (0/3 ).

F.9: yet to start (0/276 ).

G.3: yet to start.

G.4: yet to start (0/375867 ).

H.4: yet to start.

I.2: yet to start.

J.5: yet to start.

K.3: yet to start.

L.3: yet to start.

M.1: yet to start.

M.2: yet to start.

M.4: yet to start.

NOTE:: yet to start.

WIP = 0 nos. Regards KK.