Physical and Financial Progress Report of CAPEX Projects for FY2026-27 (SAIL)

- Overview of CAPEX Progress

|  | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4 |  |  |  | Total | % of Total target |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Apr | May | Jun | Total Q1 | July | Aug | Sep | Total Q2 | Oct | Nov | Dec | Total Q3 | Jan | Feb | Mar | Total Q4 |  |  |
| CAPEX (BE) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Actual Expd |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

All figures in Rs. crs.

- Overview of CAPEX Projects

| S. N. | Category | Total no. of Projects | Total cost of Projects (Rs cr.) | Expenditure incurred up to FY24-25 (Rs cr.) | CAPEX for FY 25-26 (RE) (Rs cr.) | Expenditure in FY25-26 till Mar’26 (Rs cr.) | Total Expenditure (Rs cr.) | No. of projects: i. On time ii. Delayed up to 01 year iii. Delayed more than 01 year |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1a | Being implemented from last FY | 28 | 5628.55 | 1078.77 | 1483.00 | 630.01 | 1708.78 | i. Ontime-37 ii. Delay<1-11 iii. Delay>1-4 |
| 1b | Implementation started during FY24-25 | 24 | 183.80 | 0.00 | 33.30 | 0.01 | 0.01 |  |
| 1 | Total Ongoing projects (1a+1b) | 52 | 5812.35 | 1078.77 | 1516.30 | 630.02 | 1708.79 |  |
| 2 | Milestone payments in completed projects |  |  |  | 288.51 | 172.31 | 172.31 |  |
| 3a | New Projects under tendering/ final approval and contract award | 15 | 440.13 | 0.74 | 10.40 | 0.00 | 0.74 |  |
| 3b | New Projects under Stage-I approval | 4 | 249.87 | 0.00 | 0.00 | 0.00 | 0.00 |  |
| 3 | Total New projects under consideration (3a+3b) | 19.00 | 690.00 | 0.74 | 10.40 | 0.00 | 0.74 |  |
| 4 | Spares & Capital Repairs |  |  |  | 334.80 | 2.20 | 2.20 |  |
| 5 | Other schemes/ JVs |  |  |  |  |  |  |  |
|  | Total | 71.00 | 6502.35 | 1079.51 | 2150.01 | 804.53 | 1884.04 |  |

Note COB#7 is counted as 3 Projects in SI -1a, Category- Being implemented from last FY

Format for Ongoing Projects

- Physical and Financial Progress:

| SN | Name of Project/ Package (1) | i. Total Project Cost (Rs. cr.) ii. Revised cost (Rscr), if any (2) | i. Date of approval ii. Date of award of contract (dd/mm/yy) (3) | i. Original date of completion (dd/mm/yy) ii. Revised date of completion (dd/mm/yy), if any (4) | Physical Progress (%) i. till Mar. 2026 ii. planned during FY26-27 iii. total till month June’26 (5) | CAPEX till 31.3.26 (Rscr) (6) | CAPEX target for FY26-27 BE (Rscr) (7) | CAPEX expenditure made in FY26-27 (Rscr) (8) | Cumm CAPEX expd till the Month (Rscr) (9) | Reasons of delay, if any (10) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Projects =>Rs 50 cr |  |  |  |  |  |  |  |  |  |  |
| Rourkela Steel Plant |  |  |  |  |  |  |  |  |  |  |
| 1 | Installation of 1000 tpd Oxygen Plant on COM basis | On COM basis | i. Aug'23 ii Sep'23 | - Feb'26 - Sept’26 | - | - | - | - | - | Delay in supply of equipments & civil work |
| 2 | Installation of 0.18 MTPA Micro-pellet plant at Rourkela Steel Plant on COM basis | On COM basis | i. Jul’24 ii. Aug'24 | - Jul'26 | - | - | - | - | - |  |
| 3 | COB#7 - Battery Proper-PKG-2 | 2608.16 | i. Sep'24 ii. Oct'24 | i. Mar'28 | - 36.69 - 56.25 - 13.8 | 768.38 | 700 | 376.06 | 1144.44 |  |
| 4 | COB#7 - CDCP-Pkg-3 | 1037.57 | i. Sep'24 ii. Feb’26 | i. Aug’28 | - | 36.66 | 100 | 36.66 | 73.32 | Contract Signed in Feb’26 |
| 5 | COB#7 - BPP-Pkg -4 | 1150.54 | i. Sep'24 ii. Oct'24 | i. Mar'28 | - 11.63 - 37.96 - 9.57 | 58.90 | 315 | 106.66 | 165.56 |  |
| 6 | 2 MTPA Pellet Plant on COM Basis | On COM basis | i. Jan'25 ii.Feb'25 | i. Feb'27 | - |  |  |  |  |  |
| 7 | Implementation of Treatment System-2 Under ZLD | 216.02 | i. Feb’25 ii. Mar'25 | i. Sep’26 ii. | i. 67.55 ii. 32.45 iii. 15.64 | 83.65 | 90 | 33.56 | 117.21 |  |
| 8 | 4Th Stove for BF - 5 | 120.51 | i. Jan'25 ii. Feb'25 | i. Oct'26 | i. 38.60 ii. 61.40 iii. 14.81 | 22.74 | 55 | 31.12 | 53.86 |  |
| 9 | Replacement of one EOT crane (250+75/10)t in converter charging bay of SMS-2 | 87.48 | i. Apr'25 ii. May'25 | i. Nov'26 | - 9.19 - 90.81 - 0.81 | 10.12 | 47 | 1.78 | 11.90 |  |
| 10 | Product Testing Laboratory for NPM, SPP and HSM-2, RSP | 155.26 | i. Jun'25 ii. Jul'25 | i. Aug'27 | - 28.76 - 65.69 - 23.8 | 27.94 | 50 | 25.4 | 53.34 |  |
| - Projects <Rs. 50 Cr. 42 Nos. |  | 444.05 |  |  |  | 70.38 | 159.30 | 18.78 | 89.16 |  |

Format for New CAPEX Projects under consideration for FY 2025-26

| SN | Name of Project to be taken up/ Name of Plant (1) | Estimated target project Cost (Rs. Cr.) (2) | Date of In-Principle / Stage-I Approval (3) | Date of NIT/ Bid out (4) | Planned/Actual Date of Final Approval (5) | Planned/ Actual date of Contract Award (6) | CAPEX target for FY26-27 (Rscr) (7) | CAPEX Expd. till the Month during FY26-27 (Rscr) (8) | Reasons of delay, if any (9) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Projects =>Rs 50 cr |  |  |  |  |  |  |  |  |  |
| Rourkela Steel Plant |  |  |  |  |  |  |  |  |  |
|  | Transportation of Coal from COB#6 to COB#1-5 along with installation of Silos | 367.15 | Dec’23 | 1st Tender 08.02.2024 2nd Tender 29.03.2025 3rd Tender 06.04.2026 | Oct’26 | Nov’26 | - | 0.74 |  |
| Projects <Rs. 50 cr (14 nos.) |  | 72.98 |  |  |  |  | 10.40 | 0.00 | - |
| Projects under Stage-I approval (Dust Extraction System for BF-I + Dust extraction System for SP-III+ Provision of Mixed Gas Firing in oil fired kilns at CP II + Upgradation of Electrics for 2 nos. Hot Metal Handling Cranes at SMS-II) (4 Nos.) |  | 249.87 |  |  |  |  | 0.00 | 0.00 | - |

- CAPEX including CET debit, Consultancy charges and other schemes considered.