## MOS Capex Format
| Overview of RSP CAPEX projects | [6 empty] | Report Month | 2026-06-30
S.N. | Category | Total no. of Projects | Total cost of Projects | Expenditure incurred up to FY 2025-26 | CAPEX for FY 26-27 (BE) | Expenditure in FY26-27 | Total Expenditure (Rs cr.) | Progress of Projects in column 3 No. of projects: i.On time ii.Delayed up to 01 year iii.Delayed more than 01 year (10)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
| Being implemented from last FY | 28 | 5628.5499 | 1078.7716 | 1483 | 630.0059 | 1708.7775
| Corporate AMR | 10 | 5368.3087 | 1008.39 | 1357 | 611.24 | 1619.63
| Ontime | 9 | 5368.3087 | 1008.39 | 1357 | 611.24 | 1619.63
| Delay<1 | 1 | 0 | 0 | 0 | 0 | 0
| Delay>1 | 0 | 0 | 0 | 0 | 0 | 0
| Plant AMR(<30 Cr.) | 18 | 260.2412 | 70.3816 | 126 | 18.7659 | 89.1475
| Ontime | 5 | 70.0774 | 0.1682 | 29 | 0.74435 | 0.91255
| Delay<1 | 9 | 116.2522 | 37.7353 | 63 | 10.9389 | 48.6742
| Delay>1 | 4 | 73.9116 | 32.4781 | 34 | 7.0826 | 39.5608
| Implementation started during FY25-26 | 24 | 183.804 | 0 | 33.3 | 0.0093594 | 0.0093594
| Corporate AMR | 0 | 0 | 0 | 0 | 0 | 0
| Ontime | 0 | 0 | 0 | 0 | 0 | 0
| Delay<1 | 0 | 0 | 0 | 0 | 0 | 0
| Delay>1 | 0 | 0 | 0 | 0 | 0 | 0
| Plant AMR(<30 Cr.) | 24 | 183.804 | 0 | 33.3 | 0.0093594 | 0.0093594
| Ontime | 23 | 183.4184 | 0 | 33 | 0.0093594 | 0.0093594
| Delay<1 | 1 | 0.38553 | 0 | 0.3 | 0 | 0
| Delay>1 | 0 | 0 | 0 | 0 | 0 | 0
| Total Ongoing projects | 52 | 5812.3539 | 1078.7716 | 1516.3 | 630.0152 | 1708.7869
| Ontime | 37 | 5621.8045 | 1008.5582 | 1419 | 611.9937 | 1620.5519
| Delay<1 | 11 | 116.6377 | 37.7353 | 63.3 | 10.9389 | 48.6742
| Delay>1 | 4 | 73.9116 | 32.4781 | 34 | 7.0826 | 39.5608
2 | Milestone payments in completed projects incl. MEP |  |  |  | 288.5081 | 172.3148 | 172.3148
| MEP | 1 | 14240 | 14183.99 | 0 | 0 | 14183.99
| Others (COB#4) |  |  |  |  | 0 | 0
| 30 MLD STP for township | 1 | 96.62 | 87.02 | 12.2 | 0.87 | 87.89
| TS#1 | 1 | 158.17 | 165.65 | 0 | 0.21 | 165.86
| COB #2 | 1 | 433.58 | 461.48 | 5 | 1.17 | 462.65
| Caster-IV | 1 | 1105.23 | 897.96 | 195 | 77.7 | 975.66
| NHSM | 1 | 4033.88 | 4177.77 | 0 | 0 | 4177.77
| Power enabling package for oxygen | 1 | 83.49 | 60.28 | 16 | 5.29 | 65.57
| Plant AMR(<30 Cr.)-Completed/EDC |  |  |  | 34.59 | 80.5741 | 80.5741
| Plant AMR(<30 Cr.)-old schemes | 9 | 49.9706 | 14.4408 | 24.38 | 5.6625 | 20.1033
| Plant AMR(<30 Cr.)-new schemes | 2 | 1.4124 | 0 | 1.3381 | 0.83811 | 0.83811
3a | New Projects under tendering/ final approval and contract award | 15 | 440.1264 | 0.74 | 10.4 | 0 | 0.74
| Corporate AMR-under tendering | 1 | 367.15 | 0.74 | 0 | 0 | 0.74 | Coal Transportation
| Corporate AMR- under final approval and contract award | 0 | 0 | 0 | 0 | 0 | 0
| Plant AMR(<30 Cr.) | 14 | 72.9764 | 0 | 10.4 | 0 | 0
3b | New Projects under Stage-I approval | 4 | 249.87 | 0 | 0 | 0 | 0
| Dust Extraction for BF#1 | 1 | 52.56 | 0 | 0 | 0 | 0
| Provision of Mixed Gas Firing in oil fired kilns at CP II | 1 | 64.66 | 0 | 0 | 0 | 0
| Dust Extraction for SP-III | 1 | 70.71 | 0 | 0 | 0 | 0
| Upgradation of Electrics for 2 nos. Hot Metal Handling Cranes at SMS-II | 1 | 61.94 | 0 | 0 | 0 | 0
| Others-CET Consultancy debit, etc |  |  |  | 0 | 0 | 0
3 | Total New projects under consideration (3a+3b) | 19 | 689.9964 | 0.74 | 10.4 | 0 | 0.74 | 3a+3b
4 | Spares & Capital Repairs |  |  |  | 334.8 | 2.2 | 2.2
5 | Other schemes/ JVs | [5 empty] | 0
| Total | 71 | 6502.3502 | 1079.5116 | 2150.0081 | 804.53 | 1884.0416
Note: COB#7 - Considered as 3 Projects in count ( PKG2- Battery proper , PKG3- CDCP, PKG4- BPP)

## Format Projects-PMC
Format for Projects-PMC
Timeline Analysis of Ongoing Projects
|  | No of Projects | Total Cost (Rs Cr) | Expenditure incurred up to FY 2025-26 | Financial progress in FY26-27 |  | Total Expd till
[5 empty] | CAPEX target | Expd in FY26-27 | 2026-06-30
New projects (yet to be awarded) |  | 19 | 689.9964 | 0.74 | 10.4 | 0 | 0.74
Ongoing Projects |  | 52 | 5812.3539 | 1078.7716 | 1516.3 | 630.0152 | 1708.7869
Total Projects |  | 71 | 6502.3502 | 1079.5116 | 1526.7 | 630.0152 | 1709.5269
Timeline of Ongoing Projects(<50 crore) | On time | 28 | 253.4958 | 0.1682 | 62 | 0.75371 | 0.92191
| Delayed upto 1 year | 10 | 116.6377 | 37.7353 | 63.3 | 10.9389 | 48.6742
| Delayed > 1 year | 4 | 73.9116 | 32.4781 | 34 | 7.0826 | 39.5608
Timeline of Ongoing Projects(>50 crore) | On time | 9 | 5368.3087 | 1008.39 | 1357 | 611.24 | 1619.63
| Delayed upto 1 year | 1 | 0 | 0 | 0 | 0 | 0
| Delayed > 1 year | 0 | 0 | 0 | 0 | 0 | 0
Other Payments related to Projects/CAPEXs
Milestone payments in completed projects |  |  |  |  | 288.5081 | 172.3148 | 172.3148
Spares /Capital repair |  |  |  |  | 334.8 | 2.2 | 2.2
Other schemes/ JV proj
Total |  | 71 | 6502.3502 | 1079.5116 | 2150.0081 | 804.53 | 1884.0416

## Details of Ongoing Projects
Details of On-going Projects As on |  | 2026-06-30
Category | > 30 Cr | < 30 Cr | TOTAL
Number of Total Projects | 10 | 42 | 52
On Time | 9 | 28 | 37
Delayed by less than year | 1 | 10 | 11
Delayed by more than year | 0 | 4 | 4
Projects in BOO/COM/MDO mode (Out of Total Projects) | 3 | 0