## SUMMARY (hidden)
Annexure-IV
STEEL AUTHORITY OF INDIA LTD.
CAPEX STATUS OF PROJECTS -SANCTIONED PROJECTS (on-going & completed schemes)
Rs in crore
SN | Name of the Plant/Unit | Sanctioned | Anticipated | Actuals | Balance as on | Expenditure Apr-Oct'18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total Estimate | Balance amount required for completion of project after 2019-20
|  | Cost | Cost | upto |  |  | RE | BE | Estimate | Estimate | Estimate | 2018-23
|  |  |  | 31.03.18 | 01.04.2018
1 | Bhilai Steel Plant
1.1 | On-going schemes | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF!
1.2 | Completed Schemes | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF!
| Total BSP | #REF! | #REF! | #REF! | #REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
2 | Durgapur Steel Plant
2.1 | On-going schemes | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF!
2.2 | Completed Schemes | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF!
| Total DSP | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
3 | Rourkela Steel Plant
3.1 | On-going schemes | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF!
3.2 | Completed Schemes | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF!
| Total RSP | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
4 | Bokaro Steel Plant
4.1 | On-going schemes | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF!
4.2 | Completed Schemes | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF!
| Total BSL | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | #REF!
5 | ISP
5.1 | On-going schemes | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF!
5.2 | Completed Schemes | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF!
| Total ISP | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
6 | Alloy Steels Plant
6.1 | On-going schemes | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF!
6.2 | Completed Schemes | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF!
| Total ASP | #REF! | #N/A | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #REF!
7 | Salem Steel Plant
7.1 | On-going schemes | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF!
7.2 | Completed Schemes | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF!
| Total SSP | #REF! | #N/A | #N/A | #N/A | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
8 | VISL
8.1 | On-going schemes | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF!
8.2 | Completed Schemes | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF!
| Total VISL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
9 | Raw Materials Division
9.1 | On-going schemes | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF!
9.2 | Completed Schemes | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF!
| Total RMD | #REF! | #N/A | #N/A | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
10 | Central Units
10.1 | On-going schemes | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF!
10.2 | Completed Schemes | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF!
10.4 | JV | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF!
| Total CU (except JV) | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  |  | #REF!
11 | Chandrapur Ferro Alloy Plant
11.1 | On-going schemes | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF!
11.2 | Completed Schemes | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF!
| Total CFP | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF!
12 | Total SAIL
12.1 | On-going schemes | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
12.2 | Completed Schemes | #N/A | #REF! | #N/A | #REF! | #REF! | #N/A | #N/A | 0 | #N/A | #N/A | #REF! | #REF!
12.4 | Capital Repair/Spares |  |  |  |  | #REF! | #REF! | #REF!
12.5 | New Schemes |  |  |  |  | #REF! | #REF! | #REF!
| Grand Total | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!

## Month-wise plan RE (hidden)
STEEL AUTHORITY OF INDIA LTD.
Name of the Plant/Unit :
Rs. in Crore
SN | Name of the Scheme | Sanctioned Cost | Anticipated Cost | Actual Capex Upto 31.03.2024 | Physical Progress Upto 31.03.2024 (For >30 Cr On-going) | Physical Progress Planned for 2024-25 (For >30 Cr On-going) | 2024-25 BE | Apr'2024 | [7 empty] | May'2024 | [7 empty] | Jun'2024 | [7 empty] | Jul'2024 | [7 empty] | Aug'2024 | [7 empty] | Sep'2024 | [7 empty] | Oct'2024 | [7 empty] | Nov'2024 | [7 empty] | Dec'2024 | [7 empty] | Jan'2025 | [7 empty] | Feb'2025 | [7 empty] | Mar'2025
[8 empty] | Capex plan 1st F/N | Actual Capex 1st F/N | Capex plan 2nd F/N | Actual Capex 2nd F/N | CAPEX Plan | Actual CAPEX | Phy. Prog. Plan for the month (%) | Actual Prog. For the month (%) | Capex plan 1st F/N | Actual Capex 1st F/N | Capex plan 2nd F/N | Actual Capex 2nd F/N | CAPEX Plan | Actual CAPEX | Phy. Prog. Plan for the month (%) | Actual Prog. For the month (%) | Capex plan 1st F/N | Actual Capex 1st F/N | Capex plan 2nd F/N | Actual Capex 2nd F/N | CAPEX Plan | Actual CAPEX | Phy. Prog. Plan for the month (%) | Actual Prog. For the month (%) | Capex plan 1st F/N | Actual Capex 1st F/N | Capex plan 2nd F/N | Actual Capex 2nd F/N | CAPEX Plan | Actual CAPEX | Phy. Prog. Plan for the month (%) | Actual Prog. For the month (%) | Capex plan 1st F/N | Actual Capex 1st F/N | Capex plan 2nd F/N | Actual Capex 2nd F/N | CAPEX Plan | Actual CAPEX | Phy. Prog. Plan for the month (%) | Actual Prog. For the month (%) | Capex plan 1st F/N | Actual Capex 1st F/N | Capex plan 2nd F/N | Actual Capex 2nd F/N | CAPEX Plan | Actual CAPEX | Phy. Prog. Plan for the month (%) | Actual Prog. For the month (%) | Capex plan 1st F/N | Actual Capex 1st F/N | Capex plan 2nd F/N | Actual Capex 2nd F/N | CAPEX Plan | Actual CAPEX | Phy. Prog. Plan for the month (%) | Actual Prog. For the month (%) | Capex plan 1st F/N | Actual Capex 1st F/N | Capex plan 2nd F/N | Actual Capex 2nd F/N | CAPEX Plan (RE) | Actual CAPEX | Phy. Prog. Plan for the month (%) | Actual Prog. For the month (%) | Capex plan 1st F/N | Actual Capex 1st F/N | Capex plan 2nd F/N | Actual Capex 2nd F/N | CAPEX Plan (RE) | Actual CAPEX | Phy. Prog. Plan for the month (%) | Actual Prog. For the month (%) | Capex plan 1st F/N | Actual Capex 1st F/N | Capex plan 2nd F/N | Actual Capex 2nd F/N | CAPEX Plan (RE) | Actual CAPEX | Phy. Prog. Plan for the month (%) | Actual Prog. For the month (%) | Capex plan 1st F/N | Actual Capex 1st F/N | Capex plan 2nd F/N | Actual Capex 2nd F/N | CAPEX Plan (RE) | Actual CAPEX | Phy. Prog. Plan for the month (%) | Actual Prog. For the month (%) | Capex plan 1st F/N | Actual Capex 1st F/N | Capex plan 2nd F/N | Actual Capex 2nd F/N | CAPEX Plan (RE) | Actual CAPEX | Phy. Prog. Plan for the month (%) | Actual Prog. For the month (%) | Cum CAPEX Plan | Cum Actual CAPEX | Cum Phy. Prog. Plan for the month (%) | Cum Actual Prog. For the month (%)
A | MEP | 14240 | 14240 | 14183.73 |  |  | 7.6 |  |  |  |  | 0.26 | 0.26 | [6 empty] | 0 | 0 | [30 empty] | 0 | 0 | [14 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | [7 empty] | 0 | [7 empty] | 2.19 | [7 empty] | 2.45
B | Completed AMR schemes
1 | Installation of Treatment System#1 under ZLD | 158.17 | 158.17 | 138.82 |  |  | 7.9 |  |  |  |  | 3.62 | 3.62 | [6 empty] | 0 | 0 | [6 empty] | 1.56 | 1.56 | [6 empty] | 0.44 | 0.44 | [6 empty] | 0.38 | 0.38 | [6 empty] | 0.37 | 0.37 | [15 empty] | 0.18 | [7 empty] | 0.17186 | [7 empty] | 0.14 | [6 empty] | 0.18 | [7 empty] | 1.35 | [7 empty] | 7.9
2 | Others(NHSM) | [10 empty] | 0.47 | 0.47 | [14 empty] | 0.02 | 0.02
3
| Other schemes <Rs 30 Crore | [50 empty] | 0.27 | 0.27 | [6 empty] | 0.1 | 0.1
| Sub-total (B) | 158.17 | 158.17 | 138.82 |  |  | 7.9 |  |  |  |  | 4.09 | 4.09 | [6 empty] | 0 | 0 | [6 empty] | 1.58 | 1.58 | [6 empty] | 0.44 | 0.44 | [6 empty] | 0.38 | 0.38 | [6 empty] | 0.64 | 0.64 | [6 empty] | 0.1 | 0.1 | [6 empty] | 0 | 0.18 | [6 empty] | 0 | 0.17186 | [6 empty] | 0 | 0.14 | [6 empty] | 0.18 | 0 | [6 empty] | 1.35 | 0 | [6 empty] | 8.76
C | Ongoing AMR Schemes
1 | COB#2 | 433.58 | 433.58 | 53.15 | 78.83% | 19.2% | 53.15 |  |  |  |  | 5.03 | 5.03 | 4.16% | 2.163% |  |  |  |  | 4.32 | 4.32 | 4.14% | 1.31% |  |  |  |  | 19.06 | 19.06 | 4.4% | 1.295% |  |  |  |  | 5.99 | 5.99 | 3.65% | 2.096% |  |  |  |  | 3.22 | 3.22 | 2.85% | 1.779% |  |  |  |  | 4.56 | 4.56 |  | 2.004% |  |  |  |  | 11.63 | 11.63 |  | 2.78% |  |  |  |  | 0.82 | 5.66 |  | 1.033% |  |  |  |  | 0 | 0.62 |  | 0.64% |  |  |  |  | 0 | 0.9 |  | 0.76% |  |  |  |  | 0.14 | 11.09 |  | 0.6% |  |  |  |  | 0 | [7 empty] | 54.77 | 72.08 | 0.192 | 16.46% | 95.29%
2 | Caster-IV | 1105.23 | 1105.23 | 357 | 44.16% | 54.72% | 357 |  |  |  |  | 6.49 | 6.49 | 4.84% | 4.881% |  |  |  |  | 25.88 | 25.88 | 6.33% | 1.924% |  |  |  |  | 18.01 | 18.01 | 5.52% | 2.737% |  |  |  |  | 44.22 | 44.22 | 6.24% | 3.901% |  |  |  |  | 36.65 | 36.65 | 6.71% | 2.748% |  |  |  |  | 25.09 | 25.09 | 8.64% | 2.634% |  |  |  |  | 50.2 | 50.2 | 3.84% | 3.68% |  |  |  |  | 16.99 | 16.99 | 2.01% | 3.561% |  |  |  |  | 30 | 20.8 | 5.3% | 3.99% |  |  |  |  | 30 | 28.66 | 2.13% | 0.8% |  |  |  |  | 30 | 53.54 | 2.3% | 5.87% |  |  |  |  | 43.47 |  | 0.86% | [5 empty] | 357 |  |  | 36.72% | 80.89%
3 | Power enabling package for oxygen | 69.62 | 69.62 | 16 | 62.87% | 37.13% | 16 |  |  |  |  | 1.79 | 1.79 | 2.85% | 1.7% |  |  |  |  | 0.9 | 0.9 | 7.11% | 6.459% |  |  |  |  | 1.69 | 1.69 | 3.67% | 5.93% |  |  |  |  | 6.43 | 6.43 | 4.75% | 1.516% |  |  |  |  | 0.56 | 0.56 | 2.09% | 4.053% |  |  |  |  | 0.52 | 0.52 | 16.66% | 0.5494% |  |  |  |  | 1.47 | 1.47 |  | 0% |  |  |  |  | 0.96 | 0.96 |  | 0.518% |  |  |  |  | 0 | 0.15 |  | 0.13% |  |  |  |  | 0 | 0.95 |  | 0.01% |  |  |  |  | 0 | 0.63 | [6 empty] | 1.68 | [7 empty] | 16 |  |  | 20.86% | 83.73%
4 | STP for township | 96.62 | 96.62 | 48 | 12.55% | 87.45% | 48 |  |  |  |  | 1.73 | 1.73 | 3.34% | 1.22% |  |  |  |  | 3.31 | 3.31 | 3.62% | 2.296% |  |  |  |  | 0.53 | 0.53 | 2.43% | 3.24% |  |  |  |  | 3.58 | 3.58 | 3.88% | 1.764% |  |  |  |  | 3.1 | 3.1 | 6.76% | 1.654% |  |  |  |  | 2.34 | 2.34 | 10.19% | 1.188% |  |  |  |  | 7.67 | 7.67 | 14.24% | 2.23% |  |  |  |  | 3.13 | 3.13 | 13.85% | 1.491% |  |  |  |  | 5 | 6.15 | 11.41% | 7.57% |  |  |  |  | 5 | 5.41 | 12.16% | 18.68% |  |  |  |  | 5 | 5.15 | 5.57% | 8.4% |  |  |  |  | 7.61 |  | 0% | [5 empty] | 48 |  |  | 49.73% | 62.28%
5 | Oxygen Plant on COM Basis | 0 | 0 |  |  |  | 0 | [103 empty] | 0% | 0%
Others
| Other schemes <Rs 30 Crore | [5 empty] | 200 | [44 empty] | 26.33 | 26.33 | [6 empty] | 29.41 | 29.41 | [6 empty] | 26.54 | 26.54 | [6 empty] | 4 | 27.08 | [6 empty] | 5 | 7.69 | [6 empty] | 5 | 41.9 | [6 empty] | 5.63 | [7 empty] | 101.91
| Sub-total (C) | 1705.05 | 1705.05 | 474.15 |  |  | 674.15 |  |  |  |  | 15.04 | 15.04 | [6 empty] | 34.41 | 34.41 | [6 empty] | 39.29 | 39.29 | [6 empty] | 60.22 | 60.22 | [6 empty] | 43.53 | 43.53 | [6 empty] | 58.84 | 58.84 | [6 empty] | 100.38 | 100.38 | [6 empty] | 48.44 | 53.28 | [6 empty] | 39 | 54.8 | [6 empty] | 40 | 43.61 | [6 empty] | 40.14 | 112.31 | [6 empty] | 58.39 | 0 | [6 empty] | 577.68
C1 | Completed Schemes from 'C'
Details along with names to be given for >30 Cr schemes (For <30 cr, to be given in table below)
| Total Sanctioned schemes (A+B+C) | 16103.22 | 16103.22 | 14796.7 |  |  | 689.65 |  |  |  |  | 19.39 | 19.39 | [6 empty] | 34.41 | 34.41 | [6 empty] | 40.87 | 40.87 | [6 empty] | 60.66 | 60.66 | [6 empty] | 43.91 | 43.91 | [6 empty] | 59.48 | 59.48 | [6 empty] | 100.48 | 100.48 | [6 empty] | 48.44 | 53.46 | [6 empty] | 39 | 54.9719 | [6 empty] | 40 | 43.75 | [6 empty] | 40.32 | 112.31 | [6 empty] | 61.93 | 0 | [6 empty] | 588.89
D | Provision for Schemes to be considered
D1 | Approved In-principle
1 | 4th Stove BF#5 | 76.59 | 76.59 | 0.66 |  |  | 9 | [20 empty] | 0.18 | 0.18 | [22 empty] | 0.08 | 0.08 | [14 empty] | 0 | 0.01 | [22 empty] | 0 | [7 empty] | 0 | [7 empty] | 0.26
2 | COB#7 | 2882.53 | 2882.53 | 12.14 |  |  | 136.25 | [20 empty] | 0.12 | 0.12 | [14 empty] | 0.16 | 0.16 | [6 empty] | 0.12 | 0.12 | [14 empty] | 0 | 0.64 | [6 empty] | 50 | [7 empty] | 30 | 48.26 | [6 empty] | 19.6 | [7 empty] | 0 | [7 empty] | 100
3 | Pellet Plant on COM Basis | 0 | 0 |  |  |  | 0
4 | Micro-Pellet Plant on COM Basis | 0 | 0 |  |  |  | 0
5 | Treatment System#2 | 177.22 | 177.22 |  |  |  | 0 | [60 empty] | 0.1 | [23 empty] | 0.08
6 | Coal Transportation | 367.55 | 367.55 |  |  |  | 0
Other schemes <Rs 30 Crore
| Sub-total (D1) | 3503.89 | 3503.89 |  |  |  | 145.25 |  |  |  |  | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0.3 | 0.3 | [6 empty] | 0 | 0 | [6 empty] | 0.16 | 0.16 | [6 empty] | 0.2 | 0.2 | [6 empty] | 0 | 0 | [6 empty] | 0.1 | 0.65 | [6 empty] | 50 | 0 | [6 empty] | 30 | 48.26 | [6 empty] | 19.68 | 0 | [6 empty] | 0 | 0 | [6 empty] | 100.44
D1-I | Ordered schemes from 'D1'
Details along with names to be given for >30 Cr schemes (For <30 cr, to be given in table below)
D2 | Proposals under consideration
1 | New Product Testing Laboratory | 186.6 | 186.6 | 0.89 |  |  | 18 | [20 empty] | 0.02 | 0.02 | [22 empty] | 0.01 | 0.01 | [15 empty] | 0.23 | [22 empty] | 0 | [7 empty] | 0 | [7 empty] | 0.03
2 | Mixed Gas Booster | 124.55 | 124.55 | 0.76 |  |  | 0 | [20 empty] | 0.04 | 0.04
| Others(SMS#3) | [5 empty] | 0 |  |  |  |  | 0.02 | 0.02 | [14 empty] | 0.08 | 0.08 | [6 empty] | 1.11 | 1.11 | [14 empty] | 0.05 | 0.05 | [15 empty] | 0.94 | [38 empty] | 1.26
Other schemes <Rs 30 Crore
| Sub-total (D2) |  | 311.15 |  |  |  | 18 |  |  |  |  | 0.02 | 0.02 | [6 empty] | 0 | 0 | [6 empty] | 0.14 | 0.14 | [6 empty] | 1.11 | 1.11 | [6 empty] | 0 | 0 | [6 empty] | 0.06 | 0.06 | [6 empty] | 0 | 0 | [6 empty] | 0 | 1.17 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 1.33
D2-I | Ordered schemes from 'D2'
Details along with names to be given for >30 Cr schemes (For <30 cr, to be given in table below)
Allocation for approval of FY 2023-24
Plant Level Schemes FY 2024-25
| Total Provision for Schemes to be considered (D=D1+D2) | 3503.89 | 3815.04 |  |  |  | 163.25 |  |  |  |  | 0.02 | 0.02 | [6 empty] | 0 | 0 | [6 empty] | 0.44 | 0.44 | [6 empty] | 1.11 | 1.11 | [6 empty] | 0.16 | 0.16 | [6 empty] | 0.26 | 0.26 | [6 empty] | 0 | 0 | [6 empty] | 0.1 | 1.82 | [6 empty] | 50 | 0 | [6 empty] | 30 | 48.26 | [6 empty] | 19.68 | 0 | [6 empty] | 0 | 0 | [6 empty] | 101.77
E | Capital Repairs/Spares
1 | Capital Spares (As per IndAs) | [5 empty] | 210.1 |  |  |  |  | 5.8 | 5.8 | [6 empty] | 10.81 | 10.81 | [6 empty] | 13.61 | 13.61 | [6 empty] | 5.2 | 5.2 | [6 empty] | 10.1 | 10.1 | [6 empty] | 15.5 | 15.5 | [6 empty] | 10 | 10 | [6 empty] | 70.56 | 63.82 | [6 empty] | 25 | 59.23 | [6 empty] | 40 | 18.09 | [6 empty] | 40 | 20.5 | [6 empty] | 43.42 | [7 empty] | 290
2 | Capital Repairs (As per IndAs)
| Sub-total (E) | [5 empty] | 210.1 |  |  |  |  | 5.8 | 5.8 | [6 empty] | 10.81 | 10.81 | [6 empty] | 13.61 | 13.61 | [6 empty] | 5.2 | 5.2 | [6 empty] | 10.1 | 10.1 | [6 empty] | 15.5 | 15.5 | [6 empty] | 10 | 10 | [6 empty] | 70.56 | 63.82 | [6 empty] | 25 | 59.23 | [6 empty] | 40 | 18.09 | [6 empty] | 40 | 20.5 | [6 empty] | 43.42 | 0 | [6 empty] | 290
Summary:
| Allocation for Sanctioned schemes (A+B+C) | 16103.22 | 16103.22 | 14796.7 |  |  | 689.65 |  |  |  |  | 19.39 | 19.39 | [6 empty] | 34.41 | 34.41 | [6 empty] | 40.87 | 40.87 | [6 empty] | 60.66 | 60.66 | [6 empty] | 43.91 | 43.91 | [6 empty] | 59.48 | 59.48 | [6 empty] | 100.48 | 100.48 | [6 empty] | 48.44 | 53.46 | [6 empty] | 39 | 54.9719 | [6 empty] | 40 | 43.75 | [6 empty] | 40.32 | 112.31 | [6 empty] | 61.93 | 0 | [6 empty] | 588.89
| Allocation for schemes to be considered (D) | 3503.89 | 3815.04 |  |  |  | 163.25 |  |  |  |  | 0.02 | 0.02 | [6 empty] | 0 | 0 | [6 empty] | 0.44 | 0.44 | [6 empty] | 1.11 | 1.11 | [6 empty] | 0.16 | 0.16 | [6 empty] | 0.26 | 0.26 | [6 empty] | 0 | 0 | [6 empty] | 0.1 | 1.82 | [6 empty] | 50 | 0 | [6 empty] | 30 | 48.26 | [6 empty] | 19.68 | 0 | [6 empty] | 0 | 0 | [6 empty] | 101.77
| Allocation for capital repair & spares ( E) | [5 empty] | 210.1 |  |  |  |  | 5.8 | 5.8 | [6 empty] | 10.81 | 10.81 | [6 empty] | 13.61 | 13.61 | [6 empty] | 5.2 | 5.2 | [6 empty] | 10.1 | 10.1 | [6 empty] | 15.5 | 15.5 | [6 empty] | 10 | 10 | [6 empty] | 70.56 | 63.82 | [6 empty] | 25 | 59.23 | [6 empty] | 40 | 18.09 | [6 empty] | 40 | 20.5 | [6 empty] | 43.42 | 0 | [6 empty] | 290
| GRAND TOTAL (A+B+C+D+E) | [5 empty] | 1063 | 10.06 | 17 | 40.24 | 33.3 | 50.3 | 50.3 |  |  | 14.142 | 0 | 56.568 | 70.71 | 70.71 | 70.71 |  |  | 16.64 | 28 | 66.56 | 55.2 | 83.2 | 83.2 |  |  | 18.044 | 0 | 72.176 | 90.22 | 90.22 | 90.22 |  |  | 16.88 | 0 | 67.52 | 84.4 | 84.4 | 84.4 |  |  | 15.048 | 0 | 60.192 | 75.24 | 75.24 | 75.24 |  |  | 22.096 | 0 | 88.384 | 110.48 | 110.48 | 110.48 |  |  | 23.82 | 0 | 95.28 | 119.1 | 119.1 | 119.1 |  |  | 22.8 | 0 | 91.2 | 114.2019 | 114 | 114.2019 |  |  | 22 | 0 | 88 | 110.1 | 110 | 110.1 |  |  | 20 | 0 | 80 | 132.81 | 100 | 132.81 |  |  | 21.07 | 0 | 84.28 | 0 | 105.35 | 0 | [6 empty] | 1113
[12 empty] | Plant AMR | 25.09 | [6 empty] | Plant AMR | 25.49 | [6 empty] | Plant AMR | 28.28 | [5 empty] | Plant AMR |  | 23.25 | [5 empty] | Plant AMR |  | 30.23
NOTE:
1. Month-wise plan and actuals of Physical progress is to be given for On-going projects costing >Rs.30 Crore
2. For projects costing >Rs.150 Crore, F/N plan and actuals of physical progress may also be provided besides monthly data (may be given inside bracket)
3. Physical & Financial plan/ progress for BOO/ MDO/ COM basis on-going projects also be provided

## Month-wise plan (hidden)
STEEL AUTHORITY OF INDIA LTD.
Name of the Plant/Unit :
Rs. in Crore
SN | Name of the Scheme | Sanctioned Cost | Anticipated Cost | Actual Capex Upto 31.03.2024 | Physical Progress Upto 31.03.2024 (For >30 Cr On-going) | Physical Progress Planned for 2024-25 (For >30 Cr On-going) | 2024-25 BE | Apr'2024 | [7 empty] | May'2024 | [7 empty] | Jun'2024 | [7 empty] | Jul'2024 | [7 empty] | Aug'2024 | [7 empty] | Sep'2024 | [7 empty] | Oct'2024 | [7 empty] | Nov'2024 | [7 empty] | Dec'2024 | [7 empty] | Jan'2025 | [7 empty] | Feb'2025 | [7 empty] | Mar'2025
[8 empty] | Capex plan 1st F/N | Actual Capex 1st F/N | Capex plan 2nd F/N | Actual Capex 2nd F/N | CAPEX Plan | Actual CAPEX | Phy. Prog. Plan for the month (%) | Actual Prog. For the month (%) | Capex plan 1st F/N | Actual Capex 1st F/N | Capex plan 2nd F/N | Actual Capex 2nd F/N | CAPEX Plan | Actual CAPEX | Phy. Prog. Plan for the month (%) | Actual Prog. For the month (%) | Capex plan 1st F/N | Actual Capex 1st F/N | Capex plan 2nd F/N | Actual Capex 2nd F/N | CAPEX Plan | Actual CAPEX | Phy. Prog. Plan for the month (%) | Actual Prog. For the month (%) | Capex plan 1st F/N | Actual Capex 1st F/N | Capex plan 2nd F/N | Actual Capex 2nd F/N | CAPEX Plan | Actual CAPEX | Phy. Prog. Plan for the month (%) | Actual Prog. For the month (%) | Capex plan 1st F/N | Actual Capex 1st F/N | Capex plan 2nd F/N | Actual Capex 2nd F/N | CAPEX Plan | Actual CAPEX | Phy. Prog. Plan for the month (%) | Actual Prog. For the month (%) | Capex plan 1st F/N | Actual Capex 1st F/N | Capex plan 2nd F/N | Actual Capex 2nd F/N | CAPEX Plan | Actual CAPEX | Phy. Prog. Plan for the month (%) | Actual Prog. For the month (%) | Capex plan 1st F/N | Actual Capex 1st F/N | Capex plan 2nd F/N | Actual Capex 2nd F/N | CAPEX Plan | Actual CAPEX | Phy. Prog. Plan for the month (%) | Actual Prog. For the month (%) | Capex plan 1st F/N | Actual Capex 1st F/N | Capex plan 2nd F/N | Actual Capex 2nd F/N | CAPEX Plan | Actual CAPEX | Phy. Prog. Plan for the month (%) | Actual Prog. For the month (%) | Capex plan 1st F/N | Actual Capex 1st F/N | Capex plan 2nd F/N | Actual Capex 2nd F/N | CAPEX Plan (RE) | Actual CAPEX | Phy. Prog. Plan for the month (%) | Actual Prog. For the month (%) | Capex plan 1st F/N | Actual Capex 1st F/N | Capex plan 2nd F/N | Actual Capex 2nd F/N | CAPEX Plan | Actual CAPEX | Phy. Prog. Plan for the month (%) | Actual Prog. For the month (%) | Capex plan 1st F/N | Actual Capex 1st F/N | Capex plan 2nd F/N | Actual Capex 2nd F/N | CAPEX Plan | Actual CAPEX | Phy. Prog. Plan for the month (%) | Actual Prog. For the month (%) | Capex plan 1st F/N | Actual Capex 1st F/N | Capex plan 2nd F/N | Actual Capex 2nd F/N | CAPEX Plan | Actual CAPEX | Phy. Prog. Plan for the month (%) | Actual Prog. For the month (%) | Cum CAPEX Plan | Cum Actual CAPEX | Cum Phy. Prog. Plan for the month (%) | Cum Actual Prog. For the month (%)
A | MEP | 14240 | 14240 | 14183.73 |  |  | 7.6 |  |  |  |  | 0.8 | 0.26 | [6 empty] | 0.4 | 0 | [6 empty] | 0.6 | [7 empty] | 1.2 | [7 empty] | 0.5 | [7 empty] | 0.9 | 0 | [6 empty] | 0.4 | [7 empty] | 0.8 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0.9 | [7 empty] | 0.3 | [7 empty] | 0.55 | [7 empty] | 7.35
B | Completed AMR schemes
1 | Installation of Treatment System#1 under ZLD | 158.17 | 158.17 | 138.82 |  |  | 7.9 |  |  |  |  | 0 | 3.62 | [6 empty] | 0 | 0 | [6 empty] | 4 | 1.56 | [7 empty] | 0.44 | [7 empty] | 0.38 | [7 empty] | 0.37 | [15 empty] | 0.18 | [7 empty] | 0.17186 | [7 empty] | 0.14 | [14 empty] | 3.9 | [7 empty] | 7.9
2 | Others(NHSM) | [11 empty] | 0.47 | [15 empty] | 0.02
3
| Other schemes <Rs 30 Crore | [51 empty] | 0.27 | [7 empty] | 0.1
| Sub-total (B) | 158.17 | 158.17 | 138.82 |  |  | 7.9 |  |  |  |  | 0 | 4.09 | [6 empty] | 0 | 0 | [6 empty] | 4 | 1.58 | [6 empty] | 0 | 0.44 | [6 empty] | 0 | 0.38 | [6 empty] | 0 | 0.64 | [6 empty] | 0 | 0.1 | [6 empty] | 0 | 0.18 | [6 empty] | 0 | 0.17186 | [6 empty] | 0 | 0.14 | [6 empty] | 0 | 0 | [6 empty] | 3.9 | 0 | [6 empty] | 7.9
C | Ongoing AMR Schemes
1 | COB#2 | 433.58 | 433.58 | 53.15 | 78.83% | 19.2% | 53.15 |  |  |  |  | 5 | 5.03 | 4.16% | 2.163% |  |  |  |  | 5 | 4.32 | 4.14% | 1.31% |  |  |  |  | 5 | 19.06 | 4.4% | 1.295% |  |  |  |  | 4 | 5.99 | 3.65% | 2.096% |  |  |  |  | 4 | 3.22 | 2.85% | 1.779% |  |  |  |  | 4 | 4.56 |  | 2.004% |  |  |  |  | 2 | 11.63 |  | 2.78% |  |  |  |  | 1 | 5.66 |  | 1.033% |  |  |  |  | 0 | 0.62 |  | 0.64% |  |  |  |  | 5.5 | 0.9 |  | 0.76% |  |  |  |  | 5.5 | [7 empty] | 11 | [7 empty] | 52 | 60.99 | 0.192 | 15.86% | 94.69%
2 | Caster-IV | 1105.23 | 1105.23 | 357 | 44.16% | 54.72% | 357 |  |  |  |  | 5 | 6.49 | 4.84% | 4.881% |  |  |  |  | 25 | 25.88 | 6.33% | 1.924% |  |  |  |  | 35 | 18.01 | 5.52% | 2.737% |  |  |  |  | 30 | 44.22 | 6.24% | 3.901% |  |  |  |  | 40 | 36.65 | 6.71% | 2.748% |  |  |  |  | 40 | 25.09 | 8.64% | 2.634% |  |  |  |  | 40 | 50.2 | 3.84% | 3.68% |  |  |  |  | 40 | 16.99 | 2.01% | 3.561% |  |  |  |  | 30 | 20.8 | 5.3% | 3.99% |  |  |  |  | 30 | 28.66 | 2.13% | 0.8% |  |  |  |  | 25 |  | 2.3% | [5 empty] | 17 |  | 0.86% | [5 empty] | 357 |  |  | 30.85% | 75.02%
3 | Power enabling package for oxygen | 69.62 | 69.62 | 16 | 62.87% | 37.13% | 16 |  |  |  |  | 0.2 | 1.79 | 2.85% | 1.7% |  |  |  |  | 1.6 | 0.9 | 7.11% | 6.459% |  |  |  |  | 0.4 | 1.69 | 3.67% | 5.93% |  |  |  |  | 6.8 | 6.43 | 4.75% | 1.516% |  |  |  |  | 0.5 | 0.56 | 2.09% | 4.053% |  |  |  |  | 0.1 | 0.52 | 16.66% | 0.5494% |  |  |  |  | 0 | 1.47 |  | 0% |  |  |  |  | 0 | 0.96 |  | 0.518% |  |  |  |  | 0 | 0.15 |  | 0.13% |  |  |  |  | 1.6 | 0.95 |  | 0.02% |  |  |  |  | 0 | [7 empty] | 3.2 | [7 empty] | 14.4 |  |  | 20.87% | 83.74%
4 | STP for township | 96.62 | 96.62 | 48 | 12.55% | 87.45% | 48 |  |  |  |  | 3 | 1.73 | 3.34% | 1.22% |  |  |  |  | 3 | 3.31 | 3.62% | 2.296% |  |  |  |  | 3 | 0.53 | 2.43% | 3.24% |  |  |  |  | 5 | 3.58 | 3.88% | 1.764% |  |  |  |  | 5 | 3.1 | 6.76% | 1.654% |  |  |  |  | 5 | 2.34 | 10.19% | 1.188% |  |  |  |  | 6 | 7.67 | 14.24% | 2.23% |  |  |  |  | 6 | 3.13 | 13.85% | 1.491% |  |  |  |  | 5 | 6.15 | 11.41% | 7.57% |  |  |  |  | 2 | 5.41 | 12.16% | 18.67% |  |  |  |  | 2 |  | 5.57% | [5 empty] | 2 |  | 0% | [5 empty] | 47 |  |  | 41.32% | 53.87%
5 | Oxygen Plant on COM Basis | 0 | 0 |  |  |  | 0 | [103 empty] | 0% | 0%
Others
| Other schemes <Rs 30 Crore | [5 empty] | 200 |  |  |  |  | 12 | [7 empty] | 15 | [7 empty] | 15 | [7 empty] | 17 | [7 empty] | 15 | [7 empty] | 15 | 26.33 | [6 empty] | 17 | 29.41 | [6 empty] | 15 | 26.54 | [6 empty] | 4 | 27.08 | [6 empty] | 20 | 7.69 | [6 empty] | 22 | [7 empty] | 22 | [7 empty] | 189
| Sub-total (C) | 1705.05 | 1705.05 | 474.15 |  |  | 674.15 |  |  |  |  | 25.2 | 15.04 | [6 empty] | 49.6 | 34.41 | [6 empty] | 58.4 | 39.29 | [6 empty] | 62.8 | 60.22 | [6 empty] | 64.5 | 43.53 | [6 empty] | 64.1 | 58.84 | [6 empty] | 65 | 100.38 | [6 empty] | 62 | 53.28 | [6 empty] | 39 | 54.8 | [6 empty] | 59.1 | 43.61 | [6 empty] | 54.5 | 0 | [6 empty] | 55.2 | 0 | [6 empty] | 659.4
C1 | Completed Schemes from 'C'
Details along with names to be given for >30 Cr schemes (For <30 cr, to be given in table below)
| Total Sanctioned schemes (A+B+C) | 16103.22 | 16103.22 | 14796.7 |  |  | 689.65 |  |  |  |  | 26 | 19.39 | [6 empty] | 50 | 34.41 | [6 empty] | 63 | 40.87 | [6 empty] | 64 | 60.66 | [6 empty] | 65 | 43.91 | [6 empty] | 65 | 59.48 | [6 empty] | 65.4 | 100.48 | [6 empty] | 62.8 | 53.46 | [6 empty] | 39 | 54.9719 | [6 empty] | 60 | 43.75 | [6 empty] | 54.8 | 0 | [6 empty] | 59.65 | 0 | [6 empty] | 674.65
D | Provision for Schemes to be considered
D1 | Approved In-principle
1 | 4th Stove BF#5 | 76.59 | 76.59 | 0.66 |  |  | 9 | [21 empty] | 0.18 | [23 empty] | 0.08 | [14 empty] | 4 | 0.01 | [22 empty] | 4 | [7 empty] | 1 | [7 empty] | 9
2 | COB#7 | 2882.53 | 2882.53 | 12.14 |  |  | 136.25 | [21 empty] | 0.12 | [15 empty] | 0.16 | [7 empty] | 0.12 | [6 empty] | 24.6 | [7 empty] | 37.2 | 0.64 | [6 empty] | 50 | [7 empty] | 2 | 48.26 | [6 empty] | 2 | [7 empty] | 13.45 | [7 empty] | 129.25
3 | Pellet Plant on COM Basis | 0 | 0 |  |  |  | 0
4 | Micro-Pellet Plant on COM Basis | 0 | 0 |  |  |  | 0
5 | Treatment System#2 | 177.22 | 177.22 |  |  |  | 0
6 | Coal Transportation | 367.55 | 367.55 |  |  |  | 0
Other schemes <Rs 30 Crore
| Sub-total (D1) | 3503.89 | 3503.89 |  |  |  | 145.25 |  |  |  |  | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0.3 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0.16 | [6 empty] | 0 | 0.2 | [6 empty] | 24.6 | 0 | [6 empty] | 41.2 | 0.65 | [6 empty] | 50 | 0 | [6 empty] | 2 | 48.26 | [6 empty] | 6 | 0 | [6 empty] | 14.45 | 0 | [6 empty] | 138.25
D1-I | Ordered schemes from 'D1'
Details along with names to be given for >30 Cr schemes (For <30 cr, to be given in table below)
D2 | Proposals under consideration
1 | New Product Testing Laboratory | 186.6 | 186.6 | 0.89 |  |  | 18 | [21 empty] | 0.02 | [23 empty] | 0.01 | [15 empty] | 0.23 | [22 empty] | 8.2 | [7 empty] | 9.8 | [7 empty] | 18
2 | Mixed Gas Booster | 124.55 | 124.55 | 0.76 |  |  | 0 | [21 empty] | 0.04
| Others(SMS#3) | [5 empty] | 0 | [5 empty] | 0.02 | [15 empty] | 0.08 | [7 empty] | 1.11 | [15 empty] | 0.05 | [15 empty] | 0.94 | [38 empty] | 0
Other schemes <Rs 30 Crore
| Sub-total (D2) |  | 311.15 |  |  |  | 18 |  |  |  |  | 0 | 0.02 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0.14 | [6 empty] | 0 | 1.11 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0.06 | [6 empty] | 0 | 0 | [6 empty] | 0 | 1.17 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 8.2 | 0 | [6 empty] | 9.8 | 0 | [6 empty] | 18
D2-I | Ordered schemes from 'D2'
Details along with names to be given for >30 Cr schemes (For <30 cr, to be given in table below)
Allocation for approval of FY 2023-24
Plant Level Schemes FY 2024-25
| Total Provision for Schemes to be considered (D=D1+D2) | 3503.89 | 3815.04 |  |  |  | 163.25 |  |  |  |  | 0 | 0.02 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0.44 | [6 empty] | 0 | 1.11 | [6 empty] | 0 | 0.16 | [6 empty] | 0 | 0.26 | [6 empty] | 24.6 | 0 | [6 empty] | 41.2 | 1.82 | [6 empty] | 50 | 0 | [6 empty] | 2 | 48.26 | [6 empty] | 14.2 | 0 | [6 empty] | 24.25 | 0 | [6 empty] | 156.25
E | Capital Repairs/Spares
1 | Capital Spares (As per IndAs) | [5 empty] | 210.1 |  |  |  |  | 15 | 5.8 | [6 empty] | 20 | 10.81 | [6 empty] | 20 | 13.61 | [6 empty] | 15 | 5.2 | [6 empty] | 15 | 10.1 | [6 empty] | 15 | 15.5 | [6 empty] | 20 | 10 | [6 empty] | 15 | 63.82 | [6 empty] | 25 | 59.23 | [6 empty] | 20 | 18.09 | [6 empty] | 20 | [7 empty] | 20.1 | [7 empty] | 220.1
2 | Capital Repairs (As per IndAs)
| Sub-total (E) | [5 empty] | 210.1 |  |  |  |  | 15 | 5.8 | [6 empty] | 20 | 10.81 | [6 empty] | 20 | 13.61 | [6 empty] | 15 | 5.2 | [6 empty] | 15 | 10.1 | [6 empty] | 15 | 15.5 | [6 empty] | 20 | 10 | [6 empty] | 15 | 63.82 | [6 empty] | 25 | 59.23 | [6 empty] | 20 | 18.09 | [6 empty] | 20 | 0 | [6 empty] | 20.1 | 0 | [6 empty] | 220.1
Summary:
| Allocation for Sanctioned schemes (A+B+C) | 16103.22 | 16103.22 | 14796.7 |  |  | 689.65 |  |  |  |  | 26 | 19.39 | [6 empty] | 50 | 34.41 | [6 empty] | 63 | 40.87 | [6 empty] | 64 | 60.66 | [6 empty] | 65 | 43.91 | [6 empty] | 65 | 59.48 | [6 empty] | 65.4 | 100.48 | [6 empty] | 62.8 | 53.46 | [6 empty] | 39 | 54.9719 | [6 empty] | 60 | 43.75 | [6 empty] | 54.8 | 0 | [6 empty] | 59.65 | 0 | [6 empty] | 674.65
| Allocation for schemes to be considered (D) | 3503.89 | 3815.04 |  |  |  | 163.25 |  |  |  |  | 0 | 0.02 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0.44 | [6 empty] | 0 | 1.11 | [6 empty] | 0 | 0.16 | [6 empty] | 0 | 0.26 | [6 empty] | 24.6 | 0 | [6 empty] | 41.2 | 1.82 | [6 empty] | 50 | 0 | [6 empty] | 2 | 48.26 | [6 empty] | 14.2 | 0 | [6 empty] | 24.25 | 0 | [6 empty] | 156.25
| Allocation for capital repair & spares ( E) | [5 empty] | 210.1 |  |  |  |  | 15 | 5.8 | [6 empty] | 20 | 10.81 | [6 empty] | 20 | 13.61 | [6 empty] | 15 | 5.2 | [6 empty] | 15 | 10.1 | [6 empty] | 15 | 15.5 | [6 empty] | 20 | 10 | [6 empty] | 15 | 63.82 | [6 empty] | 25 | 59.23 | [6 empty] | 20 | 18.09 | [6 empty] | 20 | 0 | [6 empty] | 20.1 | 0 | [6 empty] | 220.1
| GRAND TOTAL (A+B+C+D+E) | [5 empty] | 1063 | 8.2 | 17 | 40.24 | 33.3 | 41 | 50.3 |  |  | 14 | 0 | 56 | 70.71 | 70 | 70.71 |  |  | 16.6 | 28 | 66.4 | 55.2 | 83 | 83.2 |  |  | 15.8 | 0 | 63.2 | 90.22 | 79 | 90.22 |  |  | 16 | 0 | 64 | 84.4 | 80 | 84.4 |  |  | 16 | 0 | 64 | 75.24 | 80 | 75.24 |  |  | 22 | 0 | 88 | 110.48 | 110 | 110.48 |  |  | 23.8 | 0 | 95.2 | 119.1 | 119 | 119.1 |  |  | 22.8 | 0 | 91.2 | 114.2019 | 114 | 114.2019 |  |  | 16.4 | 0 | 65.6 | 110.1 | 82 | 110.1 |  |  | 17.8 | 0 | 71.2 | 0 | 89 | 0 |  |  | 20.8 | 0 | 83.2 | 0 | 104 | 0 | [6 empty] | 1051
[12 empty] | Plant AMR | 25.09 | [6 empty] | Plant AMR | 25.49 | [6 empty] | Plant AMR | 28.28 | [5 empty] | Plant AMR |  | 23.25 | [5 empty] | Plant AMR |  | 30.23
NOTE:
1. Month-wise plan and actuals of Physical progress is to be given for On-going projects costing >Rs.30 Crore
2. For projects costing >Rs.150 Crore, F/N plan and actuals of physical progress may also be provided besides monthly data (may be given inside bracket)
3. Physical & Financial plan/ progress for BOO/ MDO/ COM basis on-going projects also be provided

## MEP (hidden)
Appendix-3 (contd)
STEEL AUTHORITY OF INDIA LTD.
CAPEX STATUS OF PROJECTS -SANCTIONED PROJECTS (MEP)
Rs in crore
SN | Name of the Plant/Unit | Sanctioned | Anticipated | Actuals | Actuals | 2016-17 |  | Balance as on 01.04.2018 | Expenditure Apr-Oct'18 | 2018-19 | 2019-20 | 2019-20 | 2020-21 | 2021-22 | Total Estimate | Balance amount
|  | Cost | Cost | upto | upto | RE | Actual |  |  | RE | BE | Estimate | Estimate | Estimate | 2017-22 | required for completion
|  |  |  | 31.03.18 | 31.12.16 |  | 31.03.17 | [8 empty] | of project after 19-20
1 | Bhilai Steel Plant
1.1 | MEP | #REF! | #REF! | #REF! | 18646.0876 | 1336.1 | 1830.0853 | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF!
2 | Durgapur Steel Plant
2.1 | MEP | #REF! | #REF! | #REF! | 103.44 | 30 | 79.17 | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF!
3 | Rourkela Steel Plant
3.1 | MEP | #REF! | #REF! | #REF! | 1566.74 | 458.5 | 673.94 | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF!
4 | Bokaro Steel Plant
4.1 | MEP | #REF! | #REF! | #REF! | 1027.72 | 299.77 | 522.42 | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF!
5 | ISP
5.1 | MEP | #REF! | #REF! | #REF! | 6.19 | 10 | 19.24 | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF!
6 | Salem Steel Plant
6.1 | MEP | #REF! | #REF! | #REF! | 5.92 | 6 | 7.14 | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF!
| Total Expansion | #REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
#N/A

## expansion excell (hidden)
BSP EXP
#REF! | Anticipated Cost | Actuals on | 2020-21 |  | 2021-22 | EXP as on | Check
|  | 2020-03-31 | BE | RE | BE | DEC'2020
Coke Oven Battery # 11 Complex | 1267.21 | 1170.27 | 46.6 | 64.08 | 32.65 | 6.11 | 0.21
Blast Furnace Complex | 4301.45 | 3960.12 | 90.84 | 196.2 | 121.57 | 69.21 | #N/A
SMS # 3 Complex | 5351.8 | 4871 | 203.73 | 268.37 | 212.43 | 104.17 | #N/A
Bar & Rod Mill Complex | 944.8 | 842.49 | 27.06 | 50.46 | 35.62 | 4.44 | #N/A
Universal Rail Mill Complex | 2834.58 | 2627.78 | 81.25 | 115.72 | 91.08 | 30.75 | #N/A
Augmentation of Plate Mill/SMS2 | [6 empty] | #N/A
and common packages | 7198.08 | 6764.1033 | 240.5239 | 215.2319 | 218.7456 | 146.94 | #N/A
Total | 21897.92 | 20235.7633 | 690.0039 | 910.0619 | 712.0956 | 361.62 | #N/A
DSP EXP
#REF! | 1380.28 | 1314.5828 | 44.1394 | 5.7 | 60 | 0.1 | #N/A
New Bloom Cum Round Caster | 561.76 | 505.66 | 2.3217 | 6.1 | 50 | 0.17 | #N/A
Augmentation of SMS | 265.47 | 228.0412 | 5.2305 | 7.43 | 30 | 0 | #N/A
Raw Material Handling | 254.81 | 251.4 | 1.2898 | 1.7072 | 1.7072 | 0.39 | #N/A
Rebuilding of COB-2 including Coke Sorting Plant | 219.81 | 216.51 | 0 | 1.3 | 2 | 0 | #N/A
Power,Ammonium Sulphate Plant and other infrastucture facility | 683.99 | 637.916 | 7.0185 | 6.7628 | 39.3028 | 1.37 | #N/A
Total | 3366.12 | 3154.11 | 60 | 29 | 183.01 | 2.03 | #N/A |  |  |  |  | -2.79
RSP EXP
Raw Material Handling Complex | 759.15 | 686.68 | 18 | 40 | 32.47 | 30.15 | 0
COB 6 Complex | 1262.36 | 1188.47 | 27.17 | 53.87 | 20.02 | 17.77 | -4.6185e-14
#REF! | 801.35 | 794.78 | 0 | 3.33 | 3.24 | 0 | 4.9738e-14
Blast Furnace # 5 Complex | 2815.62 | 2521.43 | 97.55 | 107.98 | 186.21 | 25.38 | 0
SMS II Complex | 1410.74 | 1308.52 | 73.91 | 56.88 | 45.34 | 26.1 | 2.0606e-13
New Plate Mill complex | 2566.17 | 2387.76 | 49.12 | 85.99 | 67.79 | 29.36 | 24.63
Other Infrastructure facility | 4624.61 | 4178.11 | 174.25 | 99.53 | 74.34 | 70.56 | 272.63
Total | 14240 | 13065.75 | 440 | 447.58 | 429.41 | 199.32 | 297.26
BSL EXP
Cold Rolling Mill | 3419.79 | 3072.24 | 0 | 11.902 | 297.0441 | 11.9 | 38.6039
Modn. of SMS-II | 827.0313 | 645.32 | 0 | 3.73 | 136.28 | 3.73 | 41.7013
Power Transmission & Distribution | 211.912 | 198.88 | 0 | 0 | 4.6 |  | 8.432
BF and CHSGP in BF 1,2, & 3 | 383.122 | 330.61 | 0 | 7.72 | 23.57 | 6.15 | 21.222
Modification of HSM | 884.6418 | 841.16 | 0 | 5.83 | 0 | 5.83 | 37.6518
Enabling Works Packages,CRM-1,Raw Material Handling,etc | 2211.5029 | 1936.45 | 0 | 234.158 | 40.8959 | 133.08 | -0.001
Total | 7938 | 7024.66 | 0 | 263.34 | 502.39 | 160.69 | 147.61
ISP EXP
COB complex | 1218.2 | 1145.36 | 5 | 5.58 | 10 | 0.0184 | 57.26
Sinter Plant | 864.07 | 856.51 |  |  |  |  | 7.56
Blast Furnace Complex | 3093.28 | 2915.31 | 8 | 8.74 | 110 | 7.5152 | 59.23
SMS complex | 3389.84 | 2962.97 | 68 | 74.24 | 13 | 2.212 | 339.63
Universal Section Mill | 1117.74 | 1026.1 | 0.04 | 0.05 | 50 | 0.0479 | 41.59
Wire Rod & Bar Mill | 898.62 | 838.51 | 1.8 | 2 | 40 | 1.6712 | 18.11
Civil Structural Mills | 678.4 | 566.99 |  |  |  |  | 111.41
Raw material Handling | 1974.99 | 1821.85 |  |  |  |  | 153.14
Auxillary and other Pakages | 7566.44 | 6856.44 | 107.16 | 116.46 | 237 | 17.4693 | 356.54
Total | 20801.58 | 18990.04 | 190 | 207.07 | 460 | 28.934 | 1144.47
Expenditure till Mar'20
| Capital Repair & Spares | MEP+AMR | MEP | AMR |  | Sanctioned AMR+MEP | Sanctioned MEP | Sanctioned AMR | Expenditure AMR+MEP | Expenditure MEP | Expenditure AMR
Capital Repair & Spares | Expenditure 20-21 | [9 empty] | 0
BSP | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #N/A | #REF! | #REF! | #N/A
DSP | #REF! | #REF! | #REF! | #N/A |  | #REF! | #REF! | #N/A | #REF! | #REF! | #N/A
RSP | #REF! | #REF! | #REF! | #N/A |  | #REF! | #REF! | #N/A | #REF! | #REF! | #N/A
BSL | #REF! | #REF! | #REF! | #N/A |  | #REF! | #REF! | #N/A | #REF! | #REF! | #N/A
ISP | #REF! | #REF! | #REF! | #N/A |  | #REF! | #REF! | #N/A | #REF! | #REF! | #N/A
RMD | #REF! | #REF! | 0 | #N/A |  | #REF! |  | #N/A | #REF! |  | #N/A
ASP | #REF! | #REF! | 0 | #N/A |  | #REF! |  | #N/A | #REF! |  | #N/A
SSP | #REF! | #REF! | #REF! | #N/A |  | #REF! | #REF! | #N/A | #REF! | #REF! | #N/A
VISP | #REF! | #REF! | 0 | #N/A |  | #REF! |  | #N/A | #REF! |  | #N/A
CFP | #REF! | #REF! | 0 | #N/A |  | #REF! |  | #N/A | #REF! |  | #N/A
CU | #REF! | #REF! | 0 | #N/A |  |  |  | #N/A |  |  | #N/A
Total | #REF! | #N/A | #N/A | #N/A |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## Sheet2 (hidden)
STEEL AUTHORITY OF INDIA LTD.
Name of the Plant/Unit: BHILAI STEEL PLANT | [7 empty] | 100 | [6 empty] | Annexure-I (A)
Rs. in Crore
SN | Name of the Scheme |  | Sanctioned | Anticipated | Actual | Actual | 2021-22 |  | 2022-23 | 2023-24 | 2024-25 | 2025-26 | Completion Schedule |  |  | 2016-17 |  |  |  |  | beyond | RECHECK
|  |  | Cost | Cost | upto | Apr-Oct'21 | BE | RE | BE | Estimate | Estimate | Estimate | Original | As per | Now | Balance amount required for completion of project | Beyond |  | CHECK | CHECK | 2017-18
[5 empty] | 31.03.2021 | [7 empty] | Approved | last Plan | Antcptd. |  | 2016-17 | Spill over | EXP 08 | ANT COST
A | Completed schemes (sanctioned prior to Jan'2021) | [16 empty] | #REF! | 0
1 | Technical Upgradation of BF-7 | 2004-004 | 170.41 | 160.76 | 160.76 | 0 | 0 | 0 | 0 | [7 empty] | #REF! | #REF! | 0 | #REF! | 0 | 0
2 | Rebuilding of COB # 5 | 2004-038 | 201.97 | 202.513 | 202.513 | 0 | 0 | 0 | 0 | [7 empty] | #REF! | #REF! | 0 | #REF! | 0 | 0
3 | Installation of HAGC and PVR in Plate Mill | 2004-043 | 46.7 | 45.7 | 45.7 | 0 | 0 | 0 | 0
4 | New Slab Caster RH & LF in SMS-2 | 2005-021 | 477.04 | 457.9657 | 457.9657 | 0 | 0 | 0 | 0
5 | Installation of Hot Metal De-sulphurisation unit | 2005056 | 83.9 | 68.766 | 68.766 | 0 | 0 | 0 | 0
6 | Power Supply facilities for Oxygen Plant | 2007003 | 56.4489 | 55.8452 | 55.8452 | 0 | 0 | 0 | 0
7 | Installation of MSDS - 5 | 2007015 | 125.94 | 132.1796 | 132.1796 | 0 | 0 | 0 | 0
8 | Rebuilding of Coke Oven Battery # 6 | 2007112 | 172.78 | 155.5517 | 155.5517 | 0 | 0 | 0 | 0
9 | Thyristorisation of Plate Mill | 2007016 | 48.31 | 41.5563 | 41.5563 | 0 | 0 | 0 | 0
10 | Implementation of ERP | 2007056 | 49.2105 | 48.0289 | 48.0289 | 0 | 0 | 0 | 0
11 | End forging plant for Thick web Rail at R&SM. | 2007111 | 45.54 | 44.9609 | 44.9609 | 0 | 0 | 0 | 0
12 | Electro-Magnetic Stirrer in Bloom Caster | 2007082 | 20.87 | 19.8645 | 19.8645 | 0 | 0 | 0 | 0
13 | 30 MLD Sewage Treatment Plant for Township | 2008019 | 41.34 | 34.1725 | 34.1725 | 0 | 0 | 0 | 0
14 | Installation of 700 TPD ASU-4 at OP-2 | 2007032 | 212.44 | 218.8735 | 218.8735 | 0 | 0 | 0 | 0
15 | Installation on-line Eddy Cuurent Testing M/c and Optico Visual Inspection System (OVIS) at Short Rail area of RSM | 20090011 | 20.26 | 18.1297 | 18.1297 | 0 | 0 | 0 | 0
16 | Implementation of MES | 2006021 | 28.97 | 22.3171 | 22.3171 | 0 | 0 | 0 | 0
17 | Modification of Mid-Stack Cooling System | 2012-0042 | 40.0704 | 42.55 | 42.5511 | 0 | 0 | 0 | 0
18 | Coal Grinding facilities for CDI of BF 6 & 7. | 20070173 | 39.4 | 38.87 | 38.8789 | 0 | 0 | 0 | 0
19 | Cold repair COB-9 | 2011-0059 | 332.65 | 332.65 | 311.7043 | 20.21 | 17.97 | 20.21 | 0
20 | Installation of Evacuation facilities for oxygen from 2*1250 TPD oxygen plant | 2005-0051 | 29.26 | 30.62 | 29.0402 | 1.5534 | 0 | 1.58 | 0
21 | Replacement of sinter cooler of SP-III | 2014-0010 | 31.41 | 31.51 | 31.5106 | 1.1702 | 0 | 1.17 | 0
22 | Other schemes <Rs 30 Crore |  | 350 | 350 | 349.8244 | 0.50707 | 29.2 | 0.51 | 0
| Sub-total (A) |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | [6 empty] | 0 | #REF! | #REF! | 0 |  | -0.7795 | 0
B | Ongoing Schemes (sanctioned prior to Jan'2021) | [16 empty] | #REF! | 0
[6 empty] | 0 | [9 empty] | 70.4 | #REF! | #REF! | 0 | #REF! | 0 | 0
1 | Upgradation of Stoves -BF-4 | 2011-0053 | 70.65 | 70.65 | 52.7144 | 1.69 | 10.83 | 4.05 | 0.3 | [6 empty] | #REF! | #REF! | #REF! | 0 | #REF! | 13.5856 | 0
2 | CDI FOR BF#4 | 2015-0014 | 19.9 | 19.9 | 6.1727 | 0 | 0 | 1.32 | 0.44 | [6 empty] | #REF! | #REF! | #REF! | 0 | #REF! | 11.9673 | 0
3 | Static facility for Env. Sound Mgt of PCB. | 2015-0011 | 136.37 | 136.37 | 28.3126 | 1.67 | 5.1 | 4.64 | 2.86
4 | Rebuilding of Coke Oven Battery No.7 & 8 - Design & engineering drawings, providing expert’s supervision, etc | 2015-0012/00-01 | 588.15 | 38.01 | 10 | 5.08 | 0 | 9 | 4
5 | Rebuilding of Coke Oven Battery No.7 & 8 - Enabling works of COB No.7 | 2015-0012/00-02 | 0 | 9.49 | 6 | 0 | 0 | 0 | 0
6 | Rebuilding of Coke Oven Battery No.7 & 8 - Battery Proper | 2015-0012/00-03 | 0 | 298.2 | 15.6 | 21 | 182 | 117.8 | 127
7 | Rebuilding of Coke Oven Battery No.7 & 8 - Oven Machines | 2015-0012/00-04 | 0 | 85.84 | 0 | 8.71 | 0 | 26.5 | 40
8 | Rebuilding of Coke Oven Battery No.7 & 8 - By-Product Plant | 2015-0012/00-05 | 0 | 40.89 | 0 | 4.1014 | 0 | 26.5 | 14
9 | Rebuilding of Coke Oven Battery No.7 & 8 - others |  | 0 | 116 | 0 | 0 | 0 |  | 15
10 | Cast House defuming System in BF-7 | 2013-0096 | 21.68 | 21.68 | 17.7154 | 0.11087 | 3.14 | 3.33 | 0.46
11 | Upgradation of Waste Gas ESPs of SP - III | 2014-0120 | 5.542 | 5.542 | 4.5156 | 0.18248 | 0 | 0.26 | 0.39
12 | Automation of GCPs of BF#1to6 | 2014-0110 | 3.28 | 0 | 0.56651 | 0 | 0 | 0 | 0
13 | Repalcement of Static Excitation system of exhauster 3,4 of SP II | 2014-0073 | 0.55 | 0 | 0.54017 | 0 | 0 | 0 | 0
14 | 180 Bedded CISF Barracks at Rajhara Mines | 2011-0110 | 10.7878 | 10.7878 | 5.8502 | 0.87192 | 0 | 1 | 0
15 | Installation of ESP type gas cleaning system as replacement of multicyclones for all the four sintering machines at SP-2 | 2014-0032 | 46.58 | 46.58 | 25.4152 | 5.5009 | 16 | 16.08 | 2.91
16 | Setting up of Secured Landfill Facility | 2015-0036 | 10.57 | 10.57 | 2.5751 | 4.55 | 0 | 6.99 | 1.31
17 | Treatment and Recycling of waste water of outlet-C | 2016-0027 | 42.2 | 42 | 38.8246 | 2.6289 | 12 | 4.74 | 0.87
18 | Installation of ESP in Sinter Dispatch Route of Sinter Plant-II, Pkg-II, Bhilai Steel Plant | 2015-0018 | 14.21 | 14.21 | 2.5246 | 2.61 | 0 | 4 | 2.8
19 | Purchase of Railway Rolling Stock (freight rakes) by SAIL under GPWIS (Stage-II) | 2020-0019 | 68 | 68 | 0 | 1.5516 | 35 | 32 | 0
20 | ROWGHAT MINES | 2009999 | 2200 | 2200 | 1500.5128 | 78.34 | 170 | 174.69 | 200
21 | ROWGHAT BARRACK | ROWG-CAMP |  |  | 158.576 | 1.71 | 0 | 2 | 0
22 | ROWGHAT CONSULTANCY | ROWG-CON |  |  | 9.36 | 0 | 0 | 0 | 0
23 | NPV PAYMENT-KALWARNAGOUR |  |  |  | 96 | 0 | 0 | 0 | 0
24 | Other schemes <Rs 30 Crore |  | 474 | 474 | 437.13 | 14.13 | 43 | 40 | 0
| MEP |  | 19857.3387 | 23347.9469 | 20866.987 | 544.9527 | 712.0956 | 956.996 | 219.345
| Sub-total (B) |  | 23569.8085 | 27056.6667 | 23285.8929 | 699.3906 | 1189.1656 | 1431.896 | 631.685 | [6 empty] | #REF! | #REF! | #REF! | 0
| Total Sanctioned schemes (A+B) |  | 26194.7284 | 29610.0513 | 25816.587 | 722.8314 | 1236.3356 | 1455.366 | 631.685 | [6 empty] | #REF! | #REF! | #REF! | 0
C | Capital Repairs/Spares | [16 empty] | #REF!
1 | Capital Spares (As per IndAs) |  |  | 822 | 384.26 | 187.27 | 76 | 190 | 260.23
2 | Capital Repairs (As per IndAs) |  |  | 306 | 209.92 | 26 | 48 | 35 | 47.34
| Sub-total (C) |  | 0 | 1128 | 594.18 | 213.27 | 124 | 225 | 307.57
D | Provision for Schemes to be considered | [16 empty] | #REF! | 0
D1 | Completed Schemes (sanctioned subsequent to Dec'2020 i.e.month of processing of AP 2021-22)
1 | Installation of Hydraulic mud gun & drill machine in BF-4 | 2019-0035 | 19.9 | 21.9 | 16.8 | 5.1 | 8 | 5.1 | 0
2 | Installation of Automatic Mould level control system in Combi caster 3 & 4 of SMS-2 | 2018-0042 | 13.53 | 13.53 | 10.53 | 0 | 3 | 3 | 0
3 | Other schemes <Rs 30 Crore
| Sub-total (D1) |  | 33.43 | 35.43 | 27.33 | 5.1 | 11 | 8.1 | 0
D2 | Ongoing Schemes (sanctioned subsequent to Dec'2020 i.e.month of processing of AP 2021-22)
1 | Replacement of Existing Flash Butt Rail Welding Machine in RSM | 2020-0006 | 16.01 | 16.01 | 0 | 1.41 | 15 | 15 | 1.01
2 | Modification in the Washing Circuit of Crushing, Screening and Washing (CSW) Plant of Dalli Mines | 2019-0039 | 148.16 | 148.16 | 0 | 6.53 | 75.51 | 75.5 | 65
3 | Other schemes <Rs 30 Crore |  | 71.5868 | 71.5868 | 0.07 | 7.94 | 0 | 29.44 | 0
| Sub-total (D2) |  | 235.7568 | 235.7568 | 0.07 | 15.88 | 90.51 | 119.94 | 66.01
D3 | Approved In-principle
1 | Installation of Refinishing Complex in URM |  | 30 | 30 | 0 | 0 | 12 | 5 | 21.29
2 | Replacement of Converter Vessels, Trunion Rings, Support system and Installation of Secondary Emission Control system for Three Converters in SMS-II |  | 268 | 268 | 0 | 0 | 95 | 7 | 73.72
3 | Other schemes <Rs 30 Crore |  |  |  | 0 | 0 | 0 | 0 | 0
| Sub-total (D3) |  | 298 | 298 | 0 | 0 | 107 | 12 | 95.01
D4 | Proposals under consideration
1 | Replacement of Stacker cum reclaimer # 1 & 2 of CPP2 of COCCD |  |  | 35.97 | 0 | 0 | 3 | 0 | 0
2 | Up gradation of Blast Furnace -6-submitted for Stage-I |  |  | 1315.82 | 0 | 0 | 196.14 | 0 | 0
3 | Replacement of Exhauster 7 of Gas Condesation plant 2 of COCCD |  |  | 24.08 | 0 | 0 | 8 | 0 | 0
4 | Inst of 140 tph Walking Beam Furnance in Plate Mill. |  |  | 137.27 | 0 | 0 | 10 | 0 | 0
5 | Procurement of 3 No 140T Rail Crane |  |  | 87 | 0 | 0 | 7 | 0 | 0
6 | Complete trck renewal at Nandini Mines |  |  | 60 | 0 | 0 | 6.93 | 0 | 0
7 | Installation of Coal grinding & Injection plant of BF-7 |  |  | 82.34 | 0 | 0 | 4 | 0 | 0
8 | Replacement of Stand # 4, 6, 7, 8 & 11 with Housing less stand in Merchant Mill |  |  | 51.13 | 0 | 0 | 6.93 | 0 | 0
9 | Replacement of Cold Shears in Merchant Mill |  |  | 31.36 | 0 | 0 | 6.64 | 0 | 0
10 | Super Accelerated Cooling system(Uniform Cooling) for High strenth Plates |  |  | 98.3 | 0 | 0 | 7.97 | 0 | 0
11 | Elimination of > 63 mm thicker plate back end sagging (bend) |  |  | 89.77 | 0 | 0 | 2.57 | 0 | 0
12 | Revamping of grinding m/c in Roll grinding shop |  |  | 33.2 | 0 | 0 | 1.11 | 0 | 0
13 | Descaling of Special steel slab by enhancing pressure to 250 Kg/cm |  |  | 31.85 | 0 | 0 | 1 | 0 | 0
14 | Other schemes <Rs 30 Crore |  |  | 1468.1966 | 0 | 0 | 35 | 44.59 | 488.7509
| Sub-total (D4) |  | 0 | 3546.2866 | 0 | 0 | 296.29 | 44.59 | 488.7509 | 0
| Allocation for approval of FY 2021-22 Rs230 Crore | [16 empty] | #REF! | 0
| Plant Level Schemes FY 2022-23 Rs314.00Crore | [16 empty] | #REF! | 0
| Sub-total (D=D1+D2+D3+D4) |  | 567.1868 | 4115.4734 | 27.4 | 20.98 | 504.8 | 184.63 | 649.7709 | 0 | [5 empty] | 190 | #REF! | #REF! | 0
| Summary: | [16 empty] | #REF! | 0
| Allocation for Sanctioned schemes (A+B) | [14 empty] | #REF! | #REF! | #REF! | 0 | #REF!
Allocation for capital repair & spares (C)
| Allocation for schemes to be considered (D) | [14 empty] | 190 | #REF! | #REF! | 0 | #REF!
| GRAND TOTAL (A+B+C+D) |  | 26761.9152 | 34853.5247 | 26438.167 | 957.0814 | 1865.1356 | 1864.996 | 1589.0259 | 0 | [5 empty] | #REF! | #REF! | #REF! | 0
Note :
1 | Allocation for approval of Plant Level Schemes for 2021-22 is inclusive of schemes already sanctioned upto .......'21 |  |  |  |  | -0.0013943
2 | Sanctioned cost / Anticipated cost is without considering CENVAT/ ITC benefits
3 | Anticipated cost worked out on FE rate as on 30.07.21 (1 USD=Rs.75; 1 GBP=Rs.105; 1 EUR=Rs.90; JPY (100 units)=Rs.69)
4 | All figures are on gross basis
............. STEEL PLANT - EXPANSION | [7 empty] | Annexure - I (A) Contd.
Rs Crores
S.No | Name of the Scheme |  | Sanctioned | Anticipated | Actual | Actual | 2021-22 |  | 2022-23 | 2023-24 | 2024-25 | 2025-26 | Completion Schedule |  |  | 2016-17
|  |  | Cost | Cost | upto | Apr-Sep'21 | BE | RE | BE | Estimate | Estimate | Estimate | Original | As per | Now | BE | Beyond
[5 empty] | 31.03.2021 | [7 empty] | Approved | last Plan | Antcptd. | ESTIMATE | 2016-17 | Spill over
A | FIRMED-UP PACKAGES
Coke Oven Battery # 11 Complex
1 | New Coal Handling Plant for COB # 11(062) | 2007-0001/062 | 470.5 | 514.91 | 433.6687 | 59.1045 | 19.85 | 69.1 | 11.16
2 | Coke Oven Battery # 11 Proper | 2007-0001/001-001 | 419.315 | 460.555 | 443.4168 | 16.5045 | 0 | 16.5 | 0
3 | Coke Oven Battery # 11 Equipments | 2007-0001/001-002 | 109.9 | 122.39 | 116.3508 | 6.0006 | 0 | 6.031 | 0
4 | 14410 T Silica Bricks & 1700 T Silica Mortar | 2007-0001/001-003 | 46.9 | 51.0326 | 47.2833 | 0 | 0 | 0 | 0
5 | Fireclay Bricks -Slab Pavement, Bus Flue & Regenerator | 2007-0001/001-004-001-01 | 1.3 | 1.45 | 1.4067 | 0 | 0 | 0 | 0
6 | Fireclay Bricks - Insulating Walls at Butress, Doors & Standpipe | 2007-0001/001-004-001-02 | 0.6 | 0.7 | 0.69085 | 0 | 0 | 0 | 0
7 | Checker Bricks | 2007-0001/001-004-002 | 2 | 2.5 | 2.2178 | 0 | 0 | 0 | 0
8 | Fire Clay Bricks for flue & oven roofing | 2007-0001/001-004-003 | 2.1 | 2.3821 | 2.3279 | 0 | 0 | 0 | 0
9 | Fire Clay Bricks for new cob 11 | 2007-0001/001-004-004 | 0.1 | 0.10105 | 0 | 0 | 0 | 0 | 0
10 | Mica Insulation Bricks & Mortar | 2007-0001/001-005 | 0.7 | 0.7 | 0.68695 | 0 | 0 | 0 | 0
11 | Coke Dry Cooling Plant | 2007-0001/002 | 369.1 | 406.12 | 382.9087 | 14.0384 | 0 | 14.04 | 0
12 | Bye Product Plant with associated facility(003A) | 2007-0001/003-001 | 364.1 | 394.21 | 339.4711 | 0 | 8.62 | 25.83 | 8.64
13 | Phenolic Effluent Treatment Plant(003c) | 2007-0001/003-003 | 20.5148 | 21.4561 | 20.4378 | 0 | 0 | 0 | 0
14 | Fuel & Flux Crushing Facilities(064) | 2007-0001/064 | 290.7258 | 310.0758 | 261.4585 | 1.0749 | 24.03 | 16.45 | 21.76
Blast Furnace # 8 Complex
15 | Blast Furnace # 8(010) | 2007-0001/010 | 1682.8 | 1906.48 | 1806.4709 | 77.6587 | 59.6 | 99.69 | 0
16 | Boilers & STG(011-1A) | 2007-0001/011-001-001 | 314.1 | 338.56 | 285.67 | 19.6453 | 10.2 | 22.15 | 7.76
17 | Steam turbine generator, back pressure turbine generator, cooling water system & power evacuation system(011-01B) | 2007-0001/011-001-002 | 176.8 | 194.97 | 173.9906 | 16.9433 | 5.6 | 20.81 | 0
18 | 3 x 225 M3 DM Water Plant(011-01C) | 2007-0001/011-001-003 | 26.3 | 27.517 | 26.4528 | 0 | 0 | 0 | 0
19 | Turbo Blowers and Auxiliaries (012) | 2007-0001/012 | 263 | 287.4395 | 261.0475 | 0.088097 | 19.88 | 16.2 | 0
20 | Second Sintering Machine (360 m2) in SP-3(020) | 2007-0001/020 | 666.7 | 764.65 | 760.3519 | 4.3027 | 0 | 4.3 | 0
21 | Hot Metal Handling System(031) | 2007-0001/031 | 121.7 | 133.2041 | 104.6483 | 3.9434 | 12.45 | 6.86 | 0
22 | Ore Handling Plant - Part B(061) | 2007-0001/061 | 570.2 | 604.24 | 520.521 | 17.1814 | 13.84 | 17.2 | 0
23 | Compressed Air Station # 4(114) | 2007-0001/114 | 135.9 | 153.69 | 149.6785 | 0 | 0 | 0 | 0
SMS # 3 Complex
24 | Civil work for BOF & CCP(033A) | 2007-0001/033-001 | -54.6189 | 53 | 52.2881 | 0 | 0 | 0 | 0
25 | Balance Civil work for BOF & CCP | 2007-0001/033-003 | 374.5612 | 430.5612 | 404.6702 | 3.7652 | 11.09 | 13.99 | 11
26 | Cast in situ Bored Piling Work in SMS-II | 2007-0001/033-001-001 | 78.5099 | 84.6363 | 74.6431 | 0 | 0 | 0 | 0
27 | Structural work for BOF & CCP | 2007-0001/033-002 | 725.0356 | 735.1256 | 597.6547 | 0 | 0 | 0 | 0
28 | BOF & CCP complex in SMS-III (Pkg. 033B2) | 2007-0001/033-005 | 10.6524 | 18.6524 | 16.9828 | 0.28229 | 1.41 | 0.77 | 0
29 | Balance Structural Pkg No.-033-B4 | 2007-0001/033-006 | 12.98 | 23.98 | 21.1118 | 1.194 | 1.4 | 1.91 | 0
30 | Balance Structural Pkg No.-033-B7 | 2007-0001/033-007 | 13.6838 | 18.6838 | 17.4278 | 0.47278 | 1 | 0.79 | 0
31 | Balance Structural Pkg No.-033-B5 | 2007-0001/033-008 | 22.1865 | 22.1865 | 13.8828 | 0.65321 | 2.69 | 1.14 | 0
32 | Balance Structural Pkg No.-033-B6 | 2007-0001/033-009 | 28.5356 | 28.5356 | 18.2631 | 0.26431 | 0 | 0.84 | 0
33 | Balance Structural (B1+B8) | 2007-0001/033-010 | 32.4 | 32.4 | 16.1019 | 0.63997 | 4 | 0.64 | 0
34 | BOF (SMS-3) (025) | 2007-0001/025 | 1373 | 1578.6096 | 1445.4518 | 1.927 | 44.35 | 26.755 | 0
35 | Secondary Refining Unit for SMS # 3 (25A) | 2007-0001/025-001 | 250.2 | 301.47 | 279.6431 | 7.6539 | 10.03 | 16.1 | 5.67
36 | Proc. of Indig. Refrac. pkg-02 STE | 2007-0001/025-006 | 4.7 | 4.7004 | 1.8212 | 0 | 0 | 0 | 0
37 | CCP (026) | 2007-0001/026 | 789.1 | 909.8702 | 783.3031 | 53.0051 | 16.5 | 53.01 | 0
38 | Hot Metal Desulphurisation unit for SMS-3 (027) | 2007-0001/027 | 42.8 | 49.25 | 36.4164 | 5.1202 | 4.17 | 11.09 | 1.19
39 | RMP #3 (028) | 2007-0001/028 | 267.9738 | 285.2861 | 244.1497 | 20.6041 | 6.21 | 24.5 | 0
40 | 7 No. Cranes for SMS # 3 above 100T Balance (029A) | 2007-0001/029-001 | 153.4437 | 165.3837 | 137.8667 | 0.56705 | 13.16 | 4.14 | 14.15
41 | EOT Cranes for SMS # 3 < 100T (029B) | 2007-0001/029-002 | 0 | 0.66 | 0.12234 | 0.54015 | 0 | 0.54 | 0
42 | EOT Cranes, repair trolleys & under sludge cranes for BOF & CCP (029B2) | 2007-0001/029-002-002 | 54.8 | 61.14 | 51.9602 | 0.71235 | 3.95 | 5.98 | 1.31
43 | 10 No. EOT Cranes for SMS # 3 > 100T (029A2) | 2007-0001/029-003 | 155.1 | 178.9827 | 160.5951 | 0.31774 | 13.48 | 3.93 | 14.46
44 | Erection testing commissioning of SMS III(131A) | 2007-0001/131-002 | 85.2771 | 94.1658 | 81.4892 | 0.27248 | 18 | 0.27 | 0
45 | Installation of Cranes for BOF & CCP (21 nos.) (029B1) | 2007-0001/029-002-001 | 159.7 | 178.24 | 154.4426 | 0.54457 | 11.48 | 13.92 | 3.82
46 | Interplant Pipe Conveyor from RMP-3 to RMP-2 (140) | 2007-0001/140 | 62.2 | 67.88 | 56.4127 | 8.9435 | 0 | 9.69 | 0
47 | External water system for SMS-III (077-01A) | 2007-0001/077-001 | -82.3424 | 28.24 | 27.7466 | 0.48881 | 0 | 0.49 | 0
48 | Balance Civil Works of Essential Facilities for External Water System for SMS-3 | 2007-0001/077-004 | 3.8464 | 24.4364 | 17.3368 | 0 | 0 | 0 | 0
49 | Proc. of various equip under external water system for SMS III | 2007-0001/077-005 | 0 | 26.87 | 26.8147 | 0 | 0 | 0 | 0
50 | Supply and Erection of Storage Tanks for external Water System for SMS III | 2007-0001/077-006 | 0 | 4.6388 | 4.6179 | 0 | 0 | 0 | 0
51 | Civil Works of WTP-2 under External Water Supply System for SMS-III | 2007-0001/077-007 | 1.2605 | 13.7719 | 6.1511 | 0 | 0 | 0 | 0
52 | Balance work for External Water System for SMS-III | 2007-0001/077-008 | 192.2 | 242.14 | 218.4057 | 10.6083 | 12.43 | 15.98 | 0
53 | Air Conditioning System & Ventilation System for BOF & CCP Complex | 2007-0001/125-001 | 41.3 | 46.66 | 35.8006 | 0.79866 | 7.94 | 3.3 | 0.97
54 | Fire Protection System for BOF &CCP/ New SMS-III | 2007-0001/126-001 | 4.21 | 6 | 5.4266 | 0 | 5.36 | 0 | 0
55 | Balance Work of Fire Protection System for BOF & CCP/New SMS-III Complex(Pkg No. 126-01A) at SMS-III of Bhilai Steel Plant. | 2007-0001/126-003 | 6.69 | 7.5 | 3.6585 | 2.8741 | 0 | 3.53 | 0.16
55a | Illumination,Earthingfor SMS-III(127) | 2007-0001/127 | 15.2 | 16.001 | 9.4422 | 0 | 5.59 | 0 | 0
56 | Installation of Drinking Water System for BOF & CASTER AREA at BSP, BHILAI – Pkg-127A-1 at Bhilai Steel Plant, Bhilai.” | 2007-0001/127-001 | 0 | 1.25 | 0.98297 | 0.16719 | 0 | 0.19 | 0.07
57 | Pneumatic Sample Transport system for BOF,CCP &SRU | 2007-0001/134 | 2.5 | 2.5 | 1.5599 | 0 | 0.19 | 0.25 | 0.06
58 | Refractory for protection of lining of BOF & CCP | 2007-0001/124 | 0 | 1 | 0.85384 | 0 | 0 | 0 | 0
59 | Road and Storm Water drainage network for SMS-III | 2007-0001/100-004-001 | 4.9 | 35.1 | 1.4329 | 0.21523 | 0 | 0.22 | 0
60 | Road and Storm Water drainage network for SMS-III | 2007-0001/100-004-002 | 35.1 | 35.1 | 13.6322 | 4.2094 | 18 | 15.4 | 1.27
61 | Erection, Testing, Cold trial & Assistance in Hot trial of Balance Plant & Equipment (Mechanical & Piping) of CV2 caster (Package No.131 | 2007-0001/131-006 | 0 | 1.85 | 0 | 2.1324 | 0 | 2.13 | 0.37
62 | Erection, Testing & Commissioning of Oxygen piping system, Nitrogen piping system, Lance cooling piping system for converter-3 of BOF & CCP COMPLEX (Package no.131A-2) at BSP, Bhilai” | 2007-0001/131-004 | 0 | 0.05 | 0 | 0.022562 | 0 | 0.02 | 0
63 | Erection, testing & commissioning of balance jobs of Gas recovery system of BOF complex of SMS-III | 2007-0001/131-005 | 0 | 0.29 | 0 | 0.14071 | 0 | 0.29 | 0
64 | Erection, Testing, Cold trial & Assistance in Hot trial of electrical works for CV2 caster | 2007-0001/131-007 | 0 | 1.1 | 0 | 0.91286 | 0 | 0.92 | 0.12
Bar & Rod Mill Complex
65 | Civil Works for BRM (051A1) | 2007-0001/051-001 | 141.4193 | 148.2802 | 125.7579 | 0.33403 | 4.99 | 7.67 | 0
66 | Structural Works for BRM (051A2) | 2007-0001/051-002 | 50.2258 | 55.4558 | 53.4417 | 0 | 0 | 1.44 | 0
67 | Addl Structural Works for BRM | 2007-0001/051-003 | 39.7356 | 49.7356 | 47.6998 | 0.0055523 | 0 | 1.68 | 0
68 | Bar and Rod Mill (046) | 2007-0001/046 | 417.6 | 512.49 | 446.3666 | 52.7377 | 21.64 | 64.8 | 0
69 | Reheating furnace for BRM (049-01) | 2007-0001/049-001 | 59.2 | 67.5645 | 62.5434 | 0.63072 | 0 | 3.54 | 1.455
70 | Hoisting & Handling Facilities in BRM & URM (030) | 2007-0001/030 | 159.4173 | 174.3273 | 112.4447 | 0.059599 | 8.985 | 3.7 | 10.92
71 | Illumination System for BRM,URM &Rail Welding Line (128) | 2007-0001/128 | 11.1 | 14.1 | 11.3603 | 0.68359 | 0 | 2.78 | 0
Universal Rail Mill Complex
72 | Civil Works for Universal Rail Mill (052A) | 2007-0001/052-001 | 277.9797 | 286.8397 | 271.1572 | 0 | 13.34 | 11.26 | 0
73 | Structural Works for Universal Rail Mill (052B) | 2007-0001/052-002 | 199.5346 | 202.3217 | 197.1781 | 0 | 0 | 0 | 0
74 | Universal Rail Mill (047) | 2007-0001/047 | 1443.3316 | 1595.7216 | 1465.2048 | 3.6006 | 66 | 83.55 | 0
75 | Reheating furnace for URM (049-03) | 2007-0001/049-003 | 85.224 | 93.058 | 83.0306 | 4.082 | 2.1306 | 7.96 | 0
76 | Air Drying Plant for Universal Rail Mill and Air Drying & Filtration Plant for Bar & Rod Mill (Pkg No 114A) | 2007-0001/114-001 | 0.7 | 1.5 | 1.3191 | 0.075509 | 0 | 0.14 | 0.03
77 | Rail Welding Plant (121) | 2007-0001/121 | 323.7 | 350.1736 | 333.6365 | 2.2553 | 0 | 2.26 | 0
78 | External water system for Mills & Fire Water Pump House (077-02A) | 2007-0001/077-002 | -17.5236 | 67.49 | 67.4911 | 0 | 0 | 0 | 0
79 | Civil and Structural works for construction of overhead pipe and cable gallery in URM Complex | 2007-0001/077-003 | 0.15961 | 2.23 | 2.2267 | 0 | 0 | 0 | 0
80 | Balance Civil Work for Completion of WTP-5 at BRM | 2007-0001/077-021 | 0.099629 | 2.8824 | 1.3693 | 0.31158 | 0 | 0.31 | 0
81 | Erection, Testing & Commissioning of Balance Electrics for Externam Water System for Mills | 2007-0001/077-022 | 0.058401 | 0.9761 | 0.5451 | 0 | 0 | 0 | 0
82 | Proc of various equipment for water packages at URM | 2007-0001/077-023 | 0 | 10.2187 | 6.7738 | 0 | 0 | 0 | 0
83 | Proc of various equipment for water packages at URM | 2007-0001/077-023-008 | 0 | 1.82 | 0.34208 | 0 | 0 | 0 | 0
84 | Balance civil works and Structural works for completion of all WTPs in URM and BRM | 2007-0001/077-024 | 0.73564 | 9.2787 | 6.2264 | 0 | 0 | 0 | 0
85 | Proc of CS Pipes ofr Balance Piping Works | 2007-0001/077-025 | 0 | 0.36 | 0 | 0 | 0 | 0 | 0
86 | Cast Basalt lined pipes, fittings | 2007-0001/077-026 | 0 | 4.5 | 4.4519 | 0 | 0 | 0 | 0
87 | Procurement of Cooling Towers | 2007-0001/077-027 | 0 | 2.5 | 2.4459 | 0 | 0 | 0 | 0
88 | Balance Work for External Water System for Mills and Fire Water Pump Houses (Package No.077-02A) | 2007-0001/077-028 | 112.3 | 178.33 | 158.4258 | 9.0657 | 6.46 | 9.93 | 3.74
89 | Civil Work of Overhead tank WTP-3 (URM) and DCW Circuit (BRM) | 2007-0001/077-029 | 0.18152 | 2.0915 | 0.90065 | 0.097394 | 0 | 0.1 | 0
90 | Proc of High Rate Nozzle less Scale Removal Filters and Media | 2007-0001/077-030 | 0 | 4.9 | 4.8587 | 0 | 0 | 0 | 0
91 | Balance Mechanical plant & Equ & Piping work | 2007-0001/077-002-000-02 | 0.12302 | 1.5711 | 1.0447 | 0 | 0 | 0 | 0
92 | Fire Protection System in Universal Rail Mill and Bar & Rod Mill | 2007-0001/126-002 | 5.4 | 25.67 | 22.8102 | 1.7308 | 1.4 | 2.28 | 0.58
93 | Air Conditioning & Ventilation System for BRM, URM & Rail Welding Line | 2007-0001/125-002 | 50.1 | 54.5202 | 43.5461 | 1.1514 | 1.75 | 4.69 | 1.18
94 | CNC Roll Turning Lathe Machines For URM | 2007-0001/142-001 | 22.3 | 26 | 25.9517 | 0 | 0 | 0 | 0
95 | Roll & Repair shop Equipment for URM with related facility. | 2007-0001/142-002 | 23.2 | 25.5 | 25.2628 | 0.12066 | 0 | 0.12 | 0
96 | Drop Test Facility for URM | 2007-0001/047-001 | 0.9 | 0.9 | 0.6594 | 0.058486 | 0 | 0.15 | 0
Augmentation of Capacity of Plate Mill
97 | Normalising Furnace | 2007-0001/050 | 37.9148 | 40.0448 | 25.1665 | 0 | 0 | 0 | 0
98 | Cooling Bed & Pilers | 2007-0001/048-003 | 203.0093 | 231.3893 | 196.978 | 0 | 0 | 0 | 0
99 | Edge Marking Machine | 2007-0001/048-004 | 7.9 | 8.81 | 5.7743 | 0 | 0 | 0 | 0
100 | 40 T EOT + 17 T Semi Portal Cranes | 2007-0001/048-005 | 7.946 | 8.876 | 6.8596 | 0 | 0 | 0 | 0
101 | CNC Roll Grinding Machine | 2007-0001/048-006 | 34.6015 | 39.3515 | 35.6354 | 0 | 0 | 0 | 0
102 | Guillotine Shear | 2007-0001/048-007 | 73.4808 | 84.2508 | 71.8466 | 0 | 0 | 0 | 0
Modification of SP # 2
103 | SP # 2 : Cold Sinter Screening System | 2007-0001/021-001 | 22.2 | 23.869 | 20.998 | 0.0596 | 0 | 0.62 | 1.68
104 | SP # 2 : Lime Dosing | 2007-0001/021-002 | 1.2 | 1.325 | 1.2369 | 0 | 0 | 0 | 0
105 | SP # 2 : Electrical & Automation System | 2007-0001/021-003 | 8.3 | 8.8811 | 8.0225 | 0 | 0 | 0 | 0
106 | SP # 2 : ESP based Dedusting System | 2007-0001/021-004 | 6.6 | 9.5 | 9.195 | 0 | 0 | 0 | 0
107 | Ore Handling Plant - Part A | 2007-0001/060 | 194.1 | 213.99 | 190.091 | 8.9117 | 0 | 8.91 | 0
Augmentation of Facilities in SMS # 2
108 | Material Handling System | 2007-0001/038-001 | 8.6 | 9.4467 | 8.1181 | 0.15595 | 0 | 0.16 | 0
109 | Gas Cleaning Plant Rectification | 2007-0001/038-003 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | Augmentation & De-bottlenecking facilities | 2007-0001/038-006 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | SMS # 2 : Revamping of Dedusting System at +47m level | 2007-0001/038-012 | 0.7 | 0.7181 | 0.71524 | 0 | 0 | 0 | 0
Common Packages
112 | MSDS-VII (070) | 2007-0001/070 | 225.0755 | 248.5655 | 205.4968 | 5.6803 | 12 | 14.79 | 4.93
113 | Installation of HT sub station at BSP (071A) | 2007-0001/071-001 | 383.3094 | 422.1994 | 400.0369 | 21.4935 | 18 | 21.49 | 0
114 | Interplant fuel gas & industrial gases piping for all units (075) | 2007-0001/075 | 151.9 | 162.66 | 155.088 | 0 | 2.45 | 7.57 | 0
115 | Energy Monitoring System | 2007-0001/075-001 | 3.1 | 3.44 | 3.2119 | 0 | 0 | 0.23 | 0
116 | Buffer Vessels and pressure reducing & metering station for oxygen,Nitrogen& argon | 2007-0001/075-002 | 49.9 | 58.28 | 54.1598 | 4.0047 | 2.94 | 4.02 | 0
117 | Installation of Oxygen and Compressed air pipelines alongwith valves (Pkg-075C) under 7 MT Modernization and Expansion of BSP | 2007-0001/075-003 | 0 | 0.52 | 0.00649 | 0.51467 | 0 | 0.51 | 0
118 | Gas Mixing and Booster Station (076) | 2007-0001/076 | 13.3 | 14.3703 | 14.2218 | 0 | 0.33 | 0 | 0
119 | Flyover & Road Network | 2007-0001/111-001 | 77.6 | 77.602 | 33.9444 | 0.80467 | 5.42 | 0.8 | 20
120 | Flyover & Road Network | 2007-0001/111-003 | 0 | 2 | 0.015732 | 1.603 | 0 | 1.6 | 0.17
121 | Fire Fighting System for Transformers TDS -1 | 2007-0001/113 | 23.1 | 23.1029 | 0.40058 | 0 | 0 | 0 | 0
122 | Propane storage & handling system | 2007-0001/032 | 8.9 | 9.56 | 8.5338 | 0.073884 | 0 | 0.3 | 0
123 | Inter Plant Telecommunication system | 2007-0001/037 | 11.9 | 13.0475 | 8.9912 | 0.061024 | 3 | 0.13 | 0
124 | Augmentation of Make-up water and drinking water systems | 2007-0001/078 | 19 | 53.54 | 53.538 | 0 | 0 | 0 | 0
125 | Balance Civil Works of IWPH, DWPH,MWPH and ECRS | 2007-0001/078-001 | 6.1702 | 5.4721 | 3.0583 | 0.060601 | 0 | 0.06 | 0
126 | Balance Outdoor Piping works for Augmentation of Makeup water and Drinking water system | 2007-0001/078-002 | 0 | 2.5153 | 1.8592 | 0.66361 | 0 | 0.66 | 0
127 | Civil works of Balance Outdoor Piping works for Augmentation of Makeup water and Drinking water system | 2007-0001/078-003 | 6.9844 | 6.0901 | 1.7781 | 0 | 0 | 0 | 0
128 | Structural works of Balance Outdoor Piping works for Augmentation of Makeup water and Drinking water system | 2007-0001/078-004 | 11.1899 | 11.1878 | 4.4974 | 0.11673 | 0 | 0.12 | 0
129 | Procurement of various equipments | 2007-0001/078-005 | 0 | 3.0252 | 2.2267 | 0.028156 | 0 | 0.03 | 0
130 | Procurement of SW pipes from balance outdoor piping work | 2007-0001/078-006 | 1.45 | 1.4454 | 0 | 0 | 0 | 0 | 0
131 | Balance work of Makeup Water and Drinking Water System (Pkg. No 078A) | 2007-0001/078-007 | 86.51 | 101.0117 | 80.0974 | 8.0796 | 8.33 | 15.51 | 2.13
132 | Procurement of SW pipes from balance outdoor piping work from RSP | 2007-0001/078-008 | 0 | 2.4766 | 0 | 0 | 0 | 0 | 0
133 | Balance Mechanical plant and Equip. and Piping Work for intake Well and Drinking Water Pump House | 2007-0001/078-009 | 0.13 | 0.1341 | 0.0012948 | 0.0069286 | 0 | 0.01 | 0
134 | Erection, Testing, Comm. Of Electrics for intake Well and Drinking Water Pump House | 2007-0001/078-010 | 0.31791 | 0.31961 | 0.20502 | 0 | 0 | 0 | 0
135 | Peripheral Yard - Railway Siding | 2007-0001/095-001 | 74.1719 | 75.9619 | 51.4036 | 0 | 2 | 0 | 0
136 | Internal Yard - Railway Siding | 2007-0001/095-002 | 60.7154 | 66.0974 | 62.3626 | 0 | 0 | 0 | 0
137 | Underbridge by box pushing technique below railway track going to slag yard in connection with modernisation of peripheral yard of bsp | 2007-0001/095-003 | 8.5909 | 8.5909 | 6.9181 | 0 | 0 | 0 | 0
138 | Electricfication work of railway track switching post | 2007-0001/095-004 | 21.82 | 21.82 | 11.6901 | 0 | 4.05 | 0 | 0
139 | Part rail track works for Plant Internal Yards | 2007-0001/095-005 | 0.24 | 5.44 | 5.43 | 0 | 0 | 0 | 0
140 | Rail track work for int.ward at BRM Area | 2007-0001/095-006 | 0.6 | 0.93 | 0.93435 | 0 | 0 | 0 | 0
141 | Balance Railway track Work for Plant Internal Yard | 2007-0001/095-007 | 19.9757 | 20.2257 | 11.2125 | 0 | 0 | 1.06 | 0.91
142 | Rerouting of UnderGround pipelines for hot metal movement | 2007-0001/095-008 | 1.3469 | 1.3469 | 0.67807 | 0 | 0 | 0 | 0
143 | WDS-6 Locomotives - 4 No. | 2007-0001/098-001-001 | 27.53 | 30.2658 | 30.2654 | 0 | 0 | 0 | 0
144 | WDS-6 Locomotives - 9 No. | 2007-0001/098-001-001-02 | 75.87 | 83.33 | 79.039 | 0 | 0 | 0 | 0
145 | Proc. of Mobile Fire fighting equipments | 2007-0001/098-003 | 5.6 | 5.6 | 5.401 | 0 | 0 | 0 | 0
146 | Instt. of Rail & Road Weigh BRIDGES | 2007-0001/099-001 | 1.6 | 1.6 | 1.514 | 0 | 0 | 0 | 0
147 | Installation of Hot Metal Rail Weigh Bridges | 2007-0001/099-002 | 1.7 | 1.8624 | 1.6671 | 0.044891 | 0 | 0.21 | 0
148 | LT S/S 50B and repl 9B&9H | 2007-0001/118 | 5.3 | 5.3 | 4.1538 | 0.37847 | 1 | 0.6 | 0.13
149 | NPC Wagons | 2007-0001/137 | 1.8 | 13.64 | 13.6447 | 0 | 0 | 0 | 0
150 | Preliminary Expenses | 2007-0001/999 | 298.4752 | 315.9994 | 232.5204 | 0.073029 | 7.65 | 0.07 | 0
151 | Consultancy Fees | 2007-0001/997-001 | 440 | 484.6404 | 491.8035 | 9.6871 | 12 | 9.69 | 0
152 | Contigency | Steel issues | 4.47 | 4.47 | 0 | 0 | 0 | 0 | 0
153 | New package SMS-3 (026C) |  | 100 | 100 | 0 | 2.07 | 40 | 7 | 40
154 | Unconfirmed packages(PKG90+100-02-04) |  | 41.31 | 41.31 | 0 | 0 | 0 | 0 | 0
155 | Rerouting of existing ash slurry pippeline at BSP |  | 10.5 | 10.5 | 0 | 0 | 0 | 0 | 0
156 | Quality Assurance and Quality Control Facility (Pkg. No.090A) | 2007-0001/090-007 | 72.59 | 72.59 | 51.9317 | 10.208 | 24.73 | 25.43 | 1.76
157 | Misc(fire Station Building)pkg-138 | pkg-116A,116B1,116B2,117,117A,118R,100-2,110,11-03,11-04 | 80.1 | 80.1 | 0 | 0 | 0 | 9.68 | 1.3
158 | Plant wide Data Network & Fire Detection & Alarm (Package-145) | 2007-0001/145 | 20 | 20 | 20.445 | 0.63634 | 0 | 1.49 | 0.49
| Sub-Total (A) |  | 17390.3387 | 19865.1769 | 17463.2144 | 518.9527 | 657.0956 | 908.996 | 195.345 | 0
B | UN-FIRMED PACKAGES |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | EDC/IDC/CONTINGENCY | 1000-0001 | 2467 | 3482.77 | 3403.7726 | 26 | 55 | 48 | 24
| TOTAL (A+B+C) |  | 19857.3387 | 23347.9469 | 20866.987 | 544.9527 | 712.0956 | 956.996 | 219.345 | 0
D | Koteshwar mines |  |  |  |  | 0 | 9.25
| GRAND TOTAL |  | 26761.9152 | 34853.5247 | 26438.167 | 957.0814 | 1874.3856 | 1864.996 | 1589.0259
Koteshwar mines have annual plan(BE) for 2021-22 is Rs9.25 crs which .

## Table 2.4 & 2.9 (hidden)
| Actual till Dec'21 | BE 21-22 | RE 21-22 | BE 22-23
Expansion
MEP- Bhilai Steel Plant (BSP) | #REF! | #REF! | #REF! | #REF!
MEP- Durgapur Steel Plant (DSP) | #REF! | #REF! | #REF! | #REF!
MEP- Rourkela Steel Plant (RSP) | #REF! | #REF! | #REF! | #REF!
MEP- Bokaro Steel Plant (BSL) | #REF! | #REF! | #REF! | #REF!
MEP- IISCO Steel Plant (ISP) | #REF! | #REF! | #REF! | #REF!
MEP - Salem Steel Plant (SSP) | #REF! | #REF! | #REF! | #REF!
Total MEP | #REF! | #REF! | #REF! | #REF!
A. MAJOR AMR SCHEMES
BSP Rowghat Mine - NPV/Mining Rights/Railway Line/Enabling work/ Power including consultancy | #REF! | #REF! | #REF! | #REF!
DSP Replacement of Converter Shells in SMS | #REF! | #REF! | #REF! | #REF!
RSP New HSM | #REF! | #REF! | #REF! | #REF!
RSP Rebuilding of COB-2 | #REF! | #REF! | #REF! | #REF!
BSL Modernisation of SMS-1 | #REF! | #REF! | #REF! | #REF!
BSL New Sinter Plant | #REF! | #REF! | #REF! | #REF!
BSL Rebuilding of COB-8 | #REF! | #REF! | #REF! | #REF!
Mines
Enhancement of Production Capacity at Gua along with Pellet Plant | #REF! | #REF! | #REF! | #REF!
Lease Renewal for Gua, KIOM & MIOM, Bolani Mines (NPV, Compensatory Afforestation, Stamp duty and Registration charges | #REF! | #REF! | #REF! | #REF!
TOTAL Major AMR | #REF! | #REF! | #REF! | #REF!
Capital Repairs & Spares | #REF! | #REF! | #REF! | #REF!
Unsanctioned Schemes | #REF! | #REF! | #REF! | #REF!
Joint Venture including Capitalisation | #REF! | #REF! | #REF! | #REF!
OTHER SMALL SCHEMES | #REF! | #REF! | #REF! | #REF!
GRAND TOTAL | #REF! | #REF! | #REF! | #REF!
| Sanctioned Cost | Actual upto Mar’21 | BE 21-22 | RE 21-22 | Actual up to Dec'21 | BE 22-23
Sanctioned Schemes
MEP | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Other AMR Schemes | #REF! | #REF! | #REF! | #REF! | #N/A | #REF!
Sub-Total | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Capital Repairs & Spares | - | - | #REF! | #REF! | #REF! | #REF!
Unsanctioned Schemes | - | - | #REF! | #REF! | #REF! | #REF!
JV including capitalisation | - | - | #REF! | #REF! | #REF! | #REF!
Total | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| MEP | Exp | AMR | Exp | CR&S | Exp | Unsanctioned | Exp | Plan Total | Exp Total | Sanctioned MEP | Actual MEP up to March'21 | Sanctioned AMR | Actual up to March'21
Bhilai Steel Plant | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Durgapur Steel Plant | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #N/A | #N/A | #REF! | #REF! | #REF! | #REF!
Rourkela Steel Plant | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #N/A | #N/A | #REF! | #REF! | #REF! | #REF!
Bokaro Steel Plant | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #N/A | #N/A | #REF! | #REF! | #REF! | #REF!
ISP | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #N/A | #N/A | #REF! | #REF! | #REF! | #REF!
Alloy Steels Plant | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #N/A | #N/A |  |  | #REF! | #REF!
Salem Steel Plant | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #N/A | #N/A | #REF! | #REF! | #REF! | #REF!
VISL | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #N/A | #N/A |  |  | #REF! | #REF!
Kuteshwer Mines | #REF! | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | #N/A | #N/A
Jharkhand Group of Mines | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #N/A | #N/A |  |  | #REF! | #REF!
Jharkhand Collieries | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #N/A | #N/A |  |  | #REF! | #REF!
Odisha Group of Mines | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #N/A | #N/A |  |  | #REF! | #REF!
Central Units excluding JV | #REF! | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | #N/A | #N/A
Joint Venture including Capitalisation | #REF! | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | #N/A | #N/A
Chandrapur Ferro Alloy Plant | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #N/A | #N/A |  |  | #REF! | #REF!
Total | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF!
Total W/O JV | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF!

## <30 Cr format
CAPEX of Projects < Rs.30 Crores
|  | Category | No. of projects | Total Cost | Expd till 31.3.26 | CAPEX (BE) for FY27 | Expd in FY27 till month | Total expd till month
| A | Total Ongoing Projects | 42 | 444.0452 | 70.3816 | 159.3 | 18.7752 | 89.1569
| i) | Ongoing since previous FY | 18 | 260.2412 | 70.3816 | 126 | 18.7659 | 89.1475
| ii) | Started during FY26-27 | 24 | 183.804 | 0 | 33.3 | 0.0093594 | 0.0093594
| B | Total Projects completed during FY 26-27 till the month (from Sl. No. A at row 6) | 11 | 51.383 | 14.4408 | 25.7181 | 6.5007 | 20.9414
| i) | Old schemes completed in FY26-27 (from Sl. No. i of A at row 7) | 9 | 49.9706 | 14.4408 | 24.38 | 5.6625 | 20.1033
| ii) | Started and completed during 2026-27 (from Sl. No. ii of A at row 8) | 2 | 1.4124 | 0 | 1.3381 | 0.83811 | 0.83811
| C | New Projects (<30 Cr) | 14 | 72.9764 | 0 | 10.4 | 0 | 0
|  | Under Tendering | 13 | 71.604 | 0 | 9.4 | 0 | 0
Under Consideration
|  | Completed schemes including IDC |  |  |  | 34.59 | 80.5741 | 80.5741
|  | TOTAL | 67 | 568.4045 | 84.8224 | 230.0081 | 105.85 | 190.6724
| No of On-going projects as on 01.04.26 | No. of projects started in 2026-27 | Status | Ongoing Projects in the Month (Nos.) | [12 empty] | No of ongoingprojects as on date
|  |  |  | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | No. of projects completed in 2026-27
| 27 | 26 | Ontime | 2026-04-01: 1; 2026-05-01: 2; 2026-06-01: 3 | 6 | 28
|  |  | Delayed by <1 year | 2026-04-01: 2; 2026-05-01: 1; 2026-06-01: 2 | 5 | 10
|  |  | Delayed by >1 year | [12 empty] | 0 | 4
|  |  | Sub-Total | 3 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 42 | 53