Annexure-E

Progress of Expansion Plan:

Status of other major projects costing Rs.150 Crore and above is given below:

| Sl. No. | Name of the Project/Plant | Cost (Gross) | Expenditure till June’2026 | Likely completion date |
| --- | --- | --- | --- | --- |
| 1 | Stamp Charge COB#7-Battery Proper Along with Oven Machine & refractories at RSP | 2584.41 | 1144.44 | Mar’2028 |
| 2 | Stamp Charge COB#7-Coke Dry Cooling Plant including BPTG, Gas Fired Boiler and DM Water Plant at RSP | 1064.55 | 73.32 | Aug’2028(2 out of 3 chambers by Mar’28) |
| 3 | Stamp Charge COB#7-By Product plant including BOD Plant and water supply system at RSP | 1140.07 | 165.56 | Mar’2028 |
| 4 | Implementation of Treatment System-2 Under ZLD | 216.02 | 117.21 | Sept’26 |
| 5 | Product Testing Laboratory for NPM, SPP & NHSM | 155.26 | 53.34 | Aug’27 |

Status of other major projects costing Rs.150 Crore and above:

- Stamp Charge COB#7-Battery Proper Along with Oven Machine & refractories at RSP

    - Sanction order issued to RSP on 07.09.2024.

    - Contracts for Battery Proper have been signed in 07-October, 2024.

| Physical progress (%) |  |  | Financial progress (%) |  |  | Reason for shortfall (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Plan for the month | Actual for the month | Overall | Plan for the month | Actual for the month | Overall |  |
| 7.00 | 3.21 | 50.48 | 1.93 | 3.14 | 44.28 |  |

    - General Layout Drawing Approved.

    - M1 & M2 Milestone completed.

    - Ground breaking done on 22.01.2025. Area survey completed.

    - Design & Engg. under progress.(Basic Engg. completed, Detail Engg. under progress)

    - Piling work (1773 nos. completed out of 1847 nos. as on 30.06.2026)

    - Piling work in Test Piles (05 nos.), Coal silo area (197 nos.), Battery#7A (253 nos.), Battery#7B (250 nos.), Buttress Wall 7A (48 nos.), Buttress Wall 7B (48 nos.), Coal Tower (156 nos.), Intermediate Bench (22 nos.), Stack Flue Tunnel (38 nos.), End Bench 7B (48 nos.), Pipe rack stockade (40 nos.), NTP#1 (8 nos.), Primary Crusher House (17 nos.) and Intermediate Storage Hopper Building (21 nos.) Hammer Exchange Building (34/34), Conveyor Y7 (12/12) completed.

    - Piling work under progress in Coke bucket car Track, End Bench-7A, Pushing Emission Control System (PECS) , Stamp Charging Pushing Machine (SCPM)  Track, Coke Bucket Repair Station, Existing Crusher House,  etc

    - Civil work Completed of Coal Handling silo-6 nos., deck slab & buttress wall of Battery#7A & Battery #7B side, Coal Tower, Conveyor Y1–Y2, , Compressor room for Silo,  Waste Gas Channel 7A, Ramp of Overhead storage Hopper etc

    - Civil work of, Waste gas tunnel, Common flue tunnel 7A&7B, Pushing Emission Control System (PECS) stack foundation, secondary crusher house, LBDS-20, Stamp Charging Pushing Machine (SCPM) Track, Coke Bucket Car Track, (HPALA) Building, control room, BC 309A & 309C, BF gas pipeline footing, Switchgear Control House – Electrical Control Room (SCH ECR), Media tunnel, Conveyor Y13, Conveyor Y14 tunnel,  Admin Building, GIS building, NTP-2, NTP-1, Cable Gallery TR-21 under progress.

    - TOPR (Temporary Oven Protection Roof) erection along with sheeting completed for Battery#7A side. TOPR erection completed for Battery#7B side, sheeting under progress

    - Structural & Mechanical Erection under progress.

- Stamp Charge COB#7-Coke Dry Cooling Plant including Back Pressure Turbine Generator (BPTG), Gas Fired Boiler and De mineralized Water (DM) Water Plant at RSP

| Physical progress (%) |  |  | Financial progress (%) |  |  | Reason for shortfall (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Plan for the month | Actual for the month | Overall | Plan for the month | Actual for the month | Overall |  |
| - | - | - | 0.09 | 3.44 | 6.89 |  |

- Sanction order issued to RSP on 07.09.2024.

- Contracts for Coke Dry Cooling Plant have been signed in 05-October, 2024.

- Contract Terminated due to banning of M/s BEC.

- Subsequently proposal was retendered on 27.08.2025.

- Proposal was firmed-up & EC in its meeting held on 05.02.2026 accorded approval for award of work. Sanction received on 06.02.2026.

- LoA issued on 07.02.2026.

- Contract signed on 20.02.2026 for Coke Dry Cooling Plant of Coke Oven Battery No. 7 with the Consortium of Larsen & Toubro Limited & State Institute for Designing Enterprises of Coke Oven and By-Product Plants LLC (JV “GIPROKOKS” LLC) with schedule completion by 20th Aug’28.

- Kick Off meeting held on 20.02.2026.

- 1st milestone(M1) & 2nd Milestone (M2)  achieved & payment done

- Design & Engineering under Progress

- Ground breaking done on 28.05.2026.

- Stamp Charge COB#7 - By-Product plant including Biochemical Oxygen Demand (BOD) Plant and water supply system at RSP

    - Sanction order issued to RSP on 07.09.2024.

    - Contract for By-product plant have been signed in 04-October, 2024.

| Physical progress (%) |  |  | Financial progress (%) |  |  | Reason for shortfall (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Plan for the month | Actual for the month | Overall | Plan for the month | Actual for the month | Overall |  |
| 1.78 | 5.59 | 21.2 | 0.88 | 4.47 | 14.52 |  |

- General Layout Drawing Approved.

- Area survey, soil investigation & underground mapping completed

- Design & Engg. Under progress.

- Piling work started in Electrostatic Tar Precipitator.

- Civil Work Completed:- LCSS-1 building, Exhauster machine foundation & Slab, PGC foundation, Tar Separator Plant (TSP) & Detarred Ammonia Plant (DAP) foundation, Tar tank foundation in old CCD Site B, Tar separator, Coarse Condensation Plant(Decanter), Workshop building, Gas Liquor Tank

- Civil Work Under progress in Gas Distribution Plant) BOD & ZLD area (Clariflocculator, Equalization Tank, Aeration Tank), cooling tower, Scrubbing plant, Electrostatic Tar Precipitator.

- Supply: All imported equipment, including the Exhauster, Tail Gas Analyzer, and Start-up Burner, as well as indigenous equipment such as the Exhauster Motor and VAM Machine, has been delivered to site.

- Mechanical works are under progress for Tar Tanks at both Old and New CCD (Coke Chemical Department) sites, as well as for the De-tarring Ammonia Plant tank

- Implementation of Treatment System-2  Under ZLD

- Sanction Order issued to RSP on 28.02.2025.

- LOA issued to agency on 28.02.2025.

- Contract signed on 12.03.2025

| Physical progress (%) |  |  | Financial progress (%) |  |  | Reason for shortfall (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Plan for the month | Actual for the month | Overall | Plan for the month | Actual for the month | Overall |  |
| 7.25 | 4.16 | 83.19 | 4.17 | 3.53 | 54.26 |  |

- Kick Off meeting held on 12.03.2025.

- Design & Engg. Under progress.

- 1st Milestone (M1) & 2nd Milestone (M2) completed in May’25.

- Pilling work(508 nos.) completed.

- Civil work completed for Common collection Sump area(CCS) & Filtration area, Electrical Building ,Ultra Filtration (UF-RO) Pump House (SMS-II), Treated Water Storage Tank, RO Feed Tank , RO reject Tank, Firewater Reservoir, Ultra filtration – Reverse Osmosis (UF-RO) –TS-II. Filter Press Building, SLF.

- Civil work under progress for  , Emergency Over Head Tank, Secure Landfill (SLF), Equalization Tank, Chemical Building, , Dyke area,  PBS Pump House, Clear water storage tank, UF Feed Tank,  etc

- Mechanical erection completed for Mechanical Gravity Filter (MGF) CCS UF Skid , SMS-II: UF RO Pump house Area All Mechanical Equipment's and Pipe Line Work Completed , PBS : UF RO Pump house Area Erection Completed .

- Pipeline laying work under progress.

- Electrical Erection : Transformer erection Completed. under progress Electrical Building (PCC Panel & Cable Tray Installation), and SMS-II UF-RO Building cum Pump House (MCC Alignment & Coupling, Air Blower System and associated equipment installation activities).

- Product Testing Laboratory for NPM, SPP & NHSM

| Physical progress (%) |  |  | Financial progress (%) |  |  | Reason for shortfall (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Plan for the month | Actual for the month | Overall | Plan for the month | Actual for the month | Overall |  |
| 4.25 | 8.41 | 52.56 | 1.93 | 2.25 | 34.36 |  |

- LoA issued on 05.06.2025.

- Contract signed on 04.07.2025.

- Kickoff meeting held on 04.07.2025.

- Design & Engg. Under progress.

- Ground breaking done on 03.11.2025.

- Enabling activities completed.

- Civil work completed for Parking shed & Scrap Shed and under progress for Main Lab Building, macro etching lab and  Drop weight tear test(DWTT) Building, MCC Building

- Supply of equipments under progress. (X-Ray Fluorescence Analyzer (Ex- XRF), Optical Emission Spectrometer (OES), Profile Projector, Image analyzer, transformer, vertical milling machine, Field Emission Scanning Electron Microscope (FESEM, Hardness testing Machine), Cupping Testing Machine, CNC & Conventional Lathes, Band Saw Machines, Vertical Drilling Machine, Grinding & Polishing Equipment, Oxygen/Nitrogen/Hydrogen Analyzer, Carbon/Sulphur Analyzer, Pulverizer, Pelletizer, Stone Grinder, Hammer Mill, Precision Balances, pH & Conductivity Meters, Oil Emulsion Tester, Dean & Stark Apparatus etc