Annexure

- Performance in Projects area of RSP:

- Status of major projects:

- Installation of 1000 tpd Oxygen Plant on Construct, Operate and Maintain (COM) Basis:

- Civil Works completed.

- Mechanical Works:

  - Completed for Cooling tower, Cold box ,Main heat Exchanger, cooling tower, pre-purifications units, seal gas tank, LAR tank

  - Erection activities for Horton Sphere, LOX & LIN tanks, vaporizers under progress

- Piping Works: Underground piping completed; above-ground piping is under progress.

- Electrical Works: 30 MVA HT transformer erections done, LT Transformer-6 nos. erection done, Panel Erection & cable tray work completed. Bus duct, Cable Laying, Testing of Transformer, Earthing & instrumentation work under progress..

- Individual equipment trials to start in June’26

- Installation of Micro Pellet plant at RSP on COM basis:

- Design & Engg. completed.

- Civil works completed

- Structural work Completed for Shed#1 & Shed#2.

- Supply of all major equipments completed.

- Mechanical Erection- Completed

- Trial run of mixers done on 30.05.2026

- Installation of Stamp Charge Coke Oven Battery No. 7 along with CDCP and By-product Plant: Contracts for Battery Proper, Coke Dry Cooling Plant and By-product plant have been signed in October, 2024.

- Battery Proper:

- Ground breaking done on 22.01.2025.

- Design & Engg under progress.

- Piling works

  - 1766 nos. completed out of 1827 nos. as on 30.05.2026

  - Completed: Test Piles (05 nos.), Coal silo area (195 nos.), Battery#7A (250 nos.), Battery#7B (250 nos.), Buttress Wall 7A (48 nos.), Buttress Wall 7B (48 nos.), Coal Tower (156 nos.), Intermediate Bench (22 nos.), Stack Flue Tunnel (38 nos.), End Bench 7B (48 nos.), Pipe rack stockade (40 nos.), Pipe rack (40 nos.), NTP#1 (8 nos.), Primary Crusher House (17 nos.) and Intermediate Storage Hopper Building (21 nos.),

  - Under progress in Coke bucket car Track, End Bench-7A, Stamp Charging Pushing Machine (SCPM)  Track, Coke Bucket Repair Station, Existing Crusher House, Hammer Exchange, etc.

- Civil works:

  - Completed- Coal Handling silo-6 nos., deck slab & buttress wall of Battery#7A & Battery #7B side, Coal Tower, Conveyor Y1–Y2, Admin Building, GIS building, NTP-2, NTP-1, Cable Gallery TR-21, etc

  - Under Progress - Waste gas tunnel, Common flue tunnel 7A&7B, Pushing Emission Control System (PECS) stack foundation, secondary crusher house, LBDS-20, Stamp Charging Pushing Machine (SCPM) Track, Coke Bucket Car Track, (HPALA) Building, control room, BC 309A & 309C, BF gas pipeline footing, Switchgear Control House – Electrical Control Room (SCH ECR), Media tunnel, Conveyor Y13, Conveyor Y14 tunnel,  under progress.

- Supply of TOPR structures completed.

- TOPR erection along with sheeting completed for Battery#7A side. TOPR erection completed for Battery#7B side, sheeting under progress

- Structural Erection: under progress for Compressor Room, CI bend erection, SCPM Track, cable gallery(MSDS-3 to MSDS-6), Y1 –Y2  Conveyor system , NTP-1, NTP-2 ,Cable gallery from MSDS-3 –MSDS 6

- Mechanical erection under progress (5MT EOT crane  for Battery#7B completed)

- Coke Dry Cooling Plant:

- Earlier Contract with M/s BEC

  - Area survey, soil investigation & underground mapping completed.

  - M/s BEC Ltd. has been banned with effect from 03.06.2025. Contract Terminated,

- Retendering with order placement

  - Subsequently proposal was retendered on 27.08.2025.

  - Proposal was firmed-up & EC in its meeting held on 05.02.2026 accorded approval for award of work. Sanction received on 06.02.2026.

- Progress

  - LoA issued on 07.02.2026.

  - Contract signed on 20.02.2026 with the Consortium of Larsen & Toubro Limited & State Institute for Designing Enterprises of Coke Oven and By-Product Plants LLC (JV “GIPROKOKS” LLC) with schedule completion by 20th Aug’28. (2 out of 3 chambers by Mar’28)

  - Kick Off meeting held on 20.02.2026.

  - 1st milestone(M1) achieved & payment done.

  - Design & Engineering under Progress

  - Ground breaking done on 28.05.2026.

- By-product plant:

- Area survey, soil investigation & underground mapping completed.

- Design & Engg. under progress.

- Civil works:

  - Civil work completed for LCSS-1 building, Exhauster machine foundation & Slab, PGC foundation, Tar Separator Plant (TSP) & Detarred Ammonia Plant (DAP) foundation, Tar tank foundation in old CCD Site B, Tar separator, Coarse Condensation Plant(Decanter), Workshop building, Gas Liquor Tank

  - Under progress in Gas Distribution Plant) BOD & ZLD area (Clariflocculator, Equalization Tank, Aeration Tank), cooling tower, Scrubbing plant, Electrostatic Tar Precipitator. Mechanical work under progress in Tar Tank in Old & New CCD Site, & DAP tank

- Supply:  Exhauster delivered on site.

- Mechanical works are under progress for Tar Tanks at both Old and New CCD (Coke Chemical Department) sites, De-tarring Ammonia Plant tank.

- Installation of 2 Mtpa Pellet Plant on COM basis:

- Contract signed on 14.02.2025.

- Enabling job-Site area leveling (1.5 lakh cum) completed.

- Design & Engineering completed.

- Order placed for all critical items.

- Major civil work completed.

- Equipment supply under progress.(approx 85% completed)

- Structural erection under progress(PD Building, TG building, grinding, filter press, etc)

- Equipment erection completed TG building, annular cooler, balling mill, thickener, screens & under progress for filter press, grinding mill, hydro cyclone, ESP, etc

- Refractory work under progress in Duct Lines Cooler, Rotary Kiln, TG unit.

- Installation of 4th Stove in BF-5:

- Contract signed on 10.02.2025.

- Ground breaking done on 26.08.2025.

- Design & Engineering completed

- Civil work completed for Gas Analyzer room and under progress for valve stand area.

- Refractory support structure supply completed, refractory supply under progress.

- All 16 Nos. tier stove shells and 10 nos. domes delivered, assembly and erection of stove shells under progress. T-1 to T-10 erected on foundation, T-11 to T-13 ready, T-15, 16 assembly under progress.

- Major Equipment-Stove Valves (imported) shipped from Germany, delivered at site.

- Implementation of Treatment System-2 under ZLD:

- Contract signed on 12.03.2025

- Design & Engineering completed.

- Pilling work (508 nos.)  completed

- Civil work completed for Common collection Sump area(CCS) & Filtration area, Electrical Building Ultra Filtration (UF-RO) Pump House (SMS-II)

- Civil work under progress for  Ultra filtration – Reverse Osmosis (UF-RO) –TS-II, Emergency Over Head Tank, Secure Landfill (SLF), Equalization Tank, Chemical Building, Filter Press Building, Dyke area, Filter Water (FW) Pump House, Plant Booster System Pumps (PBS) Pump House etc

- Mechanical erection completed for Mechanical Gravity Filter (MGF) & under progress for CCS, Backwash Waste Water Transfer Pump, UF Skid UF Pump House (Pump Alignment).

- Pipeline laying is progressing at site, with hydro testing works also in progress.

- Electrical Erection under progress Electrical Building (PCC Panel & Cable Tray Installation), and SMS-II UF-RO Building cum Pump House (MCC Alignment & Coupling, Air Blower System and associated equipment installation activities).

- Replacement of one EOT Crane (250+75/10) t in converter charging bay of SMS-2:

- Contract Signed on 28.05.2025.

- Design & Engineering completed.

- Manufacturing under progress(No load trial run done in manufacturer premises, panel inspection done, assembly under progress at manufacturer premises)

- Product Testing Laboratory for NPM, SPP & HSM-2:

- Contract signed on 04.07.2025.

- Ground breaking done on 03.11.2025.

- Design & Engg. under progress.

- Enabling/Dismantling activities completed.

- Civil work completed for parking shed & Scrap Shed and under progress for Main Lab Building, Macro Etching.

- Equipment Supply under progress: X-Ray Fluorescence Analyzer (XRF), Optical Emission Spectrometer (OES), Profile Projector, Image analyzer, Transformer, Vertical Milling Machine, Field Emission Scanning Electron Microscope (FESEM), Hardness testing Machine and  Drop weight tear test(DWTT) Building arrived at Site.

- Status of Projects under Stage-II Approval:

- Status of Projects under Tendering:

- Transportation of Coal from Coke Oven Battery COB#6 to COB#1-5 along with Installation of Silos:

- Price bid was opened on 24.06.2024. M/s Indure Pvt. Ltd. emerged as L-1 bidder. Negotiation completed, L-1 price higher than estimate. TC recommendation for re-tendering approved. Retendered on 29.03.2025 with ToD scheduled on 26.04.2025. Pre-bid held on 08.04.2025. 8 parties participated. ToD extended till 07.06.2025(2nd Extension), further extended up to 14.06.2025 (2nd Extension). Six offers received and opened on 14.06.2025. Proposal for cancellation of tender approved by CA on 28.08.2025. Retendered on 06.04.2026 with ToD scheduled on 04.05.2026. Pre-bid held on 16.04.2026(11 bidders participated). ToD extended till 18.05.2026. 4 offers received & opened on 18.05.2026. Under Techno-commercial evaluation

- Status of projects under Stage-I approval:

- Dust Extraction system for BF#1:

- Proposal sent to Corporate Office for stage-I approval on 22.03.2025.

- EMD Observation received on 07.04.2025 & complied on 19.04.2025.

- CoD held on 21.05.2025. Compliance to CoD Observation sent to Corporate Office on 07.01.2026.

- CoD held on 18.05.2026.

- Dust Extraction system for SP#3:

- Proposal sent to Corporate Office for stage-I approval on 11.09.2025.

- CoD held on 18.09.2025. Compliance to CoD Observations sent to corporate office on 30.03.2026.

- CoD held on 18.05.2026.

- Provision of Mixed Gas Firing in oil fired kilns at CP II

- Proposal sent to Corporate office on 26.05.2026 for stage-I approval