Production Performance: PPC

| Parameters | Nov'24 (T) | % Growth over Oct'24 | % Growth over Nov'23 | Apr-Nov 2024-25 (T) | Apr-Nov 2023-24 (T) | % Growth over CPLY |
| --- | --- | --- | --- | --- | --- | --- |
| Total Crude Steel Production |  |  |  |  |  |  |
| Total Finished Steel Production |  |  |  |  |  |  |
| OGOM Production |  |  |  |  |  |  |

The reason for the shortfall is provided in the Annexure.

Capital Expenditure (CAPEX): PROJECTS

| Expenditure Head | June’26 |  | Cumulative till June’26 |  |
| --- | --- | --- | --- | --- |
|  | Actual | Target | Actual | Target |
| MEP | 0.00 | 0.00 | 0.00 | 0.00 |
| AMR | 238.70 | 122.70 | 802.33 | 391.70 |
| Capital Repair & Spares | 2.20 | 17.30 | 2.20 | 53.30 |
| New Schemes | 0.00 | 8.93 | 0.00 | 0.00 |
| Total | 240.90 | 140.00 | 804.53 | 445.00 |

Expansion Projects and Key Projects Progress: PROJECTS

- RSP Expansion- Boundary wall construction is progressing steadily, with excavation & PCC Completed , 85% columns, 80% plinth beam, 66 % (7483 Mtr)  first lift RCC wall, and 16% (1898 Mtr) full RCC wall completed across 9.962 km.

- 0.18 MTPA Micro-pellet plants on COM basis 	Trial and testing of Mixers & Conveyor Done on 01.06.2026, All Statutory clearances received (CEA, Consent to Operate from SPCB, Licences  to Operated from Factory Boiler).

- 30 MLD STP PG certificate issued on 15.06.2026.

- 4th Stove for BF 5 all 16 Nos. Shell erection completed.

- 2 MTPA Pellet Plant Chimney Refractory erections started.

Areas of Concern that requires immediate action: PPC

Best ever production: PPC

Improvements in techno-economic and productivity parameters: PPC

Efforts towards reduction of carbon emissions: ENV.

Safety initiatives: SED

HR initiatives: HR

Achievements in GEM procurement / others: MM

Annexure

Reason for the shortfall: PPC

| Parameters | Nov'24 (T) | % Growth over Oct'24 | Remark |
| --- | --- | --- | --- |
| Total Hot metal Production |  |  |  |
| Total Crude Steel Production |  |  |  |
| Total Finished Steel Production |  |  |  |
| OGOM Production |  |  |  |

| Parameters | Nov'24 (T) | % Growth over Nov’23 | Remark |
| --- | --- | --- | --- |
| Total Hot metal Production |  |  |  |
| Total Crude Steel Production |  |  |  |
| Total Finished Steel Production |  |  |  |
| OGOM Production |  |  |  |