June’26

RSP- IMPLEMENTATION OF New Product Testing Laboratory for NPM, SPP and HSM-2

Details of the Project

| Date of Approval (dd/mm/yy) | Date of awarding contract (dd/mm/yy) | Original date of Completion (dd/mm/yy) | Revised date of Completion (dd/mm/yy) | Anticipated date of Completion (dd/mm/yy) | Time Overrun (in months) | Original Cost (in Rs. Crore), Net of ITC | Revised cost ( in Rs. Crore) | Anticipated Cost (in Rs. Crore), Net of ITC | Cost Over-run (inRs. Cr.) | Cum. Exp. Till the month (in Rs. Crore), Gross |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |
| Jun’2025 | Jul’25 | Aug’27 |  | Aug’27 | - | 155.26 | - | 155.26 | - | 53.34 |

- Progress of the Project

| Brief Description of Progress (Main package) | Overall % Target till the month | Cumulative % completion till the month | % target for the month |  | % achievement for the month |
| --- | --- | --- | --- | --- | --- |
| Design & Engineering | 93.75% | 87.50% |  | 9.38% | 40.00% |
| Civil Work (RCC) | 40.25% | 47.51% |  | 9.60% | 54.13% |
| Structural Supply | 100.00% | 100.00% |  | 0.00% | -- |
| Structural Erection | 24.00% | 92.00% |  | 8.00% | 650.00% |
| Equipment Supply | 35.56% | 37.78% |  | 1.48% | 0.00% |
| Equipment Erection | 0.00% | 0.00% |  | 0.00% | -- |

- Milestones reported on OCMS portal of MoSPI

| Name of the Milestone | Original Start Date | Original Completion Date | Anticipated Start Date | Anticipated Completion Date | Reasons for non-completion (if any) |
| --- | --- | --- | --- | --- | --- |
| Civil Work of Buildings ( Macro Etching, Main Building, DWTT, MCC cum UPS) | 03.06.2026 | 04.03.2027 | Started on 06.02.2026 |  |  |

- Reasons/ Issues/ Constraints for Time & Cost Overrun for the Project

| Name of the Issue/ Constraint | Year | Status | Action Taken by CPSEs | Intervention required at Ministry level |
| --- | --- | --- | --- | --- |

- Key Officials for the Project

- Shri. Rakesh Kumar Meena , AGM (Projects)