June’26

RSP- COB#7 - Battery Proper-PKG-2

- Details of the Project

| Date of Approval (dd/mm/yy) | Date of awarding contract (dd/mm/yy) | Original date of Completion (dd/mm/yy) | Revised date of Completion (dd/mm/yy) | Anticipated date of Completion (dd/mm/yy) | Time Overrun (in months) | Original Cost (in Rs. Crore), Net of ITC | Revised cost ( in Rs. Crore) | Anticipated Cost (in Rs. Crore), Net of ITC | Cost Over-run (inRs. Cr.) | Cum. Exp. Till the month (in Rs. Crore), Gross |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |
| Sept’2024 | Oct’24 | March’28 |  | March’28 | - | 2584.81 | - | 2584.81 | - | 1144.44 |

- Progress of the Project

| Brief Description of Progress (Main package) | Overall % Target till the month | Cumulative % completion till the month | % target for the month |  | % achievement for the month |
| --- | --- | --- | --- | --- | --- |
| Design & Engineering | 96.59% | 90.15% |  | 2.76% | 15.87% |
| Civil Work (RCC) | 65.84% | 64.68% |  | 5.55% | 122.32% |
| Structural Supply | 77.62% | 53.15% |  | 13.55% | 47.74% |
| Structural Erection | 18.86% | 18.47% |  | 3.07% | 171.93% |
| Mechanical Supply | 47.47% | 46.77% |  | 8.47% | 14.35% |
| Mechanical Erection | 1.91% | 0.99% |  | 0.96% | 0.07% |
| Electrical Supply | 47.74% | 44.52% |  | 8.39% | 76.92% |
| Electrical Erection |  |  |  |  |  |
| Refractory Supply | 78.35% | 64.93% |  | 7.97% | 24.65% |
| Refractory Erection | 15.16% | 0.00% |  | 15.16% | 0.00% |

- Milestones reported on OCMS portal of MoSPI

| Name of the Milestone | Original Start Date | Original Completion Date | Anticipated Start Date | Anticipated Completion Date | Reasons for non-completion (if any) |
| --- | --- | --- | --- | --- | --- |
| Civil Work for Silo Building | 02.05.2025 | 12.11.2026 | Actual – 07.05.2025 |  |  |

- Reasons/ Issues/ Constraints for Time & Cost Overrun for the Project

| Name of the Issue/ Constraint | Year | Status | Action Taken by CPSEs | Intervention required at Ministry level |
| --- | --- | --- | --- | --- |

- Key Officials for the Project Shri. K. K Patra ,GM (Projects)

June’26

RSP- COB#7 – By Product Plant -Pkg -4

- Details of the Project

| Date of Approval (dd/mm/yy) | Date of awarding contract (dd/mm/yy) | Original date of Completion (dd/mm/yy) | Revised date of Completion (dd/mm/yy) | Anticipated date of Completion (dd/mm/yy) | Time Overrun (in months) | Original Cost (in Rs. Crore), Net of ITC | Revised cost ( in Rs. Crore) | Anticipated Cost (in Rs. Crore), Net of ITC | Cost Over-run (inRs. Cr.) | Cum. Exp. Till the month (in Rs. Crore), Gross |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |
| Sept’2024 | Oct’24 | March’28 |  | March’28 | - | 1140.07 | - | 1140.07 | - | 165.56 |

- Progress of the Project

| Brief Description of Progress (Main package) | Overall % Target till the month | Cumulative % completion till the month | % target for the month |  | % achievement for the month |
| --- | --- | --- | --- | --- | --- |
| Design & Engineering | 57.96% | 63.97% |  | 6.35% | 6.85% |
| Civil Work (RCC) | 26.08% | 22.42% |  | 2.75% | 122.55% |
| Structural Supply | - | - |  | - | - |
| Structural Erection | - | - |  | - | - |
| Equipment Supply | 3.47% | 19.48% |  | 1.99% | 818.75% |
| Equipment Erection | 0.12% | 0.74% |  | 0.00% | 0.00% |

- Milestones reported on OCMS portal of MoSPI

| Name of the Milestone | Original Start Date | Original Completion Date | Anticipated Start Date | Anticipated Completion Date | Reasons for non-completion (if any) |
| --- | --- | --- | --- | --- | --- |
| Civil Work for Gas Distribution Plant | 24.03.2026 | 05.05.2027 | Actual – 05.12.2025 |  |  |

- Reasons/ Issues/ Constraints for Time & Cost Overrun for the Project

| Name of the Issue/ Constraint | Year | Status | Action Taken by CPSEs | Intervention required at Ministry level |
| --- | --- | --- | --- | --- |

- Key Officials for the Project

- Shri, Surya Kumar Dash, GM (Projects)