June’26

RSP- IMPLEMENTATION OF TREATMENT SYSTEM-2 UNDER ZLD

Details of the Project

| Date of Approval (dd/mm/yy) | Date of awarding contract (dd/mm/yy) | Original date of Completion (dd/mm/yy) | Revised date of Completion (dd/mm/yy) | Anticipated date of Completion (dd/mm/yy) | Time Overrun (in months) | Original Cost (in Rs. Crore), Net of ITC | Revised cost ( in Rs. Crore) | Anticipated Cost (in Rs. Crore), Net of ITC | Cost Over-run (inRs. Cr.) | Cum. Exp. Till the month (in Rs. Crore), Gross |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |
| Feb’2025 | March’25 | Sept’2026 |  | Sept’26 | - | 216.02 | - | 216.02 | - | 117.21 |

- Progress of the Project

| Brief Description of Progress (Main package) | Overall % Target till the month | Cumulative % completion till the month | % target for the month |  | % achievement for the month |
| --- | --- | --- | --- | --- | --- |
| Design & Engineering | 100.00% | 100.00% |  | 0.00% | 0.00% |
| Civil Work (RCC) | 99.16% | 98.25% |  | 0.39% | 14.30% |
| Structural Supply | 100.00% | 100.00% |  | 0.00% | 0.00% |
| Structural Erection | 100.00% | 40.00% |  | 46.00% | 8.70% |
| Equipment Supply | 100.00% | 88.25% |  | 2.11% | 91.67% |
| Equipment Erection | 45.088% | 44.91% |  | 26.32% | 78.00% |

- Milestones reported on OCMS portal of MoSPI

| Name of the Milestone | Original Start Date | Original Completion Date | Anticipated Start Date | Anticipated Completion Date | Reasons for non-completion (if any) |
| --- | --- | --- | --- | --- | --- |
| Civil Work for Common Collection Sump | 12.09.2025 | 08.06.2026 | Started on 12.05.2025 | Actual-16.05.2026 |  |

- Reasons/ Issues/ Constraints for Time & Cost Overrun for the Project

| Name of the Issue/ Constraint | Year | Status | Action Taken by CPSEs | Intervention required at Ministry level |
| --- | --- | --- | --- | --- |

- Key Officials for the Project

- Shri. Vinay Yadav , DGM (Projects)