Annexure – II

Proposals Under tendering

- RSP& OGoM

| Sl. No. | Name of Project | Cost (Net of ITC)/ (ITC value) | SAIL Board Approval | Status/ Reasons for delay in Order placement |
| --- | --- | --- | --- | --- |
| 1 | Transportation of Coal from Coke Oven Battery COB#6 to COB#1-5 along with Installation of Silos. | Rs.323.67 Crore / ( Rs.43.48 Crore) | 28.12.2023 | - Pre-NIT meeting held on 06.02.24, total 7 bidders participated. - NIT issued on 08.02.2024 with TOD of 08.03.2024. - Pre-bid meeting held on 22.02.2024. 8 bidders participated. - TOD extended till 29.03.2024. - Corrigendum w.r.t. Pre-bid queries uploaded and ToD further extended till 12.04.2024. - Tender opened on 12.04.2024, three bids received. Bids are under evaluation. - TER Received from CET on 14.05.2024. - Techno-commercial evaluation completed. - 28.05.2024-TC meeting held. TC recommendation approved on 05.06.2024. - 24.06.2024- Price bids opened. M/s Indure Pvt. Ltd. emerged as L-1 bidder. - 03.07.2024- Price bid evaluation report received from CET. - Price negotiations held with the L-1 bidder on 09.07.2024. - On 15.07.2024, L-1 bidder has submitted price justification. Matter is under discussion by CET with L-1 bidder. - 17.07.2024-The justification/s submitted by the L-1 bidder is forwarded to CET. - 31.07.2024-03.08.2024: Joint meeting held at CET, Ranchi for detail discussion with the L-1 bidder w.r.t. scope and their quoted prices. - 08.08.2024- As per discussions held during the TC meeting, the Consultant-CET is requested to forward their views/ recommendations on the justifications/ documents provided by the L-1 bidder towards further processing of the tender after the joint meeting held at Ranchi. - 12.08.2024-M/s Indure submitted their justification for their quoted prices. The same was forwarded to CET - 23.08.2024-TC meeting held. A Team comprising of members from Projects Deptt., Coke Ovens deptt. and F&A- deptt. of Rourkela Steel Plant shall visit CET, Ranchi to examine and discuss with the Consultant-CET in order to make comparative analysis of the Pkg. Cost estimate vis-a-vis the quoted price of L-1 bidder w.r.t. scope of work mentioned in T.S. & Drg. and submit detailed report to Tender committee - 03.09.2024-04.09.2024-Meeting scheduled to be held at Ranchi. - 06.09.2024-Negotiations held. Party sought time to submit revised offer. Offers awaited from party. - Discounted offer received on 30.09.2024, Price breakup awaited. - 07.10.2024-The L-1 bidder submitted an item-wise price breakup for evaluation - 10.10.2024-TC meeting held. CET has indicated that implication due to increase in the estimated quantity of work (for Civil & Structural). If the same is taken into account, the reassessed cost estimate for the Package would be is 35.04% higher. - 19.10.2024 & 30.10.2024-TC Meeting held. Case shall be referred to consultant CET for reasonability of price. - 02.11.2024- CET for Justification of offer price vs Estimate. - 08.11.2024-Reply from CET received. - Negotiation completed, L-1 price higher than estimate. - TC recommendation for re-tendering approved. - Retendered on 29.03.2025 with ToD scheduled on 26.04.2025. - Pre-bid meeting held on 08.04.2024. with participations of 8 Nos. bidders - Indure Pvt. Ltd. - BTL EPC Ltd. - Macmet Engg. Ltd. - Kalpataru Projects International Ltd. - Macwber Beekay - Mecon Ltd. - SEPC Ltd. (Via VC) - TATA Projects Ltd. (Via VC) - ToD extended upto 14.06.2025. (3rd Extension) - 6 offers received & opened on 14.06.2025. Offers were sent to CET for evaluation. - Proposal for cancellation of tender approved by CA on 28.08.2025. - Revised TS received in Mar’26. - NIT Issued on 06.04.2026 with ToD scheduled on 04.05.2026. Pre-bid meeting scheduled on 16.04.2026. 11 Nos. Bidders Participated - M/s. TKIL Industries Private Limited. (formerly known as M/s. Thyssenkrupp Industries India Private Limited - M/s. BTL EPC Ltd. - M/s. SEPC Ltd. - M/s. Imeco Overseas Pvt. Ltd. - M/s. Macmet Engineering Ltd. - M/s. Hamtek Technologies India Pvt. Ltd. - M/s. Mecon Ltd. - M/s. Engineering Projects India Ltd. - M/s. Reliable Hitech Infrastructure Pvt Ltd. - M/s. The Indure Private Limited. - M/s. Takshvi Infra Pvt Ltd, Engineers & Constructor (wholly owned by Amit Alliance) - TOD Extended upto 18.05.2026. - 18.05.2026-4 offers received & opened - Consortium of M/s. EPIL & M/s. RHIPL - M/s. Hamtek Technologies India Pvt. Ltd., Hyderabad - M/s. Macmet Engineering Ltd. - M/s. BTL EPC Ltd., Kolkata - Technical discussion meeting held at CET, Ranchi from 02.06.2026 to 05.06.2026. - 23.06.2026-TER received from CET. |