Annexure – III

Projects completed during last 10 years

- AMR Projects:

| Sl. No. | Project | Cost (NoC/ Net of ITC) | Expenditure till date | Completed in | Project Closed (FAC) | Details of Dispute(s), if any | Rated capacity/ (achieved or not) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Installation of New HSM at RSP | Net of ITC -3636.95 Gross- 4033.88 | 4177.77 | Jan’2020 (First Coil rolled) | 13.09.2025 |  | Rated capacity-2.94 Mtpa (HR coils) FY22-23: 60% FY23-24: 80% FY24-25: 87% FY25-26: 91% |
| 2 | Installation of Treatment System-1 for Implementation of ZLD at RSP | Net of ITC-141.43 Gross- 158.17 | 165.86 | Dec’23 | 24.07.2025 | - | Commissioned on 26.03.2026 Running at rated capacity of 43 MLD (1800 m3/hr) |
| 3 | Rebuilding of COB#2 | Net of ITC-377.18 Gross- 433.58 | 462.65 | Mar’25 | - | - | Battery is under operation |
| 4 | 30 MLD STP for township | Net of ITC-96.62 Gross- 96.62 | 87.89 | Aug’25 | - | - | Commissioned on 15.08.2025 |
| 5 | Caster-IV | Net of ITC- 970.18 Gross – 1105.23 | 975.66 | 1st Slab Cast on 13.10.2025 | - | - | Commissioned on 21.01.2026 |

- MEP Packages:

| Plant | Total no. of Packages | Completed (Nos.) | FAC issued (Nos.) | Status of Balance Packages |
| --- | --- | --- | --- | --- |
| RSP | 145 | 142 | 142 | - 2 packages were dropped/ foreclosed - 1 under arbitration |