STATUS ON

PHYSICAL & FINANCIAL PROGRESS OF CAPITAL

SCHEMES (costing Rs.50 Crore & above)

FOR PROJECTS COMMITTEE OF SAIL BOARD

(For Review)

(AS ON 30th June’2026)

(Arvind Kumar Singh)

Director (T, P & RM)

## PHYSICAL & FINANCIAL PROGRESS OF CAPITAL SCHEMES

SAIL Board in its 494th meeting held on 20th October, 2022 had desired that “Projects Committee of the SAIL Board (PCSB) shall review the implementation of major projects (costing Rs.50 crore and above) vis-a-vis approved plan and milestone timelines, at regular intervals. The Board be informed of the areas of concern/delay”.

Accordingly, status of Physical and Financial Progress of the On-going capital projects (costing Rs.50 Crore & above) till Mar’2024 is put up for review by PCSB.

- Status of Capital Projects (costing Rs.50 Crore & above)

There are thirty-four (34) projects costing Rs.50 Crore & above, including eight (8) projects on BOO/MDO/COM basis, which are under various stages of execution. The status of these projects is given below:

| Projects on Schedule | 9 |
| --- | --- |
| Projects delayed < 1 Year from Schedule | 1 |
| Projects delayed > 1 Year from Schedule | 0 |
| Total | 10 |

(Rs. Corer)

| Sl. No | Name of the Project | Cost (Net of Cenvat/ITC) / Total Project Cost (TPC) (Date of Stage-II Approval) | Scheduled completion | Expenditure Till Mar’2026 | Revised Completion Schedule | Anticipated completion Schedule |
| --- | --- | --- | --- | --- | --- | --- |
| Rourkela Steel Plant &OGoM |  |  |  |  |  |  |
| 16 | Installation of 1000 tpd O2 Plant on Construct, Operate & Maintain (COM) basis | COM Basis (Aug’2023) | Feb’2026 | - | - | Sept’2026 |
| 17 | Installation of Micro-pellet Plant on Construct and Operate & Maintain (COM) Basis | COM Basis (Jun’24) | Jul’26 | - | - | Jul’26 |
| 18 | Installation of Battery Proper along with Oven Machine and refractory’s: (Package 2) for new stamp charge COB-7 (1 MTPA) | 2312.43/2608.16 (Sept’24) | Mar’28 | 1144.44 | - | Mar’28 |
| 19 | Installation of Coke Dry Cooling Plant (Package: 3). for new stamp charge COB-7 (1 MTPA) | 909.68/1037.57 (Sept’24) | Mar’28 | 73.32 | - | Aug’28 |
| 20 | Installation of By Product Plant (Package: 4) For new stamp charge COB-7 (1 MTPA) | 1005.23/1150.54 (Sept’24) | Mar’28 | 165.56 | - | Mar’28 |
| 21 | 2 MTPA Pellet Plant on COM basis | COM Basis (Jan’25) | Feb’27 | - | - | Feb’27 |
| 22 | Installation of 4th stove for BF#5 | 104.28/120.51 (Jan’25) | Oct’26 | 53.86 | - | Oct’26 |
| 23 | Installation of Treatment System-2 under Zero Liquid Discharge Concept at RSP | 187.29/216.02 (Feb’25) | Sept’26 | 117.21 | - | Sept’26 |
| 24 | (250 + 75/10) T EOT Crane Converter Charging Bay of SMS-2 | 75.87/87.48 (Apr’25) | Nov’26 | 11.90 | - | Nov’26 |
| 25 | Product Testing Laboratory for NPM, SPP & NHSM | 137.99/155.26 (Jun’25) | July’27 | 53.34 | - | Aug’27 |

- Project-wise details are given in the following section:

  - Rourkela Steel Plant &OGoM

| Projects on Schedule | 9 |
| --- | --- |
| Projects delayed < 1 Year from Schedule | 1 |
| Projects delayed > 1 Year from Schedule | 0 |
| Total | 10 |

2.3.5	Installation of 1000 tpd Oxygen Plant on Construct and Operate & Maintain (COM) Basis at RSP

| Stage-I Cost/ RCE of Stage-I cost (Net of Cenvat/ITC) / TPC (Date of Stage-I/ RCE of Stage-I cost Approval) | Stage-II Cost (Net of Cenvat/ITC) / TPC (Date of Stage-II Approval / Sch. Compl.) Sch in Months | Expenditure (Rs. Cr.) |  |  |  |  | Physical Progress % |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Exp. Till FY26 | RE FY26 | Plan Till May’26 | Exp. May’26 | Total Exp. till May’26 | Phy. Prog. Till FY26 | Plan Till May’26 | Act. Till May’26 | Likely Completion (Delay in Months) |
| COM basis (Sept’21) Est. Capex – 425 Cr | COM basis (Aug’23/Feb’26) 29 months | - | - | - | - | - | - | - | - | July’26 (5) |

Reasons for Delay in Stage-I to Stage-II approval:

- Delay in issuance of NIT: This being first project based on COM Basis, M/s MECON was appointed as the Consultant in Nov’2021 for preparation of Comprehensive Tender Document with legal vetting. Subsequently, NIT was issued.

- Numerous deviations to NIT terms were retained by bidders.

- Multiple rounds of   techno-commercial discussions held with bidders via physical/online/Email mode for withdrawal of deviations.

The project is being implemented on COM basis.

- Contract signed with M/s Linde India Ltd. on 29.11.2023 with effective date of contract as 24.09.2023

- Area survey, underground mapping, Soil testing & area levelling completed

  - Order has been placed for all long lead critical equipment viz. MAC, BAC, Horton’s Sphere, Booster after cooler, CS Plates for storage tanks, Refrigeration unit, and direct contact air cooler.

- Over all Progress till June’26 : 93 %

- Civil Work Completed.

- Mechanical Works:

  - Completed for Cooling tower, Cold box ,Main heat Exchanger, cooling tower, pre-purifications units, seal gas tank, LAR tank

  - Erection activities for Horton Sphere, LOX & LIN tanks, vaporizers under progress. Pneumatic test of pipes of cold box under progress.

- Piping Works: Underground piping completed; above-ground piping is under progress.

- Electrical Works: 30 MVA HT transformer erections done, LT Transformer-6 nos. erection done, Panel Erection & cable tray work completed. Cooling tower, Bus duct & Instrumentation, Cable Laying, Testing of Transformer, Earthing work under progress.

Issues:

Initial delay in start of civil work-

- Though contract was effective from 24.09.2023, order for civil sub-contractor was placed by M/s Linde only on 05.07.2024 and civil works commenced on 22.07.2024 resulting in a delay of about 10 months in start of civil activities.

Inadequate mobilisation of resources

- Lack of round-the-clock working and delayed mobilisation of critical resources, including cranes required for erection of Horton Spheres, LOX/LIN/:AR tanks, and Cold Box structures, adversely affected major erection activities.

- Inadequate availability of specialised aluminium welders for Cold Box and cryogenic piping, as well as welders for Horton Sphere welding, restricted site progress and prevented extended working hours.

- Delay in finalisation of sub-contractors for electrical, instrumentation, piping, and piping works and subsequent mobilisation has impacted the progress at several fronts.

Delay in engineering and supply of critical equipment

- Delayed supply of critical equipment such as MAC-1, vaporisers (LOX & LIN), HT motors for MAC, seal gas tank, etc., against the supply schedule furnished by M/s Linde under the COM contract.

- Movement of supplied piping materials back to workshops for modification and assembly further affected erection schedules.

Increase in excavation scope due to site conditions

- Higher-than-anticipated excavation quantities due to actual contour variations increased earthwork scope and extended the duration of site preparation.

- Encounter of hard rock at surface level in several areas led to additional rock breaking, affecting foundation readiness and civil work progress especially construction of  electrical building, MAC & BAC foundations

Actions Taken:

- Continuous follow-ups with M/s Linde have been undertaken to address the issues of inadequate resource mobilisation and delays in supply of critical equipment. Repeated deliberations, escalations, and formal communications have been carried out through periodic review meetings. M/s Linde was advised to furnish updated schedules, monthly execution plans, and credible recovery programmes; however, in view of the COM nature of the contract, detailed L-2 schedules were not provided, and monitoring remained dependent on the contractor’s internal planning.

- In the ED(Projects) review meeting held on 15.01.2026, M/s Linde presented a revised action plan indicating commissioning by July’25. M/s Linde was advised to rework the plan with enhanced manpower and resources, ensure simultaneous execution at all available fronts, and strictly monitor the supply of balance equipment to target completion by June’26.

- Further, in the ED(Projects) review meeting held on 17.03.2026, M/s Linde was directed to submit a detailed micro-level execution plan and implement round-the-clock working with adequate resource augmentation to complete the project by June’26.

- In the ED(Projects) review meeting held on 21.04.2026, M/s Linde was directed to to ensure delivery of oxygen by July’2026.

- Further, in the ED(Projects) review meetings held during Mar'26, & Apr'26, M/s Linde was directed to implement round-the-clock working with adequate resource augmentation to ensure delivery of oxygen by July'26. M/s Linde was also advised to prepare a detailed micro-plan for instrumentation loop checking, interlocks, automation and other commissioning activities.

- Further, while pursuing expeditious commissioning of the facilities, discussions were held with the senior management of M/s Linde on 09.06.2026 and 10.06.2026. During the discussions, M/s Linde informed that certain installations critical to commissioning of the facilities would require additional time owing to the complexities involved in their installation and commissioning. However, the senior management of M/s Linde assured RSP that the facilities would be commissioned by Sept'26

Summary of Communications & Meetings

    - Review Meetings by ED (Projects): 24.08.2024, 18.09.2024, 22.01.2025, 25.02.2025, 26.03.2025, 17.04.2025, 05.06.2025, 28.06.2025, 30.07.2025, 01.09.2025, 16.10.2025, 15.01.2026, 17.03.2026, 21.04.2026, 10.06.2026.

    - Review Meetings by CGM/GM (Projects): 13.12.2024, 08.05.2025, 13.06.2025, 18.07.2025, 13.08.2025, 16.09.2025, 10.12.2025, 14.02.2026, 11.03.2026

    - Email Communications: 30.05.2025, 09.08.2025

    - Extensive Review Meetings by Project Manager: Conducted regularly with persistent follow-ups.

2.3.6	Installation of Micro-pellet Plant on Construct and Operate & Maintain (COM) Basis at RSP

| Stage-I Cost/ RCE of Stage-I cost (Net of Cenvat/ITC) / TPC (Date of Stage-I/ RCE of Stage-I cost Approval) | Stage-II Cost (Net of Cenvat/ITC) / TPC (Date of Stage-II Approval / Sch. Compl.) Sch in Months | Expenditure (Rs. Cr.) |  |  |  |  | Physical Progress % |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Exp. Till FY26 | RE FY26 | Plan Till June’26 | Exp. June’26 | Total Exp. till June’26 | Phy. Prog. Till FY26 | Plan Till June’26 | Act. Till June’26 | Likely Completion (Delay in Months) |
| COM basis (Jun’23) | COM basis (Jun’24/July’26) 24 Months | - | - | - | - | - | - |  |  | - |

The project is being implemented on COM basis.

- Contract signed on 29.08.2024.

- Area Survey & Soil testing job completed.

- Clearance for Layout drawing given on 29.01.2025.

- Overall Progress till June’26 : 94.80%

- Design & Engineering completed.

- Major long lead Equipments-Eirich mixer, slewing & luffing conveyor delivered at site in Dec’25.

- Civil Work completed.

- Structural work

    - Completed: Shed#1, Shed#2, and Product Conveyor.

    - Under progress for Shed#3

- Equipment Work

    - Mechanical Erection completed.

    - Trial and testing of Mixers & Conveyor Done on 01.06.2026

    - All Statutory clearances received (CEA, Consent to Operate from SPCB, Licence to Operate from Directorate of Factories & Boiler).

    - Erection of all critical equipments completed.

    - CEA clearance received on 19.06.2026.

    - Transformer charging done. Weigh bridge calibration done.

    - Trial and testing of all equipments done, plant is in process of stabilisation for delivery of final product.

2.3.7	Installation of Battery Proper along with Oven Machine and refractories: (Package 2) for new stamp charge COB-7 (1 MTPA)

| Stage-I Cost/ RCE of Stage-I cost (Net of Cenvat/ITC) / TPC (Date of Stage-I/ RCE of Stage-I cost Approval) | Stage-II Cost (Net of Cenvat/ITC) / TPC (Date of Stage-II Approval / Sch. Compl.) Sch in Months | Expenditure (Rs. Cr.) |  |  |  |  | Physical Progress % |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Exp. Till FY26 | BE FY26 | Plan Till June’26 | Exp. June’26 | Total Exp. till June’26 | Phy. Prog. Till FY26 | Plan Till June’26 | Act. Till June’26 | Likely Completion (Delay in Months) |
| Rs 2566.80/2882.53 April’22 | Over All COB#7- Rs 4227.34/4796.27 (Sept’24/Mar’28) Package-2 (2288.68/2584.41) | 768.38 | 700.0 | 150 | 376.06 | 1144.44 | 36.69 | 20.92 | 13.80 | - |

- Contract Signed on 07.10.2024 with M/s L&T & M/s Thyssenkrupp

- Area survey completed.

- 1st & 2nd milestone payment done.

- 20.01.2025-22.01.2025-Engineering meetings held

- Design & Engg. Under progress.

- Piling work (1773 nos. completed out of 1847 nos. as on 30.06.2026)

    - Piling work in Test Piles (05 nos.), Coal silo area (197 nos.), Battery#7A (253 nos.), Battery#7B (250 nos.), Buttress Wall 7A (48 nos.), Buttress Wall 7B (48 nos.), Coal Tower (156 nos.), Intermediate Bench (22 nos.), Stack Flue Tunnel (38 nos.), End Bench 7B (48 nos.), Pipe rack stockade (40 nos.), NTP#1 (8 nos.), Primary Crusher House (17 nos.) and Intermediate Storage Hopper Building (21 nos.) Hammer Exchange Building (34/34), Conveyor Y7 (12/12) completed.

    - Piling work under progress in Coke bucket car Track, End Bench-7A, Pushing Emission Control System (PECS) , Stamp Charging Pushing Machine (SCPM)  Track, Coke Bucket Repair Station, Existing Crusher House,  etc

- Civil work of, Waste gas tunnel, Common flue tunnel 7A&7B, Pushing Emission Control System (PECS) stack foundation, secondary crusher house, LBDS-20, Stamp Charging Pushing Machine (SCPM) Track, Coke Bucket Car Track, (HPALA) Building, control room, BC 309A & 309C, BF gas pipeline footing, Switchgear Control House – Electrical Control Room (SCH ECR), Media tunnel, Conveyor Y13, Conveyor Y14 tunnel,  under progress.

- Civil work Completed of Coal Handling silo-6 nos., deck slab & buttress wall of Battery#7A & Battery #7B side, Coal Tower, Conveyor Y1–Y2, Compressor room for Silo, Waste Gas Channel 7A, Ramp of Overhead storage Hopper etc

- TOPR(Temporary Oven Protection Roof) erection along with sheeting completed for Battery#7A side. TOPR erection completed for Battery#7B side, sheeting under progress

- All major equipments order placed. Supply of major equipments like Primary, Secondary crusher and Stamping, Charging & Pushing Machine done.

- Refractory Supply under progress.

- Structural Erection under progress: Compressor Room, CI bend erection, SCPM Track, cable gallery(MSDS-3 to MSDS-6), Y1 –Y2  Conveyor system , NTP-1, NTP-2.,Cable gallery from MSDS-3 –MSDS 6 .

- Mechanical erection under progress (5MT EOT crane  Battery#7B completed)

- Physical Progress:

| Activity | Cumulative Plan till June’26 | Cumulative Achieved till June’26 |
| --- | --- | --- |
| Design & Engg. | 96.59% | 90.15% |
| Civil | 65.84% | 64.68% |
| Structural Supply | 77.62% | 53.15% |
| Structure Erection | 18.86% | 18.47% |
| Refractory Supply | 78.35% | 64.93% |
| Electrical Supply | 47.74% | 44.52% |
| Mechanical Supply | 47.47% | 46.77% |
| Mechanical Erection | 1.91% | 0.99% |

2.3.8	Installation of Coke Dry Cooling Plant (Package: 3). for new stamp charge COB-7 (1 MTPA)

| Stage-I Cost/ RCE of Stage-I cost (Net of Cenvat/ITC) / TPC (Date of Stage-I/ RCE of Stage-I cost Approval) | Stage-II Cost (Net of Cenvat/ITC) / TPC (Date of Stage-II Approval / Sch. Compl.) Sch in Months | Expenditure (Rs. Cr.) |  |  |  |  | Physical Progress % |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Exp. Till FY26 | BE FY26 | Plan Till June’26 | Exp. June’26 | Total Exp. till June’26 | Phy. Prog. Till FY26 | Plan Till June’26 | Act. Till June’26 | Likely Completion (Delay in Months) |
| Rs 2566.80/2882.53 April’22 | Over All COB#7 Rs 4227.34/4796.27 (Sept’24/Mar’28) Package -3 ( 943.90/ 1064.55) | 36.66 | 100.00 | 42.00 | 36.66 | 73.32 | - | - | - | - |

- Contract Signed on 05.10.2024 with M/s BEC Ltd., M/s Giprokoks & M/s CUI.

- Area survey completed.

- General Layout drawing approved.

- Design & Engg. Under progress.

- M/s BEC Ltd. has been banned with effect from 03.06.2025. Alternate options are being explored.

- Contract was terminated and subsequently re-tendered on 27.08.2025. 	Pre-bid meeting held on 03.09.2025. 5 Parties participated. Clarifications received from the Ministry of Steel (MoS) regarding DMISP policy. 2 offers received & opened on 17.10.2025 and sent to CET for evaluation. TER received from CET on 06.12.2025.

- The price bid was opened on 23.12.2025. M/s L&T and Consortium emerged as the sole bidder. Quoted price is 2.78% higher than the corresponding estimate

- 3 rounds of negotiations held (1st-26.12.2025, 2nd-06.01.2026 & 3rd-08.01.2026). The consultant – CET submitted PBER on 09.01.2026. As per the PBER, the evaluated price is 2.26% higher than the estimated.

- TC in its meeting held on 09.01.2026 recommended for placement of order on which was approved by CA on 09.01.2026. Board Note finalised on 13.01.2026 and approved by CA on 13.01.2026.

- Proposal for order placement sent to Corporate Office on 13.01.2026.

- Corporate PAG meeting held on 20.01.2026. PAG queries received on 21.01.2026, complied on 23.01.2026 and 27.01.2026(legal opinion received from corporate law on 27.01.2026).

- EC in its meeting held on 05.02.2026 accorded approval for award of work. Sanction received on 06.02.2026.

- LoA issued on 07.02.2026.

- Contract signed on 20.02.2026 for Coke Dry Cooling Plant of Coke Oven Battery No. 7 with the Consortium of Larsen & Toubro Limited & State Institute for Designing Enterprises of Coke Oven and By-Product Plants LLC (JV “GIPROKOKS” LLC). Scheduled completion-20.08.2028.

- Kick Off meeting held on 20.02.2026.

- 1st milestone (M1) achieved & payment done in Mar’26.

- Design & Engineering under Progress

- Ground Breaking Done on 28.05.2026.

2.3.9	Installation of By Product Plant (Package: 4) for new stamp charge COB-7 (1 MTPA)

| Stage-I Cost/ RCE of Stage-I cost (Net of Cenvat/ITC) / TPC (Date of Stage-I/ RCE of Stage-I cost Approval) | Stage-II Cost (Net of Cenvat/ITC) / TPC (Date of Stage-II Approval / Sch. Compl.) Sch in Months | Expenditure (Rs. Cr.) |  |  |  |  | Physical Progress % |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Exp. Till FY26 | BE FY26 | Plan Till June’26 | Exp. June’26 | Total Exp. till June’26 | Phy. Prog. Till FY26 | Plan Till June’26 | Act. Till June’26 | Likely Completion (Delay in Months) |
| Rs 2566.80/2882.53 April’22 | 4227.34/4796.27 (Sept’24/Mar’28) Package-4 (994.76/1140.07) | 58.90 | 315.0 | 30.00 | 106.66 | 165.56 | 11.63 | 4.81 | 9.57 | - |

- Contract Signed on 04.10.2024 with M/s Hutni Projekt Frydek-Mistek, Czech Republic & M/s Hutni Projects India

- Area survey, soil investigation & underground mapping completed

- Design & Engg. under progress. (Basic Engineering completed, Detail Engineering under progress)

- Area leveling completed.

- Civil work

  - Completed:- LCSS-1 building, Exhauster machine foundation & Slab, PGC foundation, Tar Separator Plant (TSP) & Detarred Ammonia Plant (DAP) foundation, Tar tank foundation in old CCD Site B, Tar separator, Coarse Condensation Plant(Decanter, Workshop building, Gas Liquor Tank

  - Under progress in Gas Distribution Plant)BOD & ZLD area (Clariflocculator, Equalization Tank , Aeration Tank), cooling tower, Scrubbing plant, Electrostatic Tar  Precipitator, LCSS 2

- Supply: All imported equipment, including the Exhauster, Tail Gas Analyzer, and Start-up Burner, as well as indigenous equipment such as the Exhauster Motor and VAM Machine, has been delivered to site.

- Mechanical work under progress in Tar Tank in Old & New CCD Site, & DAP tank, Gas Liquor Tank.

- Physical Progress:

| Activity | Cumulative Plan till June’26 | Cumulative Achieved till June’26 |
| --- | --- | --- |
| Design & Engg. | 57.96% | 63.97% |
| Civil | 26.08% | 22.42% |
| Equipment Supply | 3.47% | 19.48% |
| Equipment Erection | 0.12% | 0.74% |

2.3.10 Installation of 2 MTPA Pellet Plant on COM basis.

| Stage-I Cost/ RCE of Stage-I cost (Net of Cenvat/ITC) / TPC (Date of Stage-I/ RCE of Stage-I cost Approval) | Stage-II Cost (Net of Cenvat/ITC) / TPC (Date of Stage-II Approval / Sch. Compl.) Sch in Months | Expenditure (Rs. Cr.) |  |  |  |  | Physical Progress % |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Exp. Till FY26 | BE FY26 | Plan Till June’26 | Exp. June’26 | Total Exp. till June’26 | Phy. Prog. Till FY26 | Plan Till June’26 | Act. Till June’26 | Likely Completion (Delay in Months) |
| COM basis (Oct’21) | COM basis (Mar’25/Feb’27) 24 Months | - | - | - | - | - | - | - | - | - |

- Contract Signed on 14.02.2025 with Consortium of M/s Odisha Metaliks & Rosemary Sponge & M/s Ispat Private Limited

- Area grading, removal of overburden (1.5 lakh cubic meters) and underground mapping completed.

- Overall Progress till June’26: 84.78%

- Design & Engineering Completed.

- Major civil work completed.

- Equipment supply under progress.(approx 80% completed)

- Structural erection completed for the ESP, Concentrate shed, etc while structural erection is under progress in the PD Building, Filter Press Building, TG Building and Grinding Building.

- Equipment erection completed for the Annular Cooler/Rotary Kiln, TG Building, both thickeners, Balling Mill and Screens, while equipment erection is under progress in the ESP, Filter Press Building, Grinding Building (Hydro cyclone), etc.

- Refractory work under progress in Duct Lines Cooler, Rotary Kiln, TG unit, Chimney.

2.3.11 Installation of 4th Stove for BF-5

| Stage-I Cost/ RCE of Stage-I cost(Net of Cenvat/ITC) / TPC (Date of Stage-I/ RCE of Stage-I cost Approval) | Stage-II Cost (Net of Cenvat/ITC) / TPC (Date of Stage-II Approval / Sch. Compl.) Sch in Months | Expenditure (Rs. Cr.) |  |  |  |  | Physical Progress % |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Exp. Till FY26 | BE FY26 | Plan Till June’26 | Exp. June’26 | Total Exp. till June’26 | Phy. Prog. Till FY26 | Plan Till June’26 | Act. Till June’26 | Likely Completion (Delay in Months) |
| 65.00/74.82 Jan’22/Dec’23 (for change in schedule) 66.77/76.59 | 104.28/120.51 (Mar’25/Oct’26) 20 Months | 22.74 | 55.00 | 15.00 | 31.12 | 58.86 | 38.60 | 38.09 | 14.81 | - |

- Contract Signed on 10.02.2025 with M/s Primetals Technologies India Pvt. Ltd.

- M1 & M2 Payment done in April’25

- Design & Engineering completed

- Civil work completed for Gas Analyzer room & valve stand and under progress for duct foundation.

- All 16 Nos. tier stove shells and 10 nos. domes delivered,

- All 16 nos. stove shells erection completed, D1 erection done, balance domes assembly under progress

- Major Equipment- Imported stove valves, Hydraulic Stand, Automation Control Desk, AMCC (Auxiliary Motor Control Centre), and Analyzer Panel Delivered on site.

- Refractory supply under progress.

Physical Progress:

| Activity | Plan till June’26 (%) | Achieved till June’26 (%) |
| --- | --- | --- |
| Design &Engg. (Nos.) | 100.00% | 100.00% |
| Civil | 100% | 98.61% |
| Structural Supply | 57.14% | 0% |
| Structural Erection | 50.00% | 0% |
| Equipment Supply | 88.86% | 75.19% |
| Equipment Erection | 55.44% | 33.92% |
| Refractory Supply | 100% | 58.50% |
| Refractory Erection | 18.38% | 0% |

- During ED(Projects) review meeting held on 09.04.2026 M/s Primetals was advised to submit detailed micro-level execution plan including make-up plan and implement round-the-clock working with adequate resource augmentation, ensure simultaneous execution at all available fronts to complete the project as per schedule.

- In subsequent review meetings held on 26.05.2026 and 24.06.2026, M/s Primetals proposed a two-stage leakage testing approach to facilitate parallel execution. M/s Primetals were advised to submit a detailed execution methodology, a revised activity-wise schedule for completion of the balance mechanical and refractory works, and a resource-backed recovery plan with round-the-clock deployment to recover delays and achieve the project milestones.

2.3.12 Implementation of Treatment System-2 under ZLD

| Stage-I Cost/ RCE of Stage-I cost (Net of Cenvat/ITC) / TPC (Date of Stage-I/ RCE of Stage-I cost Approval) | Stage-II Cost (Net of Cenvat/ITC) / TPC (Date of Stage-II Approval / Sch. Compl.) Sch in Months | Expenditure (Rs. Cr.) |  |  |  |  | Physical Progress % |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Exp. Till FY26 | BE FY26 | Plan Till June’26 | Exp. June’26 | Total Exp. till June’26 | Phy. Prog. Till FY26 | Plan Till June’26 | Act. Till June’26 | Likely Completion (Delay in Months) |
| 156.22/177.22 June’21/ | 187.29/216.02 (Feb’25/Sept’26) 18 Months | 83.65 | 90.0 | 27.00 | 33.56 | 117.21 | 67.55 | 24.09 | 15.64 | - |

- Contract Signed on 12.03.2025 with Consortium of M/s Effwa Infra & Research Pvt.Ltd., Thane  & M/s SMC Resources SDN, Malaysia

- 1st & 2nd milestone(M1 & M2) completed

- Design & Engg completed.

- Pilling work (508 nos.)  Completed.

- Civil work completed for Common collection Sump area(CCS) & Filtration area, Electrical Building ,Ultra Filtration (UF-RO) Pump House (SMS-II), Treated Water Storage Tank, RO Feed Tank , RO reject Tank,  UFRO(TS-2). Filter Press Building,  Secure Landfill (SLF)

- Civil work under progress for  Emergency Over Head Tank, Equalization Tank, Chemical Building, , Dyke area,  PBS Pump House, Clear water storage tank, UF Feed Tank,  etc

- Mechanical erection completed for the Mechanical Gravity Filter (MGF), Common Collection Sump, UF-RO Pump House (SMS-II), while mechanical erection is under progress in the UF-RO Pump House(TS-2), UF-RO Pump House (PBS) etc

- Pipeline laying work under progress.

- Transformer erection Completed, earthing & incomer cabling under progress. Electrical erection completed for the UF-RO Pump House (SMS-II), while electrical erection is under progress in the Electrical Building, UF-RO Pump House (PBS), Common Collection Sump, UF - RO Pump House(TS-2).

- Physical Progress:

| Activity | Plan till June’26 (%) | Achieved till June’26 (%) |
| --- | --- | --- |
| Design &Engg. (Nos.) | 100.00% | 100.00% |
| RCC (Cum) | 99.16% | 98.25% |
| Structure Supply | 100.00% | 100.00% |
| Structure Erection | 100.00% | 40.00% |
| Equipment supply | 100.00% | 88.25% |
| Equipment Erection | 45.09% | 44.91% |

2.3.13 Replacement of (250 + 75/10) T EOT Crane Converter Charging bay Bay of SMS-2

| Stage-I Cost/ RCE of Stage-I cost (Net of Cenvat/ITC) / TPC (Date of Stage-I/ RCE of Stage-I cost Approval) | Stage-II Cost (Net of Cenvat/ITC) / TPC (Date of Stage-II Approval / Sch. Compl.) Sch in Months | Expenditure (Rs. Cr.) |  |  |  |  | Physical Progress % |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Exp. Till FY26 | BE FY26 | Plan Till June’26 | Exp. June’26 | Total Exp. till June’26 | Phy. Prog. Till FY26 | Plan Till June’26 | Act. Till June’26 | Likely Completion (Delay in Months) |
| 65.04/74.61 July’24/ | 75.87/87.48 (April’25/Nov’26) 18 Months | 10.12 | 47.0 | 35.00 | 1.78 | 11.90 | 9.19 | 0.81 | 0.81 | - |

- Contract Signed on 28.05.2025 with M/s Anupam Industries Limited, Ahmedabad

- 1st & 2nd milestone(M1 & M2) completed & payment done

- Design & Engineering completed

  - Manufacturing.

- Electrical Drive & PLC Panel inspection was carried out at M/s ABB works from 19th to 21st May’2026.

- Inspection of the complete mechanical assembly along with no-load trial was carried out at M/s Anupam works from 19th to 21st May’2026.

- Wiring & cabling under progress for testing with new panels.

2.3.14. Product Testing Laboratory for NPM, SPP & NHSM

| Stage-I Cost/ RCE of Stage-I cost (Net of Cenvat/ITC) / TPC (Date of Stage-I/ RCE of Stage-I cost Approval) | Stage-II Cost (Net of Cenvat/ITC) / TPC (Date of Stage-II Approval / Sch. Compl.) Sch in Months | Expenditure (Rs. Cr.) |  |  |  |  | Physical Progress % |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Exp. Till FY26 | BE FY26 | Plan Till June’26 | Exp. June’26 | Total Exp. till June’26 | Phy. Prog. Till FY26 | Plan Till June’26 | Act. Till June’26 | Likely Completion (Delay in Months) |
| 164.40/186.80 Dec’23 | 137.99/155.26 (June’25/Aug’27) 25 Months | 27.94 | 50.00 | 9.00 | 25.4 | 53.34 | 28.76 | 15.29 | 23.81 | - |

- Contract signed on 04.07.2025.

- Design & Engineering under Progress.

- 1st milestone (M1) completed & payment done in Dec’25.

- Ground Breaking done on 03.11.2025.

- Enabling activities completed in Dec’25.

- Civil work completed for Parking shed & Scrap Shed and under progress for Main Lab Building, macro etching lab and  Drop weight tear test(DWTT) Building, MCC Building

- Supply of equipments under progress. (X-Ray Fluorescence Analyzer (XRF), Optical Emission Spectrometer (OES), Profile Projector, Image Analyzer, Transformer, Vertical Milling Machine, Field Emission Scanning Electron Microscope (FESEM), Hardness Testing Machine, CNC & Conventional Lathes, Band Saw Machines, Vertical Drilling Machine, Grinding & Polishing Equipment, Oxygen/Nitrogen/Hydrogen Analyzer, Carbon/Sulphur Analyzer, Microscopes, Ultrasonic Flaw Detectors, Thickness Gauge, Electrical Steel Tester, Insulation Resistivity Tester, Stacking Factor Tester, Precision Balances, pH & Conductivity Meters, etc.

- Physical Progress:

| Activity | Plan till June’26 (%) | Achieved till June’26 (%) |
| --- | --- | --- |
| Design &Engg. (Nos.) | 93.75% | 87.50% |
| RCC (Cum) | 40.25% | 47.51% |
| Structure Supply | 100.00% | 100.00% |
| Structure Erection | 24.00% | 92.00% |
| Equipment supply | 35.56% | 37.78% |